## const_CMY_Area
GIS DATA CHANGES
ELM GIS DATA CHANGE
Feature Class Changed:
const_CMY_Area
Feature Class Updated Details | [5 empty] | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Change Reason | 0 | 0 | 2
Lugo Substation | Laydown yard: Lugo II | 1 | Lugo | Modify | Moved yard to open area in substation
Mid-line Series Capacitors | Laydown yard: Ludlow Series Capacitor | 1 | Ludlow | Modify | Moved yard to single parcel
WP_ELMSC | Change Yard_ID from "Newberry" to "Newberry Springs" | 1 | Newberry Springs | N/A | Per CPUC Request

## const_Construction_Area
GIS DATA CHANGES
ELM GIS DATA CHANGE
Feature Class Changed:
const_Construction_Area
Feature Class Updated Details | [5 empty] | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Change Reason | 19 | 24 | 57
Transmission: OPGW | Pull site: EM-2 (for M0-T1) | 1 | Moh-Eld | Delete | Removed OPGW work area. Use substation work area
Repeater Sites | Distribution work area | 1 | Kelbaker: Distribution | Modify | Modified work area to close void between work areas per Contractor & to reduce impacts to JD waterways
Repeater Sites | Telecom work area | 1 | Kelbaker: Telecommunication | Modify | Modified work area to close void between work areas per Contractor & to reduce impacts to JD waterways
Repeater Sites | Distribution work area | 1 | Lanfair: Distribution | Modify | Modified work area to reduce impacts to JD waterways
Repeater Sites | Telecom work area | 1 | Lanfair: Telecommmunication | Modify | Modified work area to reduce impacts to JD waterways
Transmission: OPGW | Landing Zone: LZ_11 | 1 | Lugo-Moh | Delete | Removed per landowner request
Transmission: OPGW | Landing Zone: LZ_119 | 1 | Lugo-Moh | Delete | Removed per MNP request
Transmission: OPGW | Landing Zone: LZ_120 | 1 | Lugo-Moh | Delete | Removed per MNP request
Transmission: OPGW | Landing Zone: LZ_158 | 1 | Lugo-Moh | Delete | Removed per BLM request
Transmission: OPGW | Landing Zone: LZ_202 | 1 | Lugo-Moh | Delete | Removed per BLM request
Transmission: OPGW | Landing Zone: LZ_205 | 1 | Lugo-Moh | Delete | Removed per BLM request
Transmission: OPGW | Landing Zone: LZ_208 | 1 | Lugo-Moh | Delete | Removed per BLM request
Transmission: OPGW | Landing Zone: LZ_30 | 1 | Lugo-Moh | Delete | Removed per BLM request
Transmission: OPGW | Landing Zone: LZ_69 | 1 | Lugo-Moh | Delete | Removed per BLM request
Transmission: OPGW | Landing Zone: LZ_79 | 1 | Lugo-Moh | Delete | Removed per BLM request
Transmission: OPGW | Landing Zone: LZ_80 | 1 | Lugo-Moh | Delete | Removed per BLM request
Transmission: OPGW | Landing Zone: LZ_81 | 1 | Lugo-Moh | Delete | Removed per BLM request
Transmission: OPGW | Site access: M105-T2 SA-BS1 | 1 | Lugo-Moh | Delete | Deleted and replaced by updated shape (with "M105-T2 STR-BS1" modification)
Transmission: OPGW | Pull site: M105-T2 STR-BS1 | 1 | Lugo-Moh | Modify | Work area moved to avoid ESA per BLM request
Transmission: OPGW | Pull site: M118-T1 STR-AS1 | 1 | Lugo-Moh | Modify | Work area modified by Contractor
Transmission: OPGW | Pull site: M118-T2 STR-BS1 | 1 | Lugo-Moh | Modify | Work area modified by Contractor
Transmission: OPGW | Structure work area: M14-T3 SWA | 1 | Lugo-Moh | Delete | Removed alternative infraction work area. GIS cleanup
Transmission: OPGW | Structure work area: M22-T4 SWA | 1 | Lugo-Moh | Modify | Work area modified to include structure footprint by Contractor
Transmission: OPGW | Pull site: M29-T4-STR-BS1 | 1 | Lugo-Moh | Add | Added shape to renplaceshape "M29-T3" to "M29-T4". GIS cleanup.
Transmission: OPGW | Pull site: M29-T3 STR-BS1 | 1 | Lugo-Moh | Delete | Incorrectly labeled shape deleted
Transmission: OPGW | Pull site: M2-T1 STR-AS1 | 1 | Moh-Eld | Modify | Work area moved to previously disturbed area by Contractor
Transmission: OPGW | Pull site: M2-T1 STR-BS1 | 1 | Moh-Eld | Modify | Work area modified by Contractor
Transmission: OPGW | Structure work area: M36-T3 SWA | 1 | Lugo-Moh | Modify | Structure work area expanded to include roadway by Contractor
Transmission: OPGW | Pull site: M40-T1 STR-BS1 | 1 | Moh-Eld | Modify | Structure work area moved to flatter area by Contractor
Transmission: OPGW | Structure work area: M40-T1 SWA | 1 | Lugo-Moh | Modify | Structure work area expanded to include roadway by Contractor
Transmission: OPGW | Pull site: M42-T4 STR-AS1 | 1 | Lugo-Moh | Modify | Modified work area to reduce impacts to JD waterway
Transmission: OPGW | Pull site: M42-T4 STR-BS1 | 1 | Lugo-Moh | Modify | Work area moved closer to structure by Contractor
Transmission: OPGW | Structure work area: M42-T4 SWA | 1 | Lugo-Moh | Modify | Structure work area expanded to include roadway by Contractor
Transmission: OPGW | Structure work area: M46-T2 SWA | 1 | Lugo-Moh | Modify | Structure work area expanded to include roadway by Contractor
Transmission: OPGW | Structure work area: M49-T3 SWA | 1 | Lugo-Moh | Modify | Structure work area expanded to include roadway by Contractor
Transmission: Infraction | Foundation work area: M4-T1 FNDN | 1 | Moh-Eld | Add | Added foundation work area per Contractor's design
Transmission: OPGW | Site access: M56-T2 SA-AS1 | 1 | Lugo-Moh | Modify | Site access modified to overlap existing roadway by Contractor
Transmission: OPGW | Structure work area: M59-T3 SWA | 1 | Lugo-Moh | Modify | Structure work area expanded to include roadway by Contractor
Transmission: OPGW | Site access: M63-T1 SA-AS1 | 1 | Lugo-Moh | Modify | Site access modified to overlap work area by Contractor
Transmission: OPGW | Structure work area: M63-T1 SWA | 1 | Lugo-Moh | Modify | Structure work area expanded to include roadway by Contractor
Transmission: OPGW | Structure work area: M63-T4 SWA | 1 | Eld-Lugo | Delete | Removed alternative infraction work area. GIS cleanup.
Transmission: Interconnect | Structure work area: M67-T6 SWA | 1 | Newberry Springs | Add | Added structure work area for OH conductor work per design & Contractor
Transmission: Interconnect | Equipment setup: M67-T6 | 1 | Newberry Springs | Add | Added equipment setup area for OH conductor work per design & Contractor
Transmission: Interconnect | Structure work area: M68-T1 SWA | 1 | Newberry Springs | Add | Added structure work area for OH conductor work per design & Contractor
Transmission: Interconnect | Equipment setup: M68-T1 | 1 | Newberry Springs | Add | Added equipment setup area for OH conductor work per design & Contractor
Transmission: Interconnect | Equipment setup: M68-T2 | 1 | Newberry Springs | Add | Added equipment setup area for OH conductor work per design & Contractor
Transmission: Interconnect | Equipment setup: M68-T3 | 1 | Newberry Springs | Add | Added equipment setup area for OH conductor work per design & Contractor
Transmission: Interconnect | Structure work area: M68-T4 SWA | 1 | Newberry Springs | Add | Added structure work area for OH conductor work per design & Contractor
Transmission: Interconnect | Equipment setup: M68-T4 | 1 | Newberry Springs | Add | Added equipment setup area for OH conductor work per design & Contractor
Transmission: Interconnect | Structure work area: M68-T5 SWA | 1 | Newberry Springs | Add | Added structure work area for OH conductor work per design & Contractor
Transmission: Interconnect | Equipment setup: M68-T5 | 1 | Newberry Springs | Add | Added equipment setup area for OH conductor work per design & Contractor
Transmission: Interconnect | Structure work area: M68-T1 SWA | 1 | Ludlow | Modify | Structure work area expanded to include roadway by Contractor
Transmission: Interconnect | Structure work area: M68-T2 SWA | 1 | Ludlow | Add | Structure work area expanded to include roadway by Contractor
Transmission: Interconnect | Structure work area: M68-T3 SWA | 1 | Ludlow | Add | Added structure work area for OH conductor work per design & Contractor
Transmission: Interconnect | Equipment setup: M68-T3 | 1 | Ludlow | Add | Added equipment setup area for OH conductor work per design & Contractor
Transmission: Interconnect | Equipment setup: M68-T4 | 1 | Ludlow | Add | Added equipment setup area for OH conductor work per design & Contractor
Transmission: Interconnect | Equipment setup: M69-T1 | 1 | Ludlow | Add | Added equipment setup area for OH conductor work per design & Contractor
Transmission: OPGW | Pull site: M68-T4 STR-BS1 | 1 | Lugo-Moh | Add | Relocated work area from M69-T1 per SCE design change
Transmission: OPGW | Pull site: M69-T1 STR-BS1 | 1 | Lugo-Moh | Delete | Relocated work area to new structure per Owner design change
Transmission: OPGW | Pull site: M6-T2 STR-AS1 | 1 | Moh-Eld | Modify | Moved work area closer to structure per Contractor
Transmission: OPGW | Pull site: M88-T4 STR-BS1 | 1 | Lugo-Moh | Modify | Moved work area closer to structure per Contractor
Mid-line Series Capacitors | Parking area (at Pisgah) | 1 | Newberry Springs | Modify | Parking area at Pisgah Substation reduced per BLM request
Eldorado Substation | Substation work area | 1 | Eldorado | Modify | General disturbance area expanded to include OPGW work area
Transmission: OPGW | Landing Zone: LZ_171B | 1 | Lugo-Moh | Add | Renamed shape "Alt_LZ" to "LZ_171B". GIS cleanup.
Transmission: OPGW | Landing Zone: Alt_LZ | 1 | Lugo-Moh | Delete | Incorrectly labeled shape deleted
Transmission: OPGW | Site Access: M82-T1 SA-BS1 | 1 | Lugo-Moh | Modify | Modified work area to reduce impacts to JD waterway
Transmission: OPGW | Pull site: M128-T1 STR-BS1 | 1 | Lugo-Moh | Modify | Modified work area to reduce impacts to JD waterway
Transmission: OPGW | Pull site: M12-T2 STR-BS1 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Pull site: M151-T1 STR-AS1 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Pull site: M157-T1 STR-AS1 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Pull site: M6-T2 STR-BS1 | 1 | Moh-Eld | Modify | Modified work area to move closer to structure and to avoid JD waterway
Transmission: OPGW | Guard structure (East of M0-T1) | 1 | Moh-Eld | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Guard structure (East of M1-T1) | 1 | Moh-Eld | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Guard structure (west of M57-T2) | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Guard structure (west of M124-T3) | 1 | Lugo-Moh | Delete | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_10 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_104 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_112 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_143 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_144 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_165 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_176 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_182 | 1 | Eld-Lugo | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_183 | 1 | Eld-Lugo | Modify | Moved work area closer to structure per Contractor
Transmission: OPGW | Landing Zone: LZ_20 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_52 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | Landing Zone: LZ_53 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway
Transmission: OPGW | M46-T3 STR-BS1 | 1 | Moh-Eld | Modify | Expanded work area per Contractor
Mohave Substation | Telecom work area | 1 | Mohave | Modify | Modified work area to reduce impacts to JD waterway
Mid-line Series Capacitors | Work areas: telecom & distribution | 3 | Newberry Springs & Ludlow | Modify | Modified work area to reduce impacts to JD waterway
Subtransmission: Infraction | Subtransmisssion work area (near M20-T2) | 1 | Lugo-Moh | Modify | Modified work area per SCE design change
Mid-line Series Capacitors | Series capacitor work area | 1 | Newberry Springs | Modify | Modified work area per design & Contractor
Mid-line Series Capacitors | Series capacitor work area | 1 | Ludlow | Modify | Modified work area per design & Contractor
Transmission: OPGW | Pull site: M98-T2 STR-AS1 | 1 | Lugo-Moh | Modify | Modified work area to avoid JD waterway. Corrected structure number to "M98-T2"
Transmission: OPGW | Pull site: M98-T1 STR-AS1 | 1 | Lugo-Moh | Delete | Deleted and replaced by corrected structure number
Transmission: OPGW | Landing Zone: LZ_204 | 1 | Lugo-Moh | Delete | Per ESA
WP_ELMSC | Change Feature ID from "Newberry" to "Newberry Springs" | 4 | Newberry Springs | N/A | Per CPUC Request
Transmission: OPGW | Guard Structures | 2 | Newberry Springs | Delete | Not needed

## cvl_Design_Area
GIS DATA CHANGES
ELM GIS DATA CHANGE
Feature Class Changed:
cvl_design_Area
Feature Class Updated Details | [5 empty] | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Change Reason | 15 | 1 | 8
Transmission: Infraction | LST foundation (at M4-T1) | 4 | Moh-Eld | Add | Added new foundation reinforcement design
Mid-line Series Capacitors | gravel surfacing | 1 | Newberry | Add | Modified site development design
Mid-line Series Capacitors | retention basin | 1 | Newberry | Add | Modified site development design
Mid-line Series Capacitors | gravel surfacing | 1 | Ludlow | Add | Modified site development design
Mid-line Series Capacitors | retention basin | 1 | Ludlow | Add | Modified site development design
Mohave Substation | grading limit | 1 | Mohave | Modify | Modified site development design
Mohave Substation | asphalt surfacing | 1 | Mohave | Modify | Modified site development design
Mohave Substation | gravel surfacing | 1 | Mohave | Delete | Modified site development design
Mohave Substation | retention basin | 1 | Mohave | Add | Modified site development design
Mid-line Series Capacitors | ground disturbance area | 1 | Newberry | Modify | Modified site development design
Mid-line Series Capacitors | grading limit | 1 | Newberry | Modify | Modified site development design
Mid-line Series Capacitors | asphalt surfacing | 1 | Newberry | Modify | Modified site development design
Mid-line Series Capacitors | fence | 2 | Newberry | Add | Modified site development design
Mid-line Series Capacitors | rip rap | 1 | Newberry | Add | Modified site development design
Mid-line Series Capacitors | ground disturbance area | 1 | Ludlow | Modify | Modified site development design
Mid-line Series Capacitors | grading limit | 1 | Ludlow | Modify | Modified site development design
Mid-line Series Capacitors | asphalt surfacing | 1 | Ludlow | Modify | Modified site development design
Mid-line Series Capacitors | fence | 2 | Ludlow | Add | Modified site development design
Mid-line Series Capacitors | rip rap | 1 | Ludlow | Add | Modified site development design
WP_ELMSC | Change Feature ID from "Newberry" to "Newberry Springs" | 8 | Newberry Springs | N/A | Per CPUC Request

## eng_DistributionAlignment_Line
GIS DATA CHANGES
ELMSC GIS DATA CHANGE
Feature Class Changed:
eng_DistributionAlignment_Line
Feature Class Updated Details | [5 empty] | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Change Reason | 1 | 0 | 10
Distribution Relocation | New Overhead 12kV line | 1 | Desert View Rd | Modify | Modified distribution design
Distribution Relocation | Removal Overhead 12kV line | 1 | Desert View Rd | Modify | Modified distribution design
Distribution Relocation | Existing Overhead 12kV line | 1 | Desert View Rd | Add | Added existing line for design reference
Mid-line Series Capacitors | New Overhead 12kV line | 1 | Newberry Springs/Ludlow | Modify | Modified design at mid-line series capacitors
Mid-line Series Capacitors | New Underground 12kV line | 1 | Newberry Springs | Modify | Modified design at Newberry Springs
Repeater Sites | OH line data | 6 | Kelbaker & Lanfair | Modify | Modified KV from "12" to "16"

## eng_DistributionStructure_Pt
GIS DATA CHANGES
ELMSC GIS DATA CHANGE
Feature Class Changed:
eng_DistributionStructure_Pt
Feature Class Updated Details | [5 empty] | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Change Reason | 105 | 0 | 0
Mid-line Series Capacitors | New poles | 76 | Newberry Springs & Ludlow | Add | Base on desktop analysis, added approx. pole locations per CPUC deficiency request
Repeater Sites | New poles | 16 | Lanfair | Add | Base on desktop analysis, added approx. pole locations per CPUC deficiency request
Repeater Sites | New poles | 6 | Kelbaker | Add | Base on desktop analysis, added approx. pole locations per CPUC deficiency request
Distribution Relocation | Existing poles | 4 | Desert View Rd | Add | Added existing poles for design reference
Distribution Relocation | New poles | 2 | Desert View Rd | Add | Base on desktop analysis, added approx. pole locations per CPUC deficiency request
Distribution Relocation | Removal poles | 1 | Desert View Rd | Add | Base on desktop analysis, added approx. pole locations per CPUC deficiency request

## eng_TelcomAlignment_Line
GIS DATA CHANGES
ELMSC GIS DATA CHANGE
Feature Class Changed:
eng_TelcomAlignment_Line
Feature Class Updated Details | [5 empty] | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Change Reason | 0 | 0 | 3
Mid-line Series Capacitors | New UG conduit line | 1 | Newberry Springs | Modify | Modified UG telecom design
Mid-line Series Capacitors | New UG conduit extension | 1 | Newberry Springs | Modify | Modified UG telecom design
Mid-line Series Capacitors | New UG conduit extension | 1 | Newberry Springs | Modify | Modified UG telecom design

## eng_TelecomStructure_Point
GIS DATA CHANGES
ELMSC GIS DATA CHANGE
Feature Class Changed:
eng_TelcomStructure_Point
Feature Class Updated Details | [5 empty] | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Change Reason | 0 | 0 | 2
Mid-line Series Capacitors | Manhole 1 | 1 | Newberry Springs | Modify | Moved manhole in telecom design
Mid-line Series Capacitors | Manhole 2 | 1 | Newberry Springs | Modify | Moved manhole in telecom design

## eng_TransStructure_Point
GIS DATA CHANGES
ELM GIS DATA CHANGE
Feature Class Changed:
eng_TransStructure_Point
Feature Class Updated Details | [5 empty] | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Change Reason | 2 | 0 | 0
Transmission: Infraction | Infraction transmission structure | 1 | Eld-Lugo: M58-T1 | Add | Added structure label as infraction
Transmission: Infraction | Infraction transmission structure | 1 | Eld-Lugo: M58-T2 | Add | Added structure label as infraction

## proj_AccessRoad_Area
GIS DATA CHANGES
ELM GIS DATA CHANGE
Feature Class Changed:
proj_AccessRoad_Area
Feature Class Updated Details | [5 empty] | Add | Delete | Modify
Work Package/Segment | What was updated | Number of Features | Feature Location | Add/Delete/Modify | Change Reason | 9 | 5 | 4
Transmission: OPGW | Foot access (for M40-T1- AS) | 1 | Lugo-Moh | Modify | Widened walk path by Contractor
Transmission: OPGW | Foot access (for M46-T3- AS) | 1 | Moh-Eld | Add | Added to walk line to pull sites by Contractor
Transmission: OPGW | Foot access (for M53-T1- BS) | 1 | Moh-Eld | Add | Added to walk line to pull sites by Contractor
Transmission: OPGW | Foot access (for M53-T1- AS) | 1 | Moh-Eld | Add | Added to walk line to pull sites by Contractor
Transmission: OPGW | Foot access (for M78-T4- AS) | 1 | Lugo-Moh | Add | Added to walk line to pull sites by Contractor
Transmission: OPGW | Foot access (for M78-T4- BS) | 1 | Lugo-Moh | Add | Added to walk line to pull sites by Contractor
Transmission: OPGW | Foot access | 5 | Transmission lines | Delete | Alternate foot access paths removed
Repeater Sites | Access road | 1 | Lanfair | Modify | Modified site development design
Mid-line Series Capacitors | Internal Access Road Surface (with Aggregate Base) | 1 | Newberry Springs | Add | Modified site development design
Mid-line Series Capacitors | Access Road Surface (external) | 2 | Newberry Springs | Modify | Modified site development design
Mid-line Series Capacitors | Internal Access Road Surface (with Aggregate Base) | 1 | Ludlow | Add | Modified site development design
Mid-line Series Capacitors | Access Road Surface (external) | 1 | Ludlow | Add | Modified site development design
Mohave Substation | Access Road Surface (external) | 1 | Mohave | Add | Added access road at entrance to site
WP_ELMSC | Change Name Alt from "Newberry" to "Newberry Springs" | 8 | Newberry Springs | N/A | Per CPUC Request