## Beta Schedule Summary
ELM Construction Schedule Summary (as of 6/25/2018)
Site - Activity | Dates
| Start | End of Grading | End of Electrical | End of Testing | End
Mohave-Eldorado Transmission Line - OPGW Re-conductoring | 2019-04-01 | - | - | - | 2019-05-30
All Transmission Line - Infraction Work- Tower Raising | 2019-06-04 | - | - | - | 2019-07-29
Lugo-Mohave Transmission Line - OPGW Re-conductoring | 2019-10-09 | - | - | - | 2020-01-30
Lugo Substation (Eldorado Bank) - SC1 Construction | 2019-10-01 | - | 2020-01-08 | 2020-06-05 | 2020-07-31
Newberry Series Capacitor - SC2 Construction | 2019-06-03 | 2019-11-20 | 2020-03-09 | 2020-06-25 | 2020-08-07
Eldorado Substation (Lugo Bank) - SC3 Construction | 2019-04-01 | 2019-05-02 | 2019-06-25 | 2019-08-08 | 2019-09-23
Lugo Substation (Mohave Bank) - SC4 Construction | 2019-10-09 | - | 2020-02-05 | 2020-03-18 | 2020-04-10
Ludlow Series Capacitor - SC5 Construction | 2019-06-03 | 2019-10-14 | 2020-02-25 | 2020-04-22 | 2020-08-07
Mohave Substation (Lugo Bank) - SC6 Construction | 2019-04-04 | 2019-08-22 | 2019-10-14 | 2020-02-07 | 2020-04-03

## Beta Construction Workforce
ELM Construction Workforce Schedule (as of 6/25/2018)
NOTE: This table to be used for approximate work durations and personnel coordination only. |  |  |  | LEGEND | o |  | OPGW Re-conductoring
[5 empty] | i |  | Infraction Work (Tower Raising)
[5 empty] | g |  | Grading (Site Development)
[5 empty] | e |  | Electrical Installations
[5 empty] | t |  | Testing
[5 empty] | c |  | Closeout (No construction activities)
Site - Construction Component | Activity | Duration | 2019 | [48 empty] | 2020
|  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  |  | Jun |  |  |  |  | Jul |  |  |  |  | Aug |  |  |  |  | Sept |  |  |  |  | Oct |  |  |  |  | Nov |  |  |  |  | Dec |  |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  |  | May |  |  |  |  | Jun |  |  |  |  | Jul |  |  |  |  | Aug |  |  |  |  | Sept
Mohave-Eldorado Transmission Line - Transmission Work | Re-conductoring | 59 |  |  |  | 4/1/2019 | o | o | o | o |  | o | o | o | o | o | 5/30/2019
All Transmission Line - Infraction Work | Tower Raising | 55 | [8 empty] | i |  |  |  |  | 6/4/2019 | i | i | i | i | i | i | i | i | i | i | 7/29/2019
Lugo-Mohave Transmission Line - Transmission Work | Re-conductoring | 113 | [34 empty] | 10/9/2019 | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | o | 1/30/2020
Lugo Substation (Eldorado Bank) - SC1 Construction | Electrical | 99 | [33 empty] | 10/1/2019 | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | 1/8/2020
| Testing | 50 | [64 empty] | 4/16/2020 | t | t | t | t | t | t | t |  | t | 6/5/2020
| Closeout | 56 | [74 empty] | c | c | c | c | c | c | c | c | c | 7/31/2020
Newberry Series Capacitor - SC2 Construction | Grading | 156 | [15 empty] | 6/17/2019 | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | 11/20/2019
| Electrical | 147 | [34 empty] | 10/14/2019 | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | 3/9/2020
| Testing | 42 | [69 empty] | 5/14/2020 | t | t | t | t | t | t | t | 6/25/2020
| Closeout | 56 | [77 empty] | c | c | c | c | c | c | c | c | c | 8/20/2020
Eldorado Substation (Lugo Bank) - SC3 Construction | Grading | 17 | [6 empty] | 4/15/2019 | g | g | g | 5/2/2019
| Electrical | 85 |  |  |  | 4/1/2019 | e | e | e | e | e | e | e | e | e | e | e | e | e | e | 6/25/2019
| Testing | 43 | [17 empty] | 6/26/2019 | t | t | t | t | t | t | t | 8/8/2019
| Closeout | 57 | [25 empty] | c | c | c | c | c | c | c | c | c | c | 10/04/2019
Lugo Substation (Mohave Bank) - SC4 Construction | Electrical | 119 | [34 empty] | 10/9/2019 | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | 2/5/2020
| Testing | 70 | [50 empty] | 1/8/2020 | t | t | t | t | t | t | t | t | t | t | 3/18/2020
| Closeout | 56 | [61 empty] | c | c | c | c | c | c | c | c | c | 5/13/2020
Ludlow Series Capacitor - SC5 Construction | Grading | 133 | [13 empty] | 6/3/2019 | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | 10/14/2019
| Electrical | 172 | [28 empty] | 9/6/2019 | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | 2/25/2020
| Testing | 41 | [59 empty] | 3/12/2020 | t | t | t | t | t | t | 4/22/2020
| Closeout | 57 | [66 empty] | c | c | c | c | c | c | c | c | c | 6/18/2020
Mohave Substation (Lugo Bank) - SC6 Construction | Grading | 113 | [8 empty] | 5/1/2019 | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | g | 8/22/2019
| Electrical | 192 |  |  |  |  | 4/5/2019 | e | e | e | e | [8 empty] | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | 10/14/2019
| Testing | 84 | [40 empty] | 11/15/2019 | t | t | t | t | t | t | 12/20/2019 | [6 empty] | t | 2/7/2020
| Closeout | 56 | [55 empty] | c | c | c | c | c | c | c | c | c | 4/3/2020
|  |  | Beginning of March | [37 empty] | End of October | [19 empty] | Beginning of March
|  |  | March 1 | [22 empty] | July 31 | [34 empty] | March 1 | [23 empty] | July 31
Work Crews | # of Workers | [5 empty] | 3 | 3 | 4 | 4 | 5 | 4 | 4 | 3 | 3 | 5 | 5 | 5 | 5 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 6 | 5 | 5 | 5 | 5 | 6 | 9 | 9 | 8 | 8 | 6 | 6 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 6 | 6 | 5 | 5 | 6 | 6 | 5 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | 4 | 3 | 4 | 3 | 3 | 4 | 4 | 3 | 2 | 3 | 4 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
OPGW Re-Conductoring (o) | 25 | [5 empty] | 25 | 25 | 25 | 25 | 0 | 25 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infraction Work (i) | 12 | [5 empty] | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grading (g) | 12 | [5 empty] | 0 | 0 | 0 | 12 | 12 | 24 | 12 | 12 | 12 | 12 | 24 | 24 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electrical Installations (e) | 12 | [5 empty] | 12 | 24 | 24 | 24 | 24 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 24 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 24 | 24 | 24 | 24 | 24 | 36 | 60 | 60 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 36 | 36 | 36 | 36 | 36 | 24 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing (t) | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 10 | 5 | 5 | 5 | 5 | 5 | 10 | 5 | 5 | 5 | 5 | 10 | 5 | 5 | 5 | 5 | 10 | 10 | 5 | 10 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closeout (c) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitors | [6 empty] | 3 | 3 | 4 | 4 | 5 | 4 | 4 | 3 | 3 | 5 | 5 | 5 | 5 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 6 | 5 | 5 | 5 | 5 | 6 | 9 | 9 | 8 | 8 | 6 | 6 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 6 | 6 | 5 | 5 | 6 | 6 | 5 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | 4 | 3 | 4 | 3 | 3 | 4 | 4 | 3 | 2 | 3 | 4 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Management- Trans | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Management- SC2 & SC5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Management- SC1 & SC4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Managemnet- SC3 & SC6 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Manpower | [6 empty] | 42 | 54 | 55 | 67 | 55 | 67 | 55 | 54 | 54 | 58 | 57 | 56 | 68 | 82 | 75 | 74 | 74 | 74 | 74 | 74 | 62 | 56 | 55 | 55 | 44 | 55 | 55 | 55 | 55 | 57 | 73 | 122 | 121 | 97 | 94 | 94 | 96 | 101 | 89 | 88 | 88 | 88 | 88 | 83 | 81 | 81 | 82 | 75 | 74 | 74 | 56 | 50 | 37 | 24 | 23 | 24 | 17 | 12 | 11 | 11 | 12 | 15 | 11 | 10 | 10 | 11 | 16 | 15 | 8 | 15 | 11 | 10 | 9 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0

## Beta Construction Sequencing
ELM Construction Sequencing (as of 6/25/2018)
Site - Activity | 2019 | [15 empty] | 2020
| Mar |  | Apr | May |  | Jun |  | Jul | Aug |  | Sept |  | Oct | Nov | Dec |  | Jan |  | Feb |  | Mar |  |  | Apr |  |  | May |  | Jun |  |  | Jul | Aug | Sept
Mohave-Eldorado Transmission Line - OPGW Re-conductoring |  | 4/1/2019 |  |  |  | 5/30/2019
All Transmission Line - Infraction Work- Tower Raising |  |  |  |  | 6/4/2019 |  |  |  | 7/29/2019
Lugo-Mohave Transmission Line - OPGW Re-conductoring | [12 empty] | 10/9/2019 | [5 empty] | 1/30/2020
Lugo Substation (Eldorado Bank) - SC1 Construction | [11 empty] | 10/1/2019 | [5 empty] | 1/8/2020 | [6 empty] | 4/16/2020 |  |  |  |  | 6/5/2020
Newberry Series Capacitor - SC2 Construction | [6 empty] | 6/17/2019 | [14 empty] | 3/9/2020 | [5 empty] | 5/14/2020 |  |  | 6/25/2020
Eldorado Substation (Lugo Bank) - SC3 Construction |  | 4/1/2019 | [7 empty] | 8/8/2019
Lugo Substation (Mohave Bank) - SC4 Construction | [12 empty] | 10/9/2019 | [9 empty] | 3/18/2020
Ludlow Series Capacitor - SC5 Construction |  |  |  |  | 6/3/2019 | [20 empty] | 4/22/2020
Mohave Substation (Lugo Bank) - SC6 Construction |  |  | 4/5/2019 | [12 empty] | 12/20/2019 |  |  |  | 2/7/2020