## Schedule
Column2 | California Percent | Nevada Percent | Start Date | End Date | Working Days | Working Days in 2019 | Working Days in 2020 | Duration in 2019 | Duration in 2020 | Workforce
Trans, Subtrans, Telecom - None - Survey6 | 75 | 25 | 2019-04-01 | 2020-06-30 | 391 | 236 | 156 | 90 | 90 | 8
Trans, Subtrans, Telecom - None - Marshalling Yard7 | 75 | 25 | 2019-04-01 | 2019-07-01 | 78 | 79 | 0 | 79 | 0 | 4
Trans, Subtrans, Telecom - None - Right-of-Way Clearing8 | 0 | 100 | 2019-04-01 | 2019-06-01 | 53 | 54 | 0 | 54 | 0 | 5
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | 0 | 100 | 2019-04-01 | 2019-06-01 | 53 | 54 | 0 | 54 | 0 | 5
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | 0 | 100 | 2019-04-01 | 2019-06-01 | 53 | 54 | 0 | 54 | 0 | 6
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | 0 | 100 | 2019-04-01 | 2019-06-01 | 53 | 54 | 0 | 54 | 0 | 44
Trans, Subtrans, Telecom - None - Guard Structure Removal26 | 0 | 100 | 2019-04-01 | 2019-06-01 | 53 | 54 | 0 | 54 | 0 | 6
Trans, Subtrans, Telecom - None - Restoration27 | 0 | 100 | 2019-04-01 | 2019-06-01 | 53 | 54 | 0 | 54 | 0 | 7
Trans, Subtrans, Telecom - None - LST Foundation Reinforcement14 | 0 | 100 | 2019-05-25 | 2019-06-01 | 6 | 7 | 0 | 7 | 0 | 7
Trans, Subtrans, Telecom - None - Right-of-Way Clearing8 | 95 | 5 | 2019-10-16 | 2020-03-01 | 118 | 66 | 53 | 61 | 53 | 5
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | 95 | 5 | 2019-10-16 | 2020-03-01 | 118 | 66 | 53 | 66 | 53 | 5
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | 95 | 5 | 2019-10-16 | 2020-03-01 | 118 | 66 | 53 | 66 | 53 | 6
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | 95 | 5 | 2019-10-16 | 2020-03-01 | 118 | 66 | 53 | 66 | 53 | 44
Trans, Subtrans, Telecom - None - Guard Structure Removal26 | 95 | 5 | 2019-10-16 | 2020-03-01 | 118 | 66 | 53 | 66 | 53 | 6
Trans, Subtrans, Telecom - None - Restoration27 | 95 | 5 | 2019-10-16 | 2020-03-01 | 118 | 66 | 53 | 31 | 31 | 7
Trans, Subtrans, Telecom - None - Underground Cable Installation29 | 100 | 0 | 2019-06-01 | 2019-09-01 | 79 | 80 | 0 | 7 | 0 | 5
Trans, Subtrans, Telecom - None - Overhead Cable30 | 100 | 0 | 2019-10-01 | 2020-01-01 | 79 | 79 | 1 | 79 | 1 | 5
Trans, Subtrans, Telecom - None - All Dielectric Self Supporting (ADSS) Splicing and Termination31 | 75 | 25 | 2019-06-01 | 2020-06-01 | 314 | 184 | 132 | 10 | 10 | 5
Substations - Lugo - Survey | 0 | 100 | 2019-06-01 | 2020-06-30 | 339 | 184 | 156 | 31 | 31 | 2
Substations - Lugo - Survey | 0 | 100 | 2019-04-01 | 2020-03-31 | 313 | 236 | 78 | 109 | 78 | 2
Substations - Lugo - Grading/Civil Crew | 0 | 100 | 2020-03-01 | 2020-04-14 | 38 | 0 | 39 | 0 | 39 | 15
Substations - Lugo - Electrical Crew | 0 | 100 | 2020-04-16 | 2020-05-20 | 30 | 0 | 30 | 0 | 29 | 15
Substations - Lugo - Wiring Crew | 0 | 100 | 2020-04-16 | 2020-05-20 | 30 | 0 | 30 | 0 | 15 | 5
Substations - Lugo - Test Crew | 0 | 100 | 2020-04-16 | 2020-06-30 | 65 | 0 | 66 | 0 | 66 | 4
Substations - Mohave - Survey Crew | 100 | 0 | 2019-10-15 | 2020-06-30 | 222 | 67 | 156 | 33 | 33 | 2
Substations - Mohave - Grading/Civil Crew | 100 | 0 | 2019-11-01 | 2020-01-31 | 78 | 53 | 27 | 33 | 27 | 15
Substations - Mohave - Electrical Crew | 100 | 0 | 2020-02-01 | 2020-05-20 | 94 | 0 | 95 | 0 | 44 | 15
Substations - Mohave - Electrical Crew | 100 | 0 | 2020-01-18 | 2020-02-18 | 27 | 0 | 28 | 0 | 28 | 15
Substations - Mohave - Wiring Crew | 100 | 0 | 2020-02-01 | 2020-05-20 | 94 | 0 | 95 | 0 | 75 | 5
Substations - Mohave - Test Crew | 100 | 0 | 2020-02-01 | 2020-06-30 | 129 | 0 | 130 | 0 | 62 | 4
Substations - Mohave - Test Crew | 100 | 0 | 2020-02-18 | 2020-03-18 | 25 | 0 | 26 | 0 | 26 | 4
Substations - Eldorado - Survey | 0 | 100 | 2019-04-01 | 2020-03-31 | 313 | 236 | 78 | 89 | 78 | 2
Substations - Eldorado - Grading and Civil | 0 | 100 | 2020-01-01 | 2020-02-15 | 39 | 0 | 40 | 0 | 40 | 15
Substations - Eldorado - Electrical | 0 | 100 | 2020-02-16 | 2020-03-20 | 29 | 0 | 30 | 0 | 29 | 15
Substations - Eldorado - Wiring | 0 | 100 | 2020-02-16 | 2020-03-20 | 29 | 0 | 30 | 0 | 30 | 5
Substations - Eldorado - Testing | 0 | 100 | 2020-02-16 | 2020-03-31 | 38 | 0 | 39 | 0 | 39 | 4
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | 100 | 0 | 2019-10-08 | 2019-12-01 | 47 | 48 | 0 | 43 | 0 | 5
Substations - Lugo - Electrical (Capacitors) - SC1 | 100 | 0 | 2019-11-01 | 2020-01-15 | 65 | 53 | 13 | 53 | 13 | 15
Substations - Lugo - Wiring/Test (Capacitors) - SC1 | 100 | 0 | 2020-01-01 | 2020-03-03 | 54 | 0 | 54 | 0 | 54 | 6
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | 100 | 0 | 2019-10-15 | 2019-12-18 | 55 | 56 | 0 | 56 | 0 | 5
Substations - Lugo - Electrical (Capacitors) - SC4 | 100 | 0 | 2019-11-15 | 2020-02-12 | 77 | 41 | 37 | 41 | 37 | 15
Substations - Lugo - Wiring/Test (Capacitors) - SC4 | 100 | 0 | 2020-02-01 | 2020-03-18 | 40 | 0 | 41 | 0 | 41 | 6
Substations - Mohave - Grading/Civil (Capacitors) | 0 | 100 | 2019-04-01 | 2019-04-30 | 25 | 26 | 0 | 26 | 0 | 10
Substations - Mohave - Grading/Civil (Capacitors) | 0 | 100 | 2019-05-01 | 2019-08-01 | 79 | 80 | 0 | 31 | 0 | 10
Substations - Mohave - Electrical (Capacitors) | 0 | 100 | 2019-05-30 | 2019-10-01 | 107 | 108 | 0 | 69 | 0 | 15
Substations - Mohave - Wiring/Test (Capacitors) | 0 | 100 | 2019-09-19 | 2019-11-01 | 37 | 38 | 0 | 38 | 0 | 6
Substations - Eldorado - Grading and Civil (Capacitors) | 0 | 100 | 2019-04-01 | 2019-06-01 | 53 | 54 | 0 | 54 | 0 | 5
Substations - Eldorado - Electrical (Capacitor) | 0 | 100 | 2019-04-17 | 2019-07-01 | 65 | 66 | 0 | 38 | 0 | 15
Substations - Eldorado - Wiring/Test (Capacitors) | 0 | 100 | 2019-07-22 | 2019-10-15 | 73 | 74 | 0 | 1 | 0 | 10
Capacitors - Newberry Springs - Grading/Civil | 100 | 0 | 2019-06-10 | 2019-08-01 | 45 | 46 | 0 | 4 | 0 | 12
Capacitors - Newberry Springs - Grading/Civil | 100 | 0 | 2019-07-23 | 2019-11-01 | 87 | 88 | 0 | 1 | 0 | 12
Capacitors - Newberry Springs - Electrical | 100 | 0 | 2019-09-06 | 2020-02-15 | 139 | 101 | 40 | 1 | 1 | 20
Capacitors - Newberry Springs - Wiring/Test | 100 | 0 | 2020-02-01 | 2020-03-03 | 27 | 0 | 28 | 0 | 4 | 10
Capacitors - Ludlow - Grading/Civil | 100 | 0 | 2019-06-24 | 2019-09-01 | 60 | 60 | 0 | 1 | 0 | 12
Capacitors - Ludlow - Grading/Civil | 100 | 0 | 2019-08-23 | 2019-11-15 | 72 | 73 | 0 | 35 | 0 | 12
Capacitors - Ludlow - Electrical | 100 | 0 | 2019-09-27 | 2020-03-01 | 134 | 83 | 53 | 1 | 1 | 20
Capacitors - Ludlow - Wiring/Test | 100 | 0 | 2020-03-01 | 2020-04-08 | 33 | 0 | 34 | 0 | 34 | 10
Capacitors - Newberry Springs - Trenching, Structure Excavation1 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 4
Capacitors - Newberry Springs - Overhead Line Work2 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 3 | 3 | 6
Capacitors - Newberry Springs - Underground Cable Pulling3 and Transformer Installation | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 4
Capacitors - Newberry Springs - Underground Cable Makeup4 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 3
Capacitors - Newberry Springs - Pole Installation5 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 9 | 9 | 6
Capacitors - Ludlow - Trenching, Structure Excavation1 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 4
Capacitors - Ludlow - Overhead Line Work2 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 2 | 2 | 6
Capacitors - Ludlow - Underground Cable Makeup4 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 3
Capacitors - Newberry Springs - Pole Installation5 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 6
Repeater - Lanfair - Trenching, Structure Excavation1 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 4 | 4 | 4
Repeater - Lanfair - Overhead Line Work2 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 6
Repeater - Lanfair - Underground Cable Pulling3 and Transformer Installation | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 4
Repeater - Lanfair - Underground Cable Makeup4 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 3
Repeater - Lanfair - Pole Installation5 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 6
Repeater - Kelbaker - Trenching, Structure Excavation1 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 4
Repeater - Kelbaker - Overhead Line Work2 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 1 | 1 | 6
Repeater - Kelbaker - Underground Cable Pulling3 and Transformer Installation | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 70 | 70 | 4
Repeater - Kelbaker - Underground Cable Makeup4 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 70 | 70 | 3
Repeater - Kelbaker - Pole Installation5 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 70 | 70 | 6
Repeater - Barstow - Trenching, Structure Excavation1 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 0 | 0 | 4
Repeater - Barstow - Overhead Line Work2 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 0 | 0 | 6
Repeater - Barstow - Underground Cable Pulling3 and Transformer Installation | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 0 | 0 | 4
Repeater - Barstow - Underground Cable Makeup4 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 0 | 0 | 3
Repeater - Barstow - Pole Installation5 | 100 | 0 | 2019-10-01 | 2020-03-31 | 156 | 79 | 78 | 0 | 0 | 6
Other - Discrepancy Sites - Overhead Line Work2 | 100 | 0 | 2019-07-24 | 2019-09-06 | 38 | 39 | 0 | 0 | 0 | 6
Repeater - Lanfair - Fiber optic repeater site installation | 100 | 0 | 2019-10-01 | 2019-12-31 | 78 | 79 | 0 | 0 | 0 | 8
Repeater - Kelbaker - Fiber optic repeater site installation | 100 | 0 | 2019-10-01 | 2019-12-31 | 78 | 79 | 0 | 0 | 0 | 8
Repeater - Barstow - Fiber optic repeater site installation | 100 | 0 | 2019-10-01 | 2019-12-31 | 78 | 79 | 0 | 0 | 0 | 8

## EquipmentList
Cmpt_SubCmpt_Phase | Equipment Type | On/Off | Horsepower | CalEEMod Category | On Type | HP | Days | Qty | HoursPerDay | Grading | Soil Handling
Capacitors - Ludlow - Electrical | 135-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 20 | 1 | 5
Capacitors - Ludlow - Electrical | 20,000-Pound Forklift | off | 150 | Forklifts | -- | 150 | 40 | 1 | 8
Capacitors - Ludlow - Electrical | 27-Ton Boom Truck | off | 350 | Cranes | -- | 350 | 60 | 1 | 5
Capacitors - Ludlow - Electrical | 65-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Capacitors - Ludlow - Electrical | 85-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Capacitors - Ludlow - Electrical | Bobcat with Forks | off | 93 | Skid Steer Loaders | -- | 93 | 100 | 2 | 8
Capacitors - Ludlow - Electrical | Crane | off | 350 | Cranes | -- | 350 | 20 | 1 | 5
Capacitors - Ludlow - Electrical | Foreman's Truck | on | -- | -- | passenger | 300 | 100 | 1 | 4
Capacitors - Ludlow - Electrical | Generator | off | 50 | Generator Sets | -- | 50 | 100 | 1 | 12
Capacitors - Ludlow - Electrical | Genie 45-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Capacitors - Ludlow - Electrical | Job Site Utility Cart | on | -- | -- | passenger | 50 | 100 | 1 | 5
Capacitors - Ludlow - Electrical | Scissor Lift | off | 50 | Aerial Lifts | -- | 50 | 100 | 3 | 6
Capacitors - Ludlow - Electrical | Tele-Handler Forklift (5,000-7,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 85 | 1 | 8
Capacitors - Ludlow - Electrical | Tele-Handler Forklift (8,000-12,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 65 | 1 | 8
Capacitors - Ludlow - Electrical | Tool Truck | on | -- | -- | delivery | 300 | 100 | 1 | 7
Capacitors - Ludlow - Electrical | Worker Commute | on | -- | -- | passenger | NA | 100 | 20 | 8
Capacitors - Ludlow - Grading/Civil | 10-Cubic-Yard Dump Truck | on | -- | -- | hhdt | 500 | 100 | 3 | 5
Capacitors - Ludlow - Grading/Civil | 140 Motor Grader | off | 250 | Graders | -- | 250 | 25 | 1 | 8
Capacitors - Ludlow - Grading/Civil | 250-Ton Hydraulic Crane | off | 450 | Cranes | -- | 450 | 30 | 1 | 5
Capacitors - Ludlow - Grading/Civil | 4,000-Gallon Water Truck | on | -- | -- | hhdt | 350 | 100 | 3 | 8
Capacitors - Ludlow - Grading/Civil | 50,000-Pound Excavator /Breaker | off | 200 | Excavators | -- | 200 | 30 | 1 | 8
Capacitors - Ludlow - Grading/Civil | 500-Gallon Water Buffalo with Truck | off | 185 | Off-Highway Trucks | -- | 185 | 90 | 1 | 5
Capacitors - Ludlow - Grading/Civil | 75,000-Pound Excavator | off | 350 | Excavators | -- | 350 | 30 | 1 | 8
Capacitors - Ludlow - Grading/Civil | 84-Inch Vibratory Roller Compactor | off | 130 | Rollers | -- | 130 | 35 | 2 | 8
Capacitors - Ludlow - Grading/Civil | Bobcat Compactor | off | 93 | Skid Steer Loaders | -- | 93 | 50 | 1 | 8
Capacitors - Ludlow - Grading/Civil | Bobcat Skid Steer | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 1 | 8
Capacitors - Ludlow - Grading/Civil | Bobcat with Auger | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 1 | 8
Capacitors - Ludlow - Grading/Civil | Bobcat with Sweeper | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 1 | 8
Capacitors - Ludlow - Grading/Civil | Cat 623 Scraper | off | 400 | Graders | -- | 400 | 30 | 1 | 8
Capacitors - Ludlow - Grading/Civil | Cat 950 Loader | off | 130 | Tractors/Loaders/Backhoes | -- | 130 | 40 | 1 | 8
Capacitors - Ludlow - Grading/Civil | D-6 Cat Dozer | off | 215 | Crawler Tractors | -- | 215 | 40 | 1 | 8
Capacitors - Ludlow - Grading/Civil | Ditch Witch | off | 42 | Trenchers | -- | 42 | 50 | 1 | 8
Capacitors - Ludlow - Grading/Civil | Foreman's Truck | on | -- | -- | passenger | 300 | 90 | 1 | 4
Capacitors - Ludlow - Grading/Civil | Job Site Utility Cart | on | -- | -- | passenger | 50 | 90 | 1 | 5
Capacitors - Ludlow - Grading/Civil | LoDrill Over 50,000 Pounds | off | 350 | Bore/Drill Rigs | -- | 350 | 20 | 1 | 5
Capacitors - Ludlow - Grading/Civil | LoDrill up to 50,000 Pounds | off | 200 | Bore/Drill Rigs | -- | 200 | 30 | 1 | 5
Capacitors - Ludlow - Grading/Civil | Low Bed Equipment Hauler (5 axle) | on | -- | -- | hhdt | 700 | 40 | 1 | 4
Capacitors - Ludlow - Grading/Civil | Low Bed Equipment Hauler (7 axle) | on | -- | -- | hhdt | 800 | 40 | 1 | 4
Capacitors - Ludlow - Grading/Civil | Low Side End Dump | on | -- | -- | hhdt | 500 | 100 | 3 | 5
Capacitors - Ludlow - Grading/Civil | Mini Excavator | off | 50 | Excavators | -- | 50 | 50 | 1 | 8
Capacitors - Ludlow - Grading/Civil | Premiertrak 300 Rock Crusher | off | 280 | Crushing/Proc. Equipment | -- | 280 | 10 | 1 | 9
Capacitors - Ludlow - Grading/Civil | Skip Loader | off | 150 | Tractors/Loaders/Backhoes | -- | 150 | 100 | 1 | 4
Capacitors - Ludlow - Grading/Civil | Tool Truck | on | -- | -- | delivery | 300 | 50 | 1 | 7
Capacitors - Ludlow - Grading/Civil | Vermeer RT-450 Trencher | off | 50 | Trenchers | -- | 50 | 30 | 1 | 8
Capacitors - Ludlow - Grading/Civil | Worker Commute | on | -- | -- | passenger | NA | 100 | 12 | 8
Capacitors - Ludlow - Overhead Line Work2 | 100-Foot Bucket Truck | off | 350 | Aerial Lifts | -- | 350 | 4 | 1 | 8
Capacitors - Ludlow - Overhead Line Work2 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 40 | 2 | 2
Capacitors - Ludlow - Overhead Line Work2 | 40-Ton Crane | off | 300 | Cranes | -- | 300 | 4 | 1 | 8
Capacitors - Ludlow - Overhead Line Work2 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 40 | 1 | 7
Capacitors - Ludlow - Overhead Line Work2 | 60-Foot Digger Derrick | off | 275 | Bore/Drill Rigs | -- | 275 | 40 | 1 | 4
Capacitors - Ludlow - Overhead Line Work2 | Worker Commute | on | -- | -- | passenger | NA | 40 | 6 | 8
Capacitors - Ludlow - Trenching, Structure Excavation1 | 1-Ton Crew Cab | on | -- | -- | passenger | 300 | 1 | 1 | 2
Capacitors - Ludlow - Trenching, Structure Excavation1 | Backhoe Front Loader | off | 300 | Tractors/Loaders/Backhoes | -- | 300 | 1 | 1 | 8
Capacitors - Ludlow - Trenching, Structure Excavation1 | Dump Truck | on | -- | -- | hhdt | 350 | 1 | 1 | 4
Capacitors - Ludlow - Trenching, Structure Excavation1 | Worker Commute | on | -- | -- | passenger | NA | 1 | 4 | 8
Capacitors - Ludlow - Underground Cable Makeup4 | 1- Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Capacitors - Ludlow - Underground Cable Makeup4 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 4
Capacitors - Ludlow - Underground Cable Makeup4 | Worker Commute | on | -- | -- | passenger | NA | 1 | 3 | 8
Capacitors - Ludlow - Wiring/Test | Foreman’s Truck | on | -- | -- | passenger | 300 | 50 | 1 | 4
Capacitors - Ludlow - Wiring/Test | Job Site Utility Cart | on | -- | -- | passenger | 50 | 50 | 1 | 5
Capacitors - Ludlow - Wiring/Test | Scissor Lift | off | 50 | Aerial Lifts | -- | 50 | 50 | 3 | 6
Capacitors - Ludlow - Wiring/Test | Test Truck | on | -- | -- | delivery | 300 | 50 | 1 | 4
Capacitors - Ludlow - Wiring/Test | Tool Truck | on | -- | -- | delivery | 300 | 50 | 1 | 7
Capacitors - Ludlow - Wiring/Test | Worker Commute | on | -- | -- | passenger | NA | 50 | 10 | 8
Capacitors - Newberry Springs - Electrical | 135-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 20 | 1 | 5
Capacitors - Newberry Springs - Electrical | 20,000-Pound Forklift | off | 150 | Forklifts | -- | 150 | 40 | 1 | 8
Capacitors - Newberry Springs - Electrical | 27-Ton Boom Truck | off | 350 | Cranes | -- | 350 | 60 | 1 | 5
Capacitors - Newberry Springs - Electrical | 65-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Capacitors - Newberry Springs - Electrical | 85-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Capacitors - Newberry Springs - Electrical | Bobcat with Forks | off | 93 | Skid Steer Loaders | -- | 93 | 100 | 2 | 8
Capacitors - Newberry Springs - Electrical | Crane | off | 350 | Cranes | -- | 350 | 20 | 1 | 5
Capacitors - Newberry Springs - Electrical | Foreman's Truck | on | -- | -- | passenger | 300 | 100 | 1 | 4
Capacitors - Newberry Springs - Electrical | Generator | off | 50 | Generator Sets | -- | 50 | 100 | 1 | 10
Capacitors - Newberry Springs - Electrical | Genie 45-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Capacitors - Newberry Springs - Electrical | Job Site Utility Cart | on | -- | -- | passenger | 50 | 100 | 1 | 5
Capacitors - Newberry Springs - Electrical | Scissor Lift | off | 50 | Aerial Lifts | -- | 50 | 100 | 3 | 6
Capacitors - Newberry Springs - Electrical | Tele-Handler Forklift (8,000-12,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 65 | 1 | 8
Capacitors - Newberry Springs - Electrical | Tele-Handler Forklift (5,000-7,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 85 | 1 | 8
Capacitors - Newberry Springs - Electrical | Tool Truck | on | -- | -- | delivery | 300 | 100 | 1 | 7
Capacitors - Newberry Springs - Electrical | Worker Commute | on | -- | -- | passenger | NA | 100 | 20 | 8
Capacitors - Newberry Springs - Grading/Civil | 10-Cubic-Yard Dump Truck | on | -- | -- | hhdt | 500 | 100 | 3 | 5
Capacitors - Newberry Springs - Grading/Civil | 140 Motor Grader | off | 250 | Graders | -- | 250 | 25 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | 250-Ton Hydraulic Crane | off | 450 | Cranes | -- | 450 | 30 | 1 | 5
Capacitors - Newberry Springs - Grading/Civil | 4,000-Gallon Water Truck | on | -- | -- | hhdt | 350 | 100 | 3 | 8
Capacitors - Newberry Springs - Grading/Civil | 50,000-Pound Excavator /Breaker | off | 200 | Excavators | -- | 200 | 30 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | 500-Gallon Water Buffalo w/ Truck | off | 185 | Off-Highway Trucks | -- | 185 | 90 | 1 | 5
Capacitors - Newberry Springs - Grading/Civil | 75,000-Pound Excavator | off | 350 | Excavators | -- | 350 | 30 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | 84-Inch Vibratory Roller Compactor | off | 130 | Rollers | -- | 130 | 35 | 2 | 8
Capacitors - Newberry Springs - Grading/Civil | Bobcat Compactor | off | 93 | Skid Steer Loaders | -- | 93 | 50 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | Bobcat Skid Steer | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | Bobcat with Auger | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | Bobcat with Sweeper | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | Cat 623 Scraper | off | 400 | Graders | -- | 400 | 30 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | Cat 950 Loader | off | 130 | Tractors/Loaders/Backhoes | -- | 130 | 40 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | D-6 Cat Dozer | off | 215 | Crawler Tractors | -- | 215 | 40 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | Ditch Witch | off | 42 | Trenchers | -- | 42 | 50 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | Foreman's Truck | on | -- | -- | passenger | 300 | 90 | 1 | 4
Capacitors - Newberry Springs - Grading/Civil | Job Site Utility Cart | on | -- | -- | passenger | 50 | 90 | 1 | 5
Capacitors - Newberry Springs - Grading/Civil | LoDrill Over 50,000 Pounds | off | 350 | Bore/Drill Rigs | -- | 350 | 20 | 1 | 5
Capacitors - Newberry Springs - Grading/Civil | LoDrill up to 50,000 Pounds | off | 200 | Bore/Drill Rigs | -- | 200 | 30 | 1 | 5
Capacitors - Newberry Springs - Grading/Civil | Low Bed Equipment Hauler (5 axle) | on | -- | -- | hhdt | 700 | 40 | 1 | 4
Capacitors - Newberry Springs - Grading/Civil | Low Bed Equipment Hauler (7 axle) | on | -- | -- | hhdt | 800 | 40 | 1 | 4
Capacitors - Newberry Springs - Grading/Civil | Low Side End Dump | on | -- | -- | hhdt | 500 | 100 | 3 | 5
Capacitors - Newberry Springs - Grading/Civil | Mini Excavator | off | 50 | Excavators | -- | 50 | 50 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | Premiertak 300 Rock Crusher | off | 280 | Crushing/Proc. Equipment | -- | 280 | 10 | 1 | 9
Capacitors - Newberry Springs - Grading/Civil | Skip Loader | off | 150 | Tractors/Loaders/Backhoes | -- | 150 | 100 | 1 | 4
Capacitors - Newberry Springs - Grading/Civil | Tool Truck | on | -- | -- | delivery | 300 | 50 | 1 | 7
Capacitors - Newberry Springs - Grading/Civil | Vermeer RT-450 Trencher | off | 50 | Trenchers | -- | 50 | 30 | 1 | 8
Capacitors - Newberry Springs - Grading/Civil | Worker Commute | on | -- | -- | passenger | NA | 100 | 12 | 8
Capacitors - Newberry Springs - Overhead Line Work2 | 100-Foot Bucket Truck | off | 350 | Aerial Lifts | -- | 350 | 4 | 1 | 8
Capacitors - Newberry Springs - Overhead Line Work2 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 4 | 2 | 2
Capacitors - Newberry Springs - Overhead Line Work2 | 40-Ton Crane | off | 300 | Cranes | -- | 300 | 4 | 1 | 8
Capacitors - Newberry Springs - Overhead Line Work2 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 4 | 1 | 7
Capacitors - Newberry Springs - Overhead Line Work2 | 60-Foot Digger Derrick | off | 275 | Bore/Drill Rigs | -- | 275 | 4 | 1 | 4
Capacitors - Newberry Springs - Overhead Line Work2 | Worker Commute | on | -- | -- | passenger | NA | 4 | 6 | 8
Capacitors - Newberry Springs - Pole Installation5 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 4 | 2 | 2
Capacitors - Newberry Springs - Pole Installation5 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 4 | 1 | 7
Capacitors - Newberry Springs - Pole Installation5 | 60-Foot Digger Derrick | off | 275 | Bore/Drill Rigs | -- | 275 | 4 | 1 | 4
Capacitors - Newberry Springs - Pole Installation5 | Worker Commute | on | -- | -- | passenger | NA | 4 | 6 | 8
Capacitors - Newberry Springs - Trenching, Structure Excavation1 | 1-Ton Crew Cab | on | -- | -- | passenger | 300 | 1 | 1 | 2
Capacitors - Newberry Springs - Trenching, Structure Excavation1 | Backhoe Front Loader | off | 300 | Tractors/Loaders/Backhoes | -- | 300 | 1 | 1 | 8
Capacitors - Newberry Springs - Trenching, Structure Excavation1 | Dump Truck | on | -- | -- | hhdt | 350 | 1 | 1 | 4
Capacitors - Newberry Springs - Trenching, Structure Excavation1 | Worker Commute | on | -- | -- | passenger | NA | 1 | 4 | 8
Capacitors - Newberry Springs - Underground Cable Makeup4 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Capacitors - Newberry Springs - Underground Cable Makeup4 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 4
Capacitors - Newberry Springs - Underground Cable Makeup4 | Worker Commute | on | -- | -- | passenger | NA | 1 | 3 | 8
Capacitors - Newberry Springs - Underground Cable Pulling3 and Transformer Installation | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Capacitors - Newberry Springs - Underground Cable Pulling3 and Transformer Installation | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 7
Capacitors - Newberry Springs - Underground Cable Pulling3 and Transformer Installation | Hydraulic Rewind Puller | off | 300 | Other Construction Equipment | -- | 300 | 1 | 1 | 6
Capacitors - Newberry Springs - Underground Cable Pulling3 and Transformer Installation | Worker Commute | on | -- | -- | passenger | NA | 1 | 4 | 8
Capacitors - Newberry Springs - Wiring/Test | Foreman's Truck | on | -- | -- | passenger | 300 | 35 | 1 | 4
Capacitors - Newberry Springs - Wiring/Test | Job Site Utility Cart | on | -- | -- | passenger | 50 | 35 | 1 | 5
Capacitors - Newberry Springs - Wiring/Test | Scissor Lift | off | 50 | Aerial Lifts | -- | 50 | 35 | 3 | 6
Capacitors - Newberry Springs - Wiring/Test | Test Truck | on | -- | -- | delivery | 300 | 35 | 1 | 4
Capacitors - Newberry Springs - Wiring/Test | Tool Truck | on | -- | -- | delivery | 300 | 35 | 1 | 7
Capacitors - Newberry Springs - Wiring/Test | Worker Commute | on | -- | -- | passenger | NA | 35 | 10 | 8
Other - Discrepancy Sites - Overhead Line Work2 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Other - Discrepancy Sites - Overhead Line Work2 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 7
Other - Discrepancy Sites - Overhead Line Work2 | 60-Foot Digger Derrick | off | 275 | Bore/Drill Rigs | -- | 275 | 1 | 1 | 4
Other - Discrepancy Sites - Overhead Line Work2 | Worker Commute | on | -- | -- | passenger | NA | 1 | 6 | 8
Repeater - Barstow - Fiber optic repeater site installation | 1-Ton Crew Cab 4x4 | on | -- | -- | passenger | 300 | 12 | 1 | 4
Repeater - Barstow - Fiber optic repeater site installation | 2-Ton Truck | on | -- | -- | delivery | 300 | 12 | 1 | 4
Repeater - Barstow - Fiber optic repeater site installation | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 10 | 1 | 6
Repeater - Barstow - Fiber optic repeater site installation | Concrete Pump | off | 350 | Pumps | -- | 350 | 2 | 1 | 6
Repeater - Barstow - Fiber optic repeater site installation | Concrete Truck | on | -- | -- | hhdt | 300 | 2 | 1 | 6
Repeater - Barstow - Fiber optic repeater site installation | Crane | off | 350 | Cranes | -- | 350 | 6 | 1 | 4
Repeater - Barstow - Fiber optic repeater site installation | Drill Rig | off | 500 | Bore/Drill Rigs | -- | 500 | 7 | 1 | 6
Repeater - Barstow - Fiber optic repeater site installation | Dump Truck | on | -- | -- | hhdt | 350 | 7 | 1 | 6
Repeater - Barstow - Fiber optic repeater site installation | Flat Bed Truck | on | -- | -- | hhdt | 300 | 2 | 1 | 2
Repeater - Barstow - Fiber optic repeater site installation | Fork lift | off | 200 | Forklifts | -- | 200 | 10 | 1 | 4
Repeater - Barstow - Fiber optic repeater site installation | Worker Commute | on | -- | -- | passenger | NA | 12 | 8 | 8
Repeater - Barstow - Overhead Line Work2 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Repeater - Barstow - Overhead Line Work2 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 7
Repeater - Barstow - Overhead Line Work2 | 60-Foot Digger Derrick | off | 275 | Bore/Drill Rigs | -- | 275 | 1 | 1 | 4
Repeater - Barstow - Overhead Line Work2 | Worker Commute | on | -- | -- | passenger | NA | 1 | 6 | 8
Repeater - Barstow - Pole Installation5 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 2 | 2
Repeater - Barstow - Pole Installation5 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 7
Repeater - Barstow - Pole Installation5 | 60-Foot Digger Derrick | off | 275 | Bore/Drill Rigs | -- | 275 | 1 | 1 | 4
Repeater - Barstow - Pole Installation5 | Worker Commute | on | -- | -- | passenger | NA | 1 | 6 | 8
Repeater - Barstow - Trenching, Structure Excavation1 | 1-Ton Crew Cab | on | -- | -- | passenger | 300 | 1 | 1 | 2
Repeater - Barstow - Trenching, Structure Excavation1 | Backhoe Front Loader | off | 300 | Tractors/Loaders/Backhoes | -- | 300 | 1 | 1 | 8
Repeater - Barstow - Trenching, Structure Excavation1 | Dump Truck | on | -- | -- | hhdt | 350 | 1 | 1 | 4
Repeater - Barstow - Trenching, Structure Excavation1 | Worker Commute | on | -- | -- | passenger | NA | 1 | 4 | 8
Repeater - Barstow - Underground Cable Makeup4 | 1- Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Repeater - Barstow - Underground Cable Makeup4 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 4
Repeater - Barstow - Underground Cable Makeup4 | Worker Commute | on | -- | -- | passenger | NA | 1 | 3 | 8
Repeater - Barstow - Underground Cable Pulling3 and Transformer Installation | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Repeater - Barstow - Underground Cable Pulling3 and Transformer Installation | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 7
Repeater - Barstow - Underground Cable Pulling3 and Transformer Installation | Hydraulic Rewind Puller | off | 300 | Other Construction Equipment | -- | 300 | 1 | 1 | 6
Repeater - Barstow - Underground Cable Pulling3 and Transformer Installation | Worker Commute | on | -- | -- | passenger | NA | 1 | 4 | 8
Repeater - Kelbaker - Fiber optic repeater site installation | 1-Ton Crew Cab 4x4 | on | -- | -- | passenger | 300 | 12 | 1 | 4
Repeater - Kelbaker - Fiber optic repeater site installation | 2-Ton Truck | on | -- | -- | delivery | 300 | 12 | 1 | 4
Repeater - Kelbaker - Fiber optic repeater site installation | Backhoe/front loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 10 | 1 | 6
Repeater - Kelbaker - Fiber optic repeater site installation | Concrete Pump | off | 350 | Pumps | -- | 350 | 2 | 1 | 6
Repeater - Kelbaker - Fiber optic repeater site installation | Concrete Truck | on | -- | -- | hhdt | 300 | 2 | 1 | 6
Repeater - Kelbaker - Fiber optic repeater site installation | Crane | off | 350 | Cranes | -- | 350 | 6 | 1 | 4
Repeater - Kelbaker - Fiber optic repeater site installation | Drill Rig | off | 500 | Bore/Drill Rigs | -- | 500 | 7 | 1 | 6
Repeater - Kelbaker - Fiber optic repeater site installation | Dump Truck | on | -- | -- | hhdt | 350 | 7 | 1 | 6
Repeater - Kelbaker - Fiber optic repeater site installation | Flat Bed Truck | on | -- | -- | hhdt | 300 | 2 | 1 | 2
Repeater - Kelbaker - Fiber optic repeater site installation | Fork lift | off | 200 | Forklifts | -- | 200 | 10 | 1 | 4
Repeater - Kelbaker - Fiber optic repeater site installation | Worker Commute | on | -- | -- | passenger | NA | 12 | 8 | 8
Repeater - Kelbaker - Overhead Line Work2 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 2 | 1 | 2
Repeater - Kelbaker - Overhead Line Work2 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 2 | 1 | 7
Repeater - Kelbaker - Overhead Line Work2 | 60-Foot Digger Derrick | off | 275 | Bore/Drill Rigs | -- | 275 | 2 | 1 | 4
Repeater - Kelbaker - Overhead Line Work2 | Worker Commute | on | -- | -- | passenger | NA | 2 | 6 | 8
Repeater - Kelbaker - Pole Installation5 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 4 | 2 | 2
Repeater - Kelbaker - Pole Installation5 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 4 | 1 | 7
Repeater - Kelbaker - Pole Installation5 | 60-Foot Digger Derrick | off | 275 | Bore/Drill Rigs | -- | 275 | 4 | 1 | 4
Repeater - Kelbaker - Pole Installation5 | Worker Commute | on | -- | -- | passenger | NA | 4 | 6 | 8
Repeater - Kelbaker - Trenching, Structure Excavation1 | 1-Ton Crew Cab | on | -- | -- | passenger | 300 | 1 | 1 | 2
Repeater - Kelbaker - Trenching, Structure Excavation1 | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 1 | 1 | 8
Repeater - Kelbaker - Trenching, Structure Excavation1 | Dump Truck | on | -- | -- | hhdt | 350 | 1 | 1 | 4
Repeater - Kelbaker - Trenching, Structure Excavation1 | Worker Commute | on | -- | -- | passenger | NA | 1 | 4 | 8
Repeater - Kelbaker - Underground Cable Makeup4 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Repeater - Kelbaker - Underground Cable Makeup4 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 4
Repeater - Kelbaker - Underground Cable Makeup4 | Worker Commute | on | -- | -- | passenger | NA | 1 | 3 | 8
Repeater - Kelbaker - Underground Cable Pulling3 and Transformer Installation | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Repeater - Kelbaker - Underground Cable Pulling3 and Transformer Installation | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 7
Repeater - Kelbaker - Underground Cable Pulling3 and Transformer Installation | Hydraulic Rewind Puller | off | 300 | Other Construction Equipment | -- | 300 | 1 | 1 | 6
Repeater - Kelbaker - Underground Cable Pulling3 and Transformer Installation | Worker Commute | on | -- | -- | passenger | NA | 1 | 4 | 8
Repeater - Lanfair - Fiber optic repeater site installation | 1-Ton Crew Cab 4x4 | on | -- | -- | passenger | 300 | 12 | 1 | 4
Repeater - Lanfair - Fiber optic repeater site installation | 2-Ton Truck | on | -- | -- | delivery | 300 | 12 | 1 | 4
Repeater - Lanfair - Fiber optic repeater site installation | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 10 | 1 | 6
Repeater - Lanfair - Fiber optic repeater site installation | Concrete Pump | off | 350 | Pumps | -- | 350 | 2 | 1 | 6
Repeater - Lanfair - Fiber optic repeater site installation | Concrete Truck | on | -- | -- | hhdt | 300 | 2 | 1 | 6
Repeater - Lanfair - Fiber optic repeater site installation | Crane | off | 350 | Cranes | -- | 350 | 6 | 1 | 4
Repeater - Lanfair - Fiber optic repeater site installation | Drill Rig | off | 500 | Bore/Drill Rigs | -- | 500 | 7 | 1 | 6
Repeater - Lanfair - Fiber optic repeater site installation | Dump Truck | on | -- | -- | hhdt | 350 | 7 | 1 | 6
Repeater - Lanfair - Fiber optic repeater site installation | Flat Bed Truck | on | -- | -- | hhdt | 300 | 2 | 1 | 2
Repeater - Lanfair - Fiber optic repeater site installation | Fork lift | off | 200 | Forklifts | -- | 200 | 10 | 1 | 4
Repeater - Lanfair - Fiber optic repeater site installation | Worker Commute | on | -- | -- | passenger | NA | 12 | 8 | 8
Repeater - Lanfair - Overhead Line Work2 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 3 | 1 | 2
Repeater - Lanfair - Overhead Line Work2 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 3 | 1 | 7
Repeater - Lanfair - Overhead Line Work2 | 60-Foot Digger Derrick | off | 275 | Bore/Drill Rigs | -- | 275 | 3 | 1 | 4
Repeater - Lanfair - Overhead Line Work2 | Worker Commute | on | -- | -- | passenger | NA | 3 | 6 | 8
Repeater - Lanfair - Pole Installation5 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 9 | 2 | 2
Repeater - Lanfair - Pole Installation5 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 9 | 1 | 7
Repeater - Lanfair - Pole Installation5 | 60-Foot Digger Derrick | off | 275 | Bore/Drill Rigs | -- | 275 | 9 | 1 | 4
Repeater - Lanfair - Pole Installation5 | Worker Commute | on | -- | -- | passenger | NA | 9 | 6 | 8
Repeater - Lanfair - Trenching, Structure Excavation1 | 1-Ton Crew Cab | on | -- | -- | passenger | 300 | 1 | 1 | 2
Repeater - Lanfair - Trenching, Structure Excavation1 | Backhoe Front Loader | off | 300 | Tractors/Loaders/Backhoes | -- | 300 | 1 | 1 | 8
Repeater - Lanfair - Trenching, Structure Excavation1 | Dump Truck | on | -- | -- | hhdt | 350 | 1 | 1 | 4
Repeater - Lanfair - Trenching, Structure Excavation1 | Worker Commute | on | -- | -- | passenger | NA | 1 | 4 | 8
Repeater - Lanfair - Underground Cable Makeup4 | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Repeater - Lanfair - Underground Cable Makeup4 | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 4
Repeater - Lanfair - Underground Cable Makeup4 | Worker Commute | on | -- | -- | passenger | NA | 1 | 3 | 8
Repeater - Lanfair - Underground Cable Pulling3 and Transformer Installation | 1-Ton Crew Cab, 4x4 | on | -- | -- | passenger | 300 | 1 | 1 | 2
Repeater - Lanfair - Underground Cable Pulling3 and Transformer Installation | 55-Foot Double Bucket Truck | off | 300 | Aerial Lifts | -- | 300 | 1 | 1 | 7
Repeater - Lanfair - Underground Cable Pulling3 and Transformer Installation | Hydraulic Rewind Puller | off | 300 | Other Construction Equipment | -- | 300 | 1 | 1 | 6
Repeater - Lanfair - Underground Cable Pulling3 and Transformer Installation | Worker Commute | on | -- | -- | passenger | NA | 1 | 4 | 8
Substations - Eldorado - Electrical | Bobcat | off | 200 | Skid Steer Loaders | -- | 200 | 45 | 2 | 5
Substations - Eldorado - Electrical | Crane | off | 350 | Cranes | -- | 350 | 45 | 1 | 4
Substations - Eldorado - Electrical | Foreman's Truck | on | -- | -- | passenger | 300 | 45 | 1 | 4
Substations - Eldorado - Electrical | Forklift | off | 200 | Forklifts | -- | 200 | 45 | 2 | 5
Substations - Eldorado - Electrical | Generator | off | 50 | Generator Sets | -- | 50 | 45 | 2 | 8
Substations - Eldorado - Electrical | Job Site Utility Cart | on | -- | -- | passenger | 50 | 45 | 4 | 7
Substations - Eldorado - Electrical | Manlift | off | 150 | Aerial Lifts | -- | 150 | 45 | 2 | 5
Substations - Eldorado - Electrical | Tool Truck | on | -- | -- | delivery | 300 | 45 | 2 | 7
Substations - Eldorado - Electrical | Worker Commute | on | -- | -- | passenger | NA | 45 | 15 | 8
Substations - Eldorado - Electrical (Capacitor) | 135-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 20 | 1 | 5
Substations - Eldorado - Electrical (Capacitor) | 20,000-Pound Forklift | off | 150 | Forklifts | -- | 150 | 40 | 1 | 8
Substations - Eldorado - Electrical (Capacitor) | 27-Ton Boom Truck | off | 350 | Cranes | -- | 350 | 40 | 1 | 5
Substations - Eldorado - Electrical (Capacitor) | 65-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Substations - Eldorado - Electrical (Capacitor) | 85-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 30 | 1 | 5
Substations - Eldorado - Electrical (Capacitor) | Bobcat with Forks | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 2 | 8
Substations - Eldorado - Electrical (Capacitor) | Crane | off | 350 | Cranes | -- | 350 | 10 | 1 | 5
Substations - Eldorado - Electrical (Capacitor) | Foreman's Truck | on | -- | -- | passenger | 300 | 95 | 1 | 4
Substations - Eldorado - Electrical (Capacitor) | Genie 45-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 35 | 1 | 5
Substations - Eldorado - Electrical (Capacitor) | Job Site Utility Cart | on | -- | -- | passenger | 50 | 95 | 1 | 5
Substations - Eldorado - Electrical (Capacitor) | Scissor Lift | off | 50 | Aerial Lifts | -- | 50 | 95 | 3 | 6
Substations - Eldorado - Electrical (Capacitor) | Tele-Handler Forklift (5,000-7,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 75 | 1 | 8
Substations - Eldorado - Electrical (Capacitor) | Tele-Handler Forklift (8,000-12,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 50 | 1 | 8
Substations - Eldorado - Electrical (Capacitor) | Tool Truck | on | -- | -- | delivery | 300 | 95 | 1 | 7
Substations - Eldorado - Electrical (Capacitor) | Worker Commute | on | -- | -- | passenger | NA | 95 | 15 | 8
Substations - Eldorado - Grading and Civil | Backhoe | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 45 | 2 | 4
Substations - Eldorado - Grading and Civil | Bobcat | off | 200 | Skid Steer Loaders | -- | 200 | 45 | 2 | 5
Substations - Eldorado - Grading and Civil | Compactor | off | 300 | Rollers | -- | 300 | 45 | 1 | 5
Substations - Eldorado - Grading and Civil | Dump Truck | on | -- | -- | hhdt | 350 | 45 | 1 | 5
Substations - Eldorado - Grading and Civil | Excavator | off | 160 | Excavators | -- | 160 | 45 | 2 | 5
Substations - Eldorado - Grading and Civil | Foreman's Truck | on | -- | -- | passenger | 300 | 45 | 1 | 4
Substations - Eldorado - Grading and Civil | Fuel Truck | on | -- | -- | hhdt | 300 | 45 | 1 | 2
Substations - Eldorado - Grading and Civil | Generator | off | 50 | Generator Sets | -- | 50 | 45 | 2 | 8
Substations - Eldorado - Grading and Civil | Grader | off | 290 | Graders | -- | 290 | 45 | 2 | 5
Substations - Eldorado - Grading and Civil | Job site Utility Cart | on | -- | -- | passenger | 50 | 45 | 4 | 7
Substations - Eldorado - Grading and Civil | LoDrill | off | 200 | Bore/Drill Rigs | -- | 200 | 45 | 1 | 5
Substations - Eldorado - Grading and Civil | Low Bed Hauler | on | -- | -- | hhdt | 300 | 45 | 1 | 4
Substations - Eldorado - Grading and Civil | Skip Loader | off | 150 | Tractors/Loaders/Backhoes | -- | 150 | 45 | 1 | 4
Substations - Eldorado - Grading and Civil | Tool Truck | on | -- | -- | delivery | 300 | 45 | 2 | 7
Substations - Eldorado - Grading and Civil | Trencher | off | 175 | Trenchers | -- | 175 | 45 | 1 | 5
Substations - Eldorado - Grading and Civil | Water Truck | on | -- | -- | hhdt | 300 | 45 | 2 | 8
Substations - Eldorado - Grading and Civil | Worker Commute | on | -- | -- | passenger | NA | 45 | 15 | 8
Substations - Eldorado - Grading and Civil (Capacitors) | 10-Cubic-Yard Dump Truck | on | -- | -- | hhdt | 500 | 20 | 3 | 5
Substations - Eldorado - Grading and Civil (Capacitors) | 250-Ton Hydraulic Crane | off | 450 | Cranes | -- | 450 | 15 | 1 | 5
Substations - Eldorado - Grading and Civil (Capacitors) | 4,000-Gallon Water Truck | on | -- | -- | hhdt | 350 | 20 | 3 | 8
Substations - Eldorado - Grading and Civil (Capacitors) | 500-Gallon Water Buffalo with Truck | off | 185 | Off-Highway Trucks | -- | 185 | 15 | 1 | 5
Substations - Eldorado - Grading and Civil (Capacitors) | Bobcat Skid Steer | off | 93 | Skid Steer Loaders | -- | 93 | 15 | 1 | 8
Substations - Eldorado - Grading and Civil (Capacitors) | Bobcat with Auger | off | 93 | Skid Steer Loaders | -- | 93 | 15 | 1 | 8
Substations - Eldorado - Grading and Civil (Capacitors) | Bobcat with Sweeper | off | 93 | Skid Steer Loaders | -- | 93 | 15 | 1 | 8
Substations - Eldorado - Grading and Civil (Capacitors) | Ditch Witch | off | 42 | Trenchers | -- | 42 | 20 | 1 | 8
Substations - Eldorado - Grading and Civil (Capacitors) | Foreman's Truck | on | -- | -- | passenger | 300 | 15 | 1 | 4
Substations - Eldorado - Grading and Civil (Capacitors) | Job Site Utility Cart | on | -- | -- | passenger | 50 | 15 | 1 | 5
Substations - Eldorado - Grading and Civil (Capacitors) | Low Bed Equipment Hauler (5 axle) | on | -- | -- | hhdt | 700 | 15 | 1 | 4
Substations - Eldorado - Grading and Civil (Capacitors) | Low Bed Equipment Hauler (7 axle) | on | -- | -- | hhdt | 800 | 15 | 1 | 4
Substations - Eldorado - Grading and Civil (Capacitors) | Mini Excavator | off | 50 | Excavators | -- | 50 | 15 | 1 | 8
Substations - Eldorado - Grading and Civil (Capacitors) | Worker Commute | on | -- | -- | passenger | NA | 20 | 5 | 8
Substations - Eldorado - Survey | Foreman's Truck | on | -- | -- | passenger | 300 | 10 | 1 | 4
Substations - Eldorado - Survey | Job site Utility Cart | on | -- | -- | passenger | 50 | 10 | 1 | 7
Substations - Eldorado - Survey | Tool Truck | on | -- | -- | delivery | 300 | 10 | 1 | 7
Substations - Eldorado - Survey | Worker Commute | on | -- | -- | passenger | NA | 10 | 2 | 8
Substations - Eldorado - Testing | Test Truck | on | -- | -- | delivery | 300 | 75 | 2 | 7
Substations - Eldorado - Testing | Worker Commute | on | -- | -- | passenger | NA | 75 | 4 | 8
Substations - Eldorado - Wiring | Foreman's Truck | on | -- | -- | passenger | 300 | 60 | 1 | 4
Substations - Eldorado - Wiring | Job Site Utility Cart | on | -- | -- | passenger | 50 | 60 | 2 | 7
Substations - Eldorado - Wiring | Manlift | off | 150 | Aerial Lifts | -- | 150 | 25 | 1 | 5
Substations - Eldorado - Wiring | Tool Truck | on | -- | -- | delivery | 300 | 60 | 2 | 7
Substations - Eldorado - Wiring | Worker Commute | on | -- | -- | passenger | NA | 60 | 5 | 8
Substations - Eldorado - Wiring/Test (Capacitors) | Foreman's Truck | on | -- | -- | passenger | 300 | 40 | 1 | 4
Substations - Eldorado - Wiring/Test (Capacitors) | Job Site Utility Cart | on | -- | -- | passenger | 50 | 35 | 1 | 5
Substations - Eldorado - Wiring/Test (Capacitors) | Scissor Lift | off | 50 | Aerial Lifts | -- | 50 | 40 | 3 | 6
Substations - Eldorado - Wiring/Test (Capacitors) | Test Truck | on | -- | -- | delivery | 300 | 40 | 1 | 4
Substations - Eldorado - Wiring/Test (Capacitors) | Tool Truck | on | -- | -- | delivery | 300 | 35 | 1 | 7
Substations - Eldorado - Wiring/Test (Capacitors) | Worker Commute | on | -- | -- | passenger | NA | 40 | 10 | 8
Substations - Lugo - Electrical (Capacitors) - SC1 | 135-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC1 | 20,000-Pound Forklift | off | 150 | Forklifts | -- | 150 | 50 | 1 | 8
Substations - Lugo - Electrical (Capacitors) - SC1 | 27-Ton Boom Truck | off | 350 | Cranes | -- | 350 | 50 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC1 | 65-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 50 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC1 | 85-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC1 | Bobcat with Forks | off | 93 | Skid Steer Loaders | -- | 93 | 50 | 2 | 8
Substations - Lugo - Electrical (Capacitors) - SC1 | Crane | off | 350 | Cranes | -- | 350 | 20 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC1 | Foreman's Truck | on | -- | -- | passenger | 300 | 50 | 1 | 4
Substations - Lugo - Electrical (Capacitors) - SC1 | Genie 45-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 50 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC1 | Job Site Utility Cart | on | -- | -- | passenger | 50 | 50 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC1 | Scissor Lift | off | 50 | Aerial Lifts | -- | 50 | 50 | 3 | 6
Substations - Lugo - Electrical (Capacitors) - SC1 | Tele-Handler Forklift (5,000-7,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 50 | 1 | 8
Substations - Lugo - Electrical (Capacitors) - SC1 | Tele-Handler Forklift (8,000-12,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 50 | 1 | 8
Substations - Lugo - Electrical (Capacitors) - SC1 | Tool Truck | on | -- | -- | delivery | 300 | 50 | 1 | 7
Substations - Lugo - Electrical (Capacitors) - SC1 | Worker Commute | on | -- | -- | passenger | NA | 50 | 15 | 8
Substations - Lugo - Electrical (Capacitors) - SC4 | 135-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC4 | 20,000-Pound Forklift | off | 150 | Forklifts | -- | 150 | 50 | 1 | 8
Substations - Lugo - Electrical (Capacitors) - SC4 | 27-Ton Boom Truck | off | 350 | Cranes | -- | 350 | 50 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC4 | 65-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 50 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC4 | 85-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC4 | Bobcat with Forks | off | 93 | Skid Steer Loaders | -- | 93 | 50 | 2 | 8
Substations - Lugo - Electrical (Capacitors) - SC4 | Crane | off | 350 | Cranes | -- | 350 | 20 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC4 | Foreman's Truck | on | -- | -- | passenger | 300 | 50 | 1 | 4
Substations - Lugo - Electrical (Capacitors) - SC4 | Genie 45-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 50 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC4 | Job Site Utility Cart | on | -- | -- | passenger | 50 | 50 | 1 | 5
Substations - Lugo - Electrical (Capacitors) - SC4 | Scissor Lift | off | 50 | Aerial Lifts | -- | 50 | 50 | 3 | 6
Substations - Lugo - Electrical (Capacitors) - SC4 | Tele-Handler Forklift (5,000-7,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 50 | 1 | 8
Substations - Lugo - Electrical (Capacitors) - SC4 | Tele-Handler Forklift (8,000-12,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 50 | 1 | 8
Substations - Lugo - Electrical (Capacitors) - SC4 | Tool Truck | on | -- | -- | delivery | 300 | 50 | 1 | 7
Substations - Lugo - Electrical (Capacitors) - SC4 | Worker Commute | on | -- | -- | passenger | NA | 50 | 15 | 8
Substations - Lugo - Electrical Crew | Bobcat | off | 200 | Skid Steer Loaders | -- | 200 | 85 | 2 | 5
Substations - Lugo - Electrical Crew | Crane | off | 350 | Cranes | -- | 350 | 85 | 1 | 4
Substations - Lugo - Electrical Crew | Foreman's Truck | on | -- | -- | passenger | 300 | 85 | 1 | 4
Substations - Lugo - Electrical Crew | Forklift | off | 200 | Forklifts | -- | 200 | 85 | 2 | 5
Substations - Lugo - Electrical Crew | Generator | off | 50 | Generator Sets | -- | 50 | 85 | 2 | 8
Substations - Lugo - Electrical Crew | Job Site Utility Cart | on | -- | -- | passenger | 50 | 85 | 4 | 7
Substations - Lugo - Electrical Crew | Manlift | off | 150 | Aerial Lifts | -- | 150 | 85 | 2 | 5
Substations - Lugo - Electrical Crew | Tool Truck | on | -- | -- | delivery | 300 | 85 | 2 | 7
Substations - Lugo - Electrical Crew | Worker Commute | on | -- | -- | passenger | NA | 85 | 15 | 8
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | 10-Cubic-Yard Dump Truck | on | -- | -- | hhdt | 500 | 30 | 3 | 5
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | 250-Ton Hydraulic Crane | off | 450 | Cranes | -- | 450 | 30 | 1 | 5
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | 4,000 Water Truck | on | -- | -- | hhdt | 350 | 30 | 3 | 8
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | 500-Gallon Water Buffalo with Truck | off | 185 | Off-Highway Trucks | -- | 185 | 30 | 1 | 5
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | Bobcat Skid Steer | off | 93 | Skid Steer Loaders | -- | 93 | 30 | 1 | 8 | 5.1
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | Bobcat with Auger | off | 93 | Skid Steer Loaders | -- | 93 | 30 | 1 | 8
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | Bobcat with Sweeper | off | 93 | Skid Steer Loaders | -- | 93 | 30 | 1 | 8
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | Foreman's Truck | on | -- | -- | passenger | 300 | 30 | 1 | 4
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | Job site Utility Cart | on | -- | -- | passenger | 50 | 30 | 1 | 5
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | Low Bed Equipment Hauler (5 axle) | on | -- | -- | hhdt | 700 | 20 | 1 | 4
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | Low Bed Equipment Hauler (7 axle) | on | -- | -- | hhdt | 800 | 20 | 1 | 4
Substations - Lugo - Grading/Civil (Capacitors) - SC1 | Worker Commute | on | -- | -- | passenger | NA | 30 | 5 | 8
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | 10-Cubic-Yard Dump Truck | on | -- | -- | hhdt | 500 | 30 | 3 | 5
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | 250-Ton Hydraulic Crane | off | 450 | Cranes | -- | 450 | 30 | 1 | 5
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | 4,000 Water Truck | on | -- | -- | hhdt | 350 | 30 | 3 | 8
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | 500-Gallon Water Buffalo with Truck | off | 185 | Off-Highway Trucks | -- | 185 | 30 | 1 | 5
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | Bobcat Skid Steer | off | 93 | Skid Steer Loaders | -- | 93 | 30 | 1 | 8 | 5.1
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | Bobcat with Auger | off | 93 | Skid Steer Loaders | -- | 93 | 30 | 1 | 8
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | Bobcat with Sweeper | off | 93 | Skid Steer Loaders | -- | 93 | 30 | 1 | 8
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | Foreman's Truck | on | -- | -- | passenger | 300 | 30 | 1 | 4
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | Job site Utility Cart | on | -- | -- | passenger | 50 | 30 | 1 | 5
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | Low Bed Equipment Hauler (5 axle) | on | -- | -- | hhdt | 700 | 20 | 1 | 4
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | Low Bed Equipment Hauler (7 axle) | on | -- | -- | hhdt | 800 | 20 | 1 | 4
Substations - Lugo - Grading/Civil (Capacitors) - SC4 | Worker Commute | on | -- | -- | passenger | NA | 30 | 5 | 8
Substations - Lugo - Grading/Civil Crew | Backhoe | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 70 | 2 | 4
Substations - Lugo - Grading/Civil Crew | Bobcat | off | 200 | Skid Steer Loaders | -- | 200 | 70 | 2 | 5
Substations - Lugo - Grading/Civil Crew | Compactor | off | 300 | Rollers | -- | 300 | 70 | 1 | 5
Substations - Lugo - Grading/Civil Crew | Dump Truck | on | -- | -- | hhdt | 350 | 70 | 1 | 5
Substations - Lugo - Grading/Civil Crew | Excavator | off | 160 | Excavators | -- | 160 | 70 | 2 | 5
Substations - Lugo - Grading/Civil Crew | Foreman's Truck | on | -- | -- | passenger | 300 | 70 | 1 | 4
Substations - Lugo - Grading/Civil Crew | Fuel Truck | on | -- | -- | hhdt | 300 | 70 | 1 | 2
Substations - Lugo - Grading/Civil Crew | Generator | off | 50 | Generator Sets | -- | 50 | 70 | 2 | 8
Substations - Lugo - Grading/Civil Crew | Grader | off | 290 | Graders | -- | 290 | 70 | 2 | 8
Substations - Lugo - Grading/Civil Crew | Job site Utility Cart | on | -- | -- | passenger | 50 | 70 | 4 | 7
Substations - Lugo - Grading/Civil Crew | LoDrill | off | 200 | Bore/Drill Rigs | -- | 200 | 70 | 1 | 5
Substations - Lugo - Grading/Civil Crew | Low Bed Hauler | on | -- | -- | hhdt | 300 | 70 | 1 | 4
Substations - Lugo - Grading/Civil Crew | Skip Loader | off | 150 | Tractors/Loaders/Backhoes | -- | 150 | 70 | 1 | 4
Substations - Lugo - Grading/Civil Crew | Tool Truck | on | -- | -- | delivery | 300 | 70 | 2 | 7
Substations - Lugo - Grading/Civil Crew | Trencher | off | 175 | Trenchers | -- | 175 | 70 | 1 | 5
Substations - Lugo - Grading/Civil Crew | Water Truck | on | -- | -- | hhdt | 300 | 70 | 2 | 8
Substations - Lugo - Grading/Civil Crew | Worker Commute | on | -- | -- | passenger | NA | 70 | 15 | 8
Substations - Lugo - Survey | Foreman's Truck | on | -- | -- | passenger | 300 | 15 | 1 | 4
Substations - Lugo - Survey | Job site Utility Cart | on | -- | -- | passenger | 50 | 15 | 1 | 7
Substations - Lugo - Survey | Tool Truck | on | -- | -- | delivery | 300 | 15 | 1 | 7
Substations - Lugo - Survey | Worker Commute | on | -- | -- | passenger | NA | 15 | 2 | 8
Substations - Lugo - Test Crew | Test Truck | on | -- | -- | delivery | 300 | 140 | 2 | 7
Substations - Lugo - Test Crew | Worker Commute | on | -- | -- | passenger | NA | 140 | 4 | 8
Substations - Lugo - Wiring Crew | Foreman's Truck | on | -- | -- | passenger | 300 | 60 | 1 | 4
Substations - Lugo - Wiring Crew | Job Site Utility Cart | on | -- | -- | passenger | 50 | 60 | 2 | 7
Substations - Lugo - Wiring Crew | Manlift | off | 150 | Aerial Lifts | -- | 150 | 60 | 1 | 5
Substations - Lugo - Wiring Crew | Tool Truck | on | -- | -- | delivery | 300 | 60 | 2 | 7
Substations - Lugo - Wiring Crew | Worker Commute | on | -- | -- | passenger | NA | 60 | 5 | 8
Substations - Lugo - Wiring/Test (Capacitors) - SC1 | Foreman's Truck | on | -- | -- | passenger | 300 | 35 | 1 | 4
Substations - Lugo - Wiring/Test (Capacitors) - SC1 | Job Site Utility Cart | on | -- | -- | passenger | 50 | 35 | 1 | 5
Substations - Lugo - Wiring/Test (Capacitors) - SC1 | Test Truck | on | -- | -- | delivery | 300 | 35 | 1 | 4
Substations - Lugo - Wiring/Test (Capacitors) - SC1 | Tool Truck | on | -- | -- | delivery | 300 | 35 | 1 | 7
Substations - Lugo - Wiring/Test (Capacitors) - SC1 | Worker Commute | on | -- | -- | passenger | NA | 35 | 6 | 8
Substations - Lugo - Wiring/Test (Capacitors) - SC4 | Foreman's Truck | on | -- | -- | passenger | 300 | 35 | 1 | 4
Substations - Lugo - Wiring/Test (Capacitors) - SC4 | Job Site Utility Cart | on | -- | -- | passenger | 50 | 35 | 1 | 5
Substations - Lugo - Wiring/Test (Capacitors) - SC4 | Test Truck | on | -- | -- | delivery | 300 | 35 | 1 | 4
Substations - Lugo - Wiring/Test (Capacitors) - SC4 | Tool Truck | on | -- | -- | delivery | 300 | 35 | 1 | 7
Substations - Lugo - Wiring/Test (Capacitors) - SC4 | Worker Commute | on | -- | -- | passenger | NA | 35 | 6 | 8
Substations - Mohave - Electrical (Capacitors) | 135-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 20 | 1 | 5
Substations - Mohave - Electrical (Capacitors) | 20,000-Pound Forklift | off | 150 | Forklifts | -- | 150 | 40 | 1 | 8
Substations - Mohave - Electrical (Capacitors) | 27-Ton Boom Truck | off | 350 | Cranes | -- | 350 | 60 | 1 | 5
Substations - Mohave - Electrical (Capacitors) | 65-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Substations - Mohave - Electrical (Capacitors) | 85-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Substations - Mohave - Electrical (Capacitors) | Bobcat with Forks | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 2 | 8
Substations - Mohave - Electrical (Capacitors) | Crane | off | 350 | Cranes | -- | 350 | 20 | 1 | 5
Substations - Mohave - Electrical (Capacitors) | Foreman's Truck | on | -- | -- | passenger | 300 | 90 | 1 | 4
Substations - Mohave - Electrical (Capacitors) | Generator | off | 50 | Generator Sets | -- | 50 | 90 | 1 | 12
Substations - Mohave - Electrical (Capacitors) | Genie 45-Foot Manlift | off | 75 | Aerial Lifts | -- | 75 | 40 | 1 | 5
Substations - Mohave - Electrical (Capacitors) | Job Site Utility Cart | on | -- | -- | passenger | 50 | 90 | 1 | 5
Substations - Mohave - Electrical (Capacitors) | Scissor Lift | off | 50 | Aerial Lifts | -- | 50 | 90 | 3 | 6
Substations - Mohave - Electrical (Capacitors) | Tele-Handler Forklift (5,000-7,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 85 | 1 | 8
Substations - Mohave - Electrical (Capacitors) | Tele-Handler Forklift (8,000-12,000 Pounds) | off | 150 | Rough Terrain Forklifts | -- | 150 | 65 | 1 | 8
Substations - Mohave - Electrical (Capacitors) | Tool Truck | on | -- | -- | delivery | 300 | 90 | 1 | 7
Substations - Mohave - Electrical (Capacitors) | Worker Commute | on | -- | -- | passenger | NA | 90 | 15 | 8
Substations - Mohave - Electrical Crew | Bobcat | off | 200 | Skid Steer Loaders | -- | 200 | 35 | 2 | 5
Substations - Mohave - Electrical Crew | Crane | off | 350 | Cranes | -- | 350 | 35 | 1 | 4
Substations - Mohave - Electrical Crew | Foreman's Truck | on | -- | -- | passenger | 300 | 35 | 1 | 4
Substations - Mohave - Electrical Crew | Forklift | off | 200 | Forklifts | -- | 200 | 35 | 2 | 5
Substations - Mohave - Electrical Crew | Generator | off | 50 | Generator Sets | -- | 50 | 35 | 2 | 8
Substations - Mohave - Electrical Crew | Job Site Utility Cart | on | -- | -- | passenger | 50 | 35 | 4 | 7
Substations - Mohave - Electrical Crew | Manlift | off | 150 | Aerial Lifts | -- | 150 | 35 | 2 | 5
Substations - Mohave - Electrical Crew | Tool Truck | on | -- | -- | delivery | 300 | 35 | 2 | 7
Substations - Mohave - Electrical Crew | Worker Commute | on | -- | -- | passenger | NA | 35 | 15 | 8
Substations - Mohave - Grading/Civil (Capacitors) | 10 Cubic Yard Dump Truck | on | -- | -- | hhdt | 500 | 90 | 3 | 8
Substations - Mohave - Grading/Civil (Capacitors) | 250-Ton Hydraulic Crane | off | 450 | Cranes | -- | 450 | 30 | 1 | 5
Substations - Mohave - Grading/Civil (Capacitors) | 4,000-Gallon Water Truck | on | -- | -- | hhdt | 350 | 90 | 3 | 4
Substations - Mohave - Grading/Civil (Capacitors) | 50,000-Pound Excavator /Breaker | off | 200 | Excavators | -- | 200 | 30 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | 500-Gallon Water Buffalo with Truck | off | 185 | Off-Highway Trucks | -- | 185 | 90 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | 75,000-Pound Excavator | off | 350 | Excavators | -- | 350 | 30 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | 8,000-Gallon Water Pull | on | -- | -- | hhdt | 150 | 40 | 1 | 4
Substations - Mohave - Grading/Civil (Capacitors) | 84-Inch Vibratory Roller Compactor | off | 130 | Rollers | -- | 130 | 35 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Bobcat Compactor | off | 93 | Skid Steer Loaders | -- | 93 | 50 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Bobcat Skid Steer | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Bobcat with Auger | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Bobcat with Sweeper | off | 93 | Skid Steer Loaders | -- | 93 | 90 | 1 | 4
Substations - Mohave - Grading/Civil (Capacitors) | Cat 950 Loader | off | 130 | Tractors/Loaders/Backhoes | -- | 130 | 40 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | D-6 Cat Dozer | off | 215 | Crawler Tractors | -- | 215 | 40 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Ditch Witch | off | 42 | Trenchers | -- | 42 | 50 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Drill Rig | off | 500 | Bore/Drill Rigs | -- | 500 | 50 | 1 | 5
Substations - Mohave - Grading/Civil (Capacitors) | Excavator with Breaker | off | 524 | Excavators | -- | 524 | 50 | 1 | 5
Substations - Mohave - Grading/Civil (Capacitors) | Foreman's Truck | on | -- | -- | passenger | 300 | 90 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Job Site Utility Cart | on | -- | -- | passenger | 50 | 90 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | LoDrill Over 50,000 Pounds | off | 350 | Bore/Drill Rigs | -- | 350 | 20 | 1 | 5
Substations - Mohave - Grading/Civil (Capacitors) | LoDrill up to 50,000 Pounds | off | 200 | Bore/Drill Rigs | -- | 200 | 30 | 1 | 5
Substations - Mohave - Grading/Civil (Capacitors) | Low Bed Equipment Hauler (5 axle) | on | -- | -- | hhdt | 700 | 40 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Low Bed Equipment Hauler (7 axle) | on | -- | -- | hhdt | 800 | 40 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Low Side End Dump | on | -- | -- | hhdt | 500 | 90 | 3 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Mini Excavator | off | 50 | Excavators | -- | 50 | 50 | 1 | 5
Substations - Mohave - Grading/Civil (Capacitors) | Motor Grader | off | 250 | Graders | -- | 250 | 25 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Skip Loader | off | 150 | Tractors/Loaders/Backhoes | -- | 150 | 90 | 1 | 5
Substations - Mohave - Grading/Civil (Capacitors) | Tool Truck | on | -- | -- | delivery | 300 | 50 | 1 | 8
Substations - Mohave - Grading/Civil (Capacitors) | Vermeer RT-450 Trencher | off | 50 | Trenchers | -- | 50 | 30 | 1 | 5
Substations - Mohave - Grading/Civil (Capacitors) | Worker Commute | on | -- | -- | passenger | NA | 90 | 10 | 8
Substations - Mohave - Grading/Civil Crew | Backhoe | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 45 | 2 | 4
Substations - Mohave - Grading/Civil Crew | Bobcat | off | 200 | Skid Steer Loaders | -- | 200 | 45 | 2 | 5
Substations - Mohave - Grading/Civil Crew | Compactor | off | 300 | Rollers | -- | 300 | 45 | 1 | 5
Substations - Mohave - Grading/Civil Crew | Dump Truck | on | -- | -- | hhdt | 350 | 45 | 1 | 5
Substations - Mohave - Grading/Civil Crew | Excavator | off | 160 | Excavators | -- | 160 | 45 | 2 | 5
Substations - Mohave - Grading/Civil Crew | Foreman's Truck | on | -- | -- | passenger | 300 | 45 | 1 | 4
Substations - Mohave - Grading/Civil Crew | Fuel Truck | on | -- | -- | hhdt | 300 | 45 | 1 | 2
Substations - Mohave - Grading/Civil Crew | Generator | off | 50 | Generator Sets | -- | 50 | 45 | 2 | 8
Substations - Mohave - Grading/Civil Crew | Grader | off | 290 | Graders | -- | 290 | 45 | 2 | 5
Substations - Mohave - Grading/Civil Crew | Job Site Utility Cart | on | -- | -- | passenger | 50 | 45 | 4 | 7
Substations - Mohave - Grading/Civil Crew | LoDrill | off | 200 | Bore/Drill Rigs | -- | 200 | 45 | 1 | 5
Substations - Mohave - Grading/Civil Crew | Low Bed Hauler | on | -- | -- | hhdt | 300 | 45 | 1 | 4
Substations - Mohave - Grading/Civil Crew | Skip Loader | off | 150 | Tractors/Loaders/Backhoes | -- | 150 | 45 | 1 | 4
Substations - Mohave - Grading/Civil Crew | Tool Truck | on | -- | -- | delivery | 300 | 45 | 2 | 7
Substations - Mohave - Grading/Civil Crew | Trencher | off | 175 | Trenchers | -- | 175 | 45 | 1 | 5
Substations - Mohave - Grading/Civil Crew | Water Truck | on | -- | -- | hhdt | 300 | 45 | 2 | 8
Substations - Mohave - Grading/Civil Crew | Worker Commute | on | -- | -- | passenger | NA | 45 | 15 | 8
Substations - Mohave - Survey Crew | Foreman's Truck | on | -- | -- | passenger | 300 | 15 | 1 | 4
Substations - Mohave - Survey Crew | Job Site Utility Cart | on | -- | -- | passenger | 50 | 15 | 1 | 7
Substations - Mohave - Survey Crew | Tool Truck | on | -- | -- | delivery | 300 | 15 | 1 | 7
Substations - Mohave - Survey Crew | Worker Commute | on | -- | -- | passenger | NA | 15 | 2 | 8
Substations - Mohave - Test Crew | Test Truck | on | -- | -- | delivery | 300 | 60 | 2 | 7
Substations - Mohave - Test Crew | Worker Commute | on | -- | -- | passenger | NA | 60 | 4 | 8
Substations - Mohave - Wiring Crew | Foreman's Truck | on | -- | -- | passenger | 300 | 45 | 1 | 4
Substations - Mohave - Wiring Crew | Job Site Utility Cart | on | -- | -- | passenger | 50 | 45 | 2 | 7
Substations - Mohave - Wiring Crew | Manlift | off | 150 | Aerial Lifts | -- | 150 | 45 | 1 | 5
Substations - Mohave - Wiring Crew | Tool Truck | on | -- | -- | delivery | 300 | 45 | 2 | 7
Substations - Mohave - Wiring Crew | Worker Commute | on | -- | -- | passenger | NA | 45 | 5 | 8
Substations - Mohave - Wiring/Test (Capacitors) | Foreman's Truck | on | -- | -- | passenger | 300 | 50 | 1 | 4
Substations - Mohave - Wiring/Test (Capacitors) | Job Site Utility Cart | on | -- | -- | passenger | 50 | 50 | 1 | 5
Substations - Mohave - Wiring/Test (Capacitors) | Scissor Lift | off | 50 | Aerial Lifts | -- | 50 | 50 | 3 | 6
Substations - Mohave - Wiring/Test (Capacitors) | Test Truck | on | -- | -- | delivery | 300 | 40 | 1 | 4
Substations - Mohave - Wiring/Test (Capacitors) | Tool Truck | on | -- | -- | delivery | 300 | 50 | 1 | 7
Substations - Mohave - Wiring/Test (Capacitors) | Worker Commute | on | -- | -- | passenger | NA | 50 | 6 | 8
Trans, Subtrans, Telecom - None - All Dielectric Self Supporting (ADSS) Splicing and Termination31 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 60 | 1 | 8
Trans, Subtrans, Telecom - None - All Dielectric Self Supporting (ADSS) Splicing and Termination31 | Medium Duty Splicing Lab Truck | on | -- | -- | delivery | 250 | 60 | 2 | 8
Trans, Subtrans, Telecom - None - All Dielectric Self Supporting (ADSS) Splicing and Termination31 | Worker Commute | on | -- | -- | passenger | NA | 60 | 5 | 8
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 30 | 1 | 8
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | 3/4-Ton Truck, 4x4 | on | -- | -- | passenger | 275 | 30 | 1 | 8
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | Auger Truck | off | 210 | Bore/Drill Rigs | -- | 210 | 30 | 1 | 4
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | Boom/Crane Truck | off | 350 | Cranes | -- | 350 | 30 | 1 | 6
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | Compressor Trailer | off | 60 | Air Compressors | -- | 60 | 30 | 1 | 4
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | Digger Derrick 6060 | off | 300 | Bore/Drill Rigs | -- | 300 | 30 | 2 | 8
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | Extendable Flat Bed Pole Truck | on | -- | -- | hhdt | 400 | 30 | 1 | 8
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | Manlift/Bucket Truck | off | 250 | Aerial Lifts | -- | 250 | 30 | 1 | 4
Trans, Subtrans, Telecom - None - Guard Structure Installation10 | Worker Commute | on | -- | -- | passenger | NA | 30 | 6 | 8
Trans, Subtrans, Telecom - None - Guard Structure Removal26 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 20 | 1 | 8
Trans, Subtrans, Telecom - None - Guard Structure Removal26 | 3/4-Ton Truck, 4x4 | on | -- | -- | passenger | 275 | 20 | 1 | 8
Trans, Subtrans, Telecom - None - Guard Structure Removal26 | Boom/Crane Truck | off | 350 | Cranes | -- | 350 | 20 | 1 | 6
Trans, Subtrans, Telecom - None - Guard Structure Removal26 | Compressor Trailer | off | 60 | Air Compressors | -- | 60 | 20 | 1 | 4
Trans, Subtrans, Telecom - None - Guard Structure Removal26 | Digger Derrick 6060 | off | 300 | Bore/Drill Rigs | -- | 300 | 20 | 2 | 8
Trans, Subtrans, Telecom - None - Guard Structure Removal26 | Extendable Flat Bed Pole Truck | on | -- | -- | hhdt | 400 | 20 | 1 | 8
Trans, Subtrans, Telecom - None - Guard Structure Removal26 | Manlift/Bucket Truck | off | 250 | Aerial Lifts | -- | 250 | 20 | 1 | 4
Trans, Subtrans, Telecom - None - Guard Structure Removal26 | Worker Commute | on | -- | -- | passenger | NA | 20 | 6 | 8
Trans, Subtrans, Telecom - None - Install TSP Foundation21 | 3/4-Ton Truck, 4x4 | on | -- | -- | passenger | 275 | 6 | 2 | 4
Trans, Subtrans, Telecom - None - Install TSP Foundation21 | Auger Truck | off | 210 | Bore/Drill Rigs | -- | 210 | 3 | 1 | 6
Trans, Subtrans, Telecom - None - Install TSP Foundation21 | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 6 | 1 | 6
Trans, Subtrans, Telecom - None - Install TSP Foundation21 | Boom/Crane Truck | off | 350 | Cranes | -- | 350 | 6 | 1 | 4
Trans, Subtrans, Telecom - None - Install TSP Foundation21 | Concrete Mixer Truck | on | -- | -- | hhdt | 350 | 4 | 3 | 2
Trans, Subtrans, Telecom - None - Install TSP Foundation21 | Dump Truck | on | -- | -- | hhdt | 350 | 6 | 1 | 4
Trans, Subtrans, Telecom - None - Install TSP Foundation21 | Water Truck | on | -- | -- | hhdt | 300 | 6 | 1 | 8
Trans, Subtrans, Telecom - None - Install TSP Foundation21 | Worker Commute | on | -- | -- | passenger | NA | 6 | 6 | 8
Trans, Subtrans, Telecom - None - LST Foundation Reinforcement14 | 3/4-Ton Truck, 4x4 | on | -- | -- | passenger | 275 | 20 | 2 | 4
Trans, Subtrans, Telecom - None - LST Foundation Reinforcement14 | Auger Truck | off | 210 | Bore/Drill Rigs | -- | 210 | 20 | 1 | 6
Trans, Subtrans, Telecom - None - LST Foundation Reinforcement14 | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 20 | 1 | 6
Trans, Subtrans, Telecom - None - LST Foundation Reinforcement14 | Boom/Crane Truck | off | 350 | Cranes | -- | 350 | 20 | 1 | 4
Trans, Subtrans, Telecom - None - LST Foundation Reinforcement14 | Concrete Mixer Truck | on | -- | -- | hhdt | 350 | 15 | 3 | 2
Trans, Subtrans, Telecom - None - LST Foundation Reinforcement14 | Dump Truck | on | -- | -- | hhdt | 350 | 20 | 1 | 4
Trans, Subtrans, Telecom - None - LST Foundation Reinforcement14 | Water Truck | on | -- | -- | hhdt | 300 | 20 | 1 | 8
Trans, Subtrans, Telecom - None - LST Foundation Reinforcement14 | Worker Commute | on | -- | -- | passenger | NA | 20 | 7 | 8
Trans, Subtrans, Telecom - None - Marshalling Yard7 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 78 | 1 | 4
Trans, Subtrans, Telecom - None - Marshalling Yard7 | Boom/Crane Truck | off | 350 | Cranes | -- | 350 | 78 | 1 | 2
Trans, Subtrans, Telecom - None - Marshalling Yard7 | R/T Forklift | off | 125 | Rough Terrain Forklifts | -- | 125 | 78 | 1 | 6
Trans, Subtrans, Telecom - None - Marshalling Yard7 | Truck, Semi-Tractor | on | -- | -- | hhdt | 400 | 78 | 1 | 2
Trans, Subtrans, Telecom - None - Marshalling Yard7 | Water Truck | on | -- | -- | hhdt | 300 | 78 | 1 | 8
Trans, Subtrans, Telecom - None - Marshalling Yard7 | Worker Commute | on | -- | -- | passenger | NA | 78 | 4 | 8
Trans, Subtrans, Telecom - None - Overhead Cable30 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 6 | 1 | 8
Trans, Subtrans, Telecom - None - Overhead Cable30 | Manlift/Bucket Truck | off | 250 | Aerial Lifts | -- | 250 | 6 | 3 | 6
Trans, Subtrans, Telecom - None - Overhead Cable30 | Wire Truck/Trailer | off | 10 | Other Construction Equipment | -- | 10 | 6 | 1 | 6
Trans, Subtrans, Telecom - None - Overhead Cable30 | Worker Commute | on | -- | -- | passenger | NA | 6 | 5 | 8
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 210 | 6 | 4
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | 3/4-Ton Truck, 4x4 | on | -- | -- | passenger | 275 | 210 | 4 | 4
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 210 | 1 | 4
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Boom/Crane Truck | off | 350 | Cranes | -- | 350 | 210 | 2 | 8
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Bullwheel Puller | off | 350 | Other Construction Equipment | -- | 350 | 150 | 1 | 8
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | D8 Cat | off | 350 | Crawler Tractors | -- | 350 | 210 | 2 | 2
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Dump Truck | on | -- | -- | hhdt | 350 | 210 | 1 | 2
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Fuel, Helicopter Support Truck | on | -- | -- | hhdt | 300 | 210 | 4 | 6
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Hughes 530F Helicopter | NA | -- | -- | -- | NA | 210 | 4 | 6
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Lowboy Truck/Trailer | on | -- | -- | hhdt | 450 | 210 | 3 | 4
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Manlift/Bucket Truck | off | 250 | Aerial Lifts | -- | 250 | 210 | 4 | 8
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | R/T Crane (M) | off | 215 | Cranes | -- | 215 | 210 | 2 | 4
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Sag Cat w/ 2 winches | off | 350 | Crawler Tractors | -- | 350 | 105 | 2 | 2
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Skid Steer Mulcher | off | 110 | Tractors/Loaders/Backhoes | -- | 110 | 210 | 2 | 8
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Splicing Lab | on | -- | -- | passenger | 300 | 210 | 2 | 8
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Static Truck/ Tensioner | off | 350 | Other Construction Equipment | -- | 350 | 210 | 1 | 8
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Wire Truck/Trailer | off | 10 | Other Construction Equipment | -- | 10 | 150 | 4 | 6
Trans, Subtrans, Telecom - None - OHGW Removal, OPGW Installation, Splicing, Peak Modification25 | Worker Commute | on | -- | -- | passenger | NA | 210 | 44 | 8
Trans, Subtrans, Telecom - None - Restoration27 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 82 | 2 | 4
Trans, Subtrans, Telecom - None - Restoration27 | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 82 | 1 | 4
Trans, Subtrans, Telecom - None - Restoration27 | Drum Type Compactor | off | 100 | Rollers | -- | 100 | 82 | 1 | 4
Trans, Subtrans, Telecom - None - Restoration27 | Lowboy Truck/Trailer | on | -- | -- | hhdt | 450 | 82 | 1 | 4
Trans, Subtrans, Telecom - None - Restoration27 | Motor Grader | off | 250 | Graders | -- | 250 | 82 | 1 | 6
Trans, Subtrans, Telecom - None - Restoration27 | Water Truck | on | -- | -- | hhdt | 300 | 82 | 1 | 8
Trans, Subtrans, Telecom - None - Restoration27 | Worker Commute | on | -- | -- | passenger | NA | 82 | 7 | 8
Trans, Subtrans, Telecom - None - Right-of-Way Clearing8 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 82 | 1 | 8
Trans, Subtrans, Telecom - None - Right-of-Way Clearing8 | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 82 | 1 | 6
Trans, Subtrans, Telecom - None - Right-of-Way Clearing8 | Lowboy Truck/Trailer | on | -- | -- | hhdt | 450 | 82 | 1 | 4
Trans, Subtrans, Telecom - None - Right-of-Way Clearing8 | Motor Grader | off | 250 | Graders | -- | 250 | 82 | 1 | 6
Trans, Subtrans, Telecom - None - Right-of-Way Clearing8 | Track Type Dozer | off | 150 | Crawler Tractors | -- | 150 | 82 | 1 | 6
Trans, Subtrans, Telecom - None - Right-of-Way Clearing8 | Water Truck | on | -- | -- | hhdt | 300 | 82 | 1 | 8
Trans, Subtrans, Telecom - None - Right-of-Way Clearing8 | Worker Commute | on | -- | -- | passenger | NA | 82 | 5 | 8
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 8 | 1 | 8
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 8 | 1 | 4
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | Drum Type Compactor | off | 100 | Rollers | -- | 100 | 8 | 1 | 6
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | Excavator | off | 160 | Excavators | -- | 160 | 4 | 1 | 4
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | Lowboy Truck/Trailer | on | -- | -- | hhdt | 450 | 8 | 1 | 4
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | Motor Grader | off | 250 | Graders | -- | 250 | 8 | 1 | 6
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | Track Type Dozer | off | 150 | Crawler Tractors | -- | 150 | 8 | 1 | 4
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | Water Truck | on | -- | -- | hhdt | 300 | 8 | 1 | 8
Trans, Subtrans, Telecom - None - Roads and Landing Work9 | Worker Commute | on | -- | -- | passenger | NA | 8 | 5 | 8
Trans, Subtrans, Telecom - None - Survey6 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 90 | 2 | 8
Trans, Subtrans, Telecom - None - Survey6 | Worker Commute | on | -- | -- | passenger | NA | 90 | 8 | 8
Trans, Subtrans, Telecom - None - Trench Installation28 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 90 | 2 | 6
Trans, Subtrans, Telecom - None - Trench Installation28 | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 90 | 1 | 6
Trans, Subtrans, Telecom - None - Trench Installation28 | Compressor Trailer | off | 60 | Air Compressors | -- | 60 | 90 | 1 | 6
Trans, Subtrans, Telecom - None - Trench Installation28 | Dump Truck | on | -- | -- | hhdt | 350 | 90 | 2 | 6
Trans, Subtrans, Telecom - None - Trench Installation28 | Water Truck | on | -- | -- | hhdt | 300 | 90 | 1 | 8
Trans, Subtrans, Telecom - None - Trench Installation28 | Worker Commute | on | -- | -- | passenger | NA | 90 | 8 | 8
Trans, Subtrans, Telecom - None - TSP Assembly23 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 2 | 2 | 4
Trans, Subtrans, Telecom - None - TSP Assembly23 | 3/4-Ton Truck, 4x4 | on | -- | -- | passenger | 275 | 2 | 2 | 4
Trans, Subtrans, Telecom - None - TSP Assembly23 | Boom/Crane Truck | off | 350 | Cranes | -- | 350 | 2 | 1 | 8
Trans, Subtrans, Telecom - None - TSP Assembly23 | Compressor Trailer | off | 60 | Air Compressors | -- | 60 | 2 | 1 | 6
Trans, Subtrans, Telecom - None - TSP Assembly23 | Worker Commute | on | -- | -- | passenger | NA | 2 | 10 | 8
Trans, Subtrans, Telecom - None - TSP Erection24 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 2 | 2 | 4
Trans, Subtrans, Telecom - None - TSP Erection24 | 3/4-Ton Truck, 4x4 | on | -- | -- | passenger | 275 | 2 | 2 | 4
Trans, Subtrans, Telecom - None - TSP Erection24 | Compressor Trailer | off | 60 | Air Compressors | -- | 60 | 2 | 1 | 4
Trans, Subtrans, Telecom - None - TSP Erection24 | R/T Crane (L) | off | 275 | Cranes | -- | 275 | 2 | 1 | 8
Trans, Subtrans, Telecom - None - TSP Erection24 | Worker Commute | on | -- | -- | passenger | NA | 2 | 10 | 8
Trans, Subtrans, Telecom - None - TSP Foundation Removal20 | 3/4-Ton Truck, 4x4 | on | -- | -- | passenger | 275 | 8 | 1 | 4
Trans, Subtrans, Telecom - None - TSP Foundation Removal20 | Backhoe/Front Loader | off | 200 | Tractors/Loaders/Backhoes | -- | 200 | 8 | 1 | 6
Trans, Subtrans, Telecom - None - TSP Foundation Removal20 | Compressor Trailer | off | 60 | Air Compressors | -- | 60 | 8 | 1 | 8
Trans, Subtrans, Telecom - None - TSP Foundation Removal20 | Dump Truck | on | -- | -- | hhdt | 350 | 8 | 1 | 6
Trans, Subtrans, Telecom - None - TSP Foundation Removal20 | Excavator | off | 160 | Excavators | -- | 160 | 8 | 1 | 4
Trans, Subtrans, Telecom - None - TSP Foundation Removal20 | Worker Commute | on | -- | -- | passenger | NA | 8 | 4 | 8
Trans, Subtrans, Telecom - None - TSP Haul22 | 3/4-Ton Truck, 4x4 | on | -- | -- | passenger | 275 | 1 | 1 | 8
Trans, Subtrans, Telecom - None - TSP Haul22 | Boom/Crane Truck | off | 350 | Cranes | -- | 350 | 1 | 1 | 6
Trans, Subtrans, Telecom - None - TSP Haul22 | Flat Bed Pole Truck | on | -- | -- | hhdt | 400 | 1 | 1 | 8
Trans, Subtrans, Telecom - None - TSP Haul22 | Worker Commute | on | -- | -- | passenger | NA | 1 | 4 | 8
Trans, Subtrans, Telecom - None - TSP Removal19 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 6 | 2 | 4
Trans, Subtrans, Telecom - None - TSP Removal19 | Boom/Crane Truck | off | 350 | Cranes | -- | 350 | 6 | 1 | 6
Trans, Subtrans, Telecom - None - TSP Removal19 | Compressor Trailer | off | 60 | Air Compressors | -- | 60 | 6 | 1 | 8
Trans, Subtrans, Telecom - None - TSP Removal19 | Flat Bed Truck/Trailer | on | -- | -- | hhdt | 400 | 6 | 1 | 4
Trans, Subtrans, Telecom - None - TSP Removal19 | R/T Crane (M) | off | 215 | Cranes | -- | 215 | 6 | 1 | 6
Trans, Subtrans, Telecom - None - TSP Removal19 | Worker Commute | on | -- | -- | passenger | NA | 6 | 6 | 8
Trans, Subtrans, Telecom - None - Underground Cable Installation29 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 15 | 1 | 8
Trans, Subtrans, Telecom - None - Underground Cable Installation29 | Manlift/Bucket Truck | off | 250 | Aerial Lifts | -- | 250 | 15 | 3 | 6
Trans, Subtrans, Telecom - None - Underground Cable Installation29 | Wire Truck/Trailer | off | 10 | Other Construction Equipment | -- | 10 | 15 | 1 | 6
Trans, Subtrans, Telecom - None - Underground Cable Installation29 | Worker Commute | on | -- | -- | passenger | NA | 15 | 5 | 8
Trans, Subtrans, Telecom - None - Wood Pole Modification11 | 1-Ton Truck, 4x4 | on | -- | -- | passenger | 300 | 2 | 2 | 8
Trans, Subtrans, Telecom - None - Wood Pole Modification11 | Boom/Crane Truck | off | 350 | Cranes | -- | 350 | 2 | 1 | 6
Trans, Subtrans, Telecom - None - Wood Pole Modification11 | Compressor Trailer | off | 60 | Air Compressors | -- | 60 | 2 | 1 | 4
Trans, Subtrans, Telecom - None - Wood Pole Modification11 | Flat Bed Truck/ Trailer | on | -- | -- | hhdt | 400 | 2 | 1 | 8
Trans, Subtrans, Telecom - None - Wood Pole Modification11 | Manlift/Bucket Truck | off | 250 | Aerial Lifts | -- | 250 | 2 | 1 | 6
Trans, Subtrans, Telecom - None - Wood Pole Modification11 | Worker Commute | on | -- | -- | passenger | NA | 2 | 10 | 8

## OnRoadDistances
Vehicle Type | HP | Fuel | On Type | Trip Distance | Paved Percent | Paved Distance | Unpaved Distance | Trips per day
1-Ton Crew Cab, 4x4 | 300 | Gas | passenger | 100 | 90 | 90 | 10 | 1
4000 Water Truck | 425 | Diesel | hhdt | 100 | 75 | 75 | 25 | 1
Truck, Semi Tractor | 400 | Diesel | hhdt | 100 | 90 | 90 | 10 | 1
Lowboy Truck/Trailer | 450 | Diesel | hhdt | 100 | 90 | 90 | 10 | 1
3/4-Ton Truck, 4x4 | 275 | Gas | passenger | 100 | 90 | 90 | 10 | 1
Flat Bed Truck/Trailer | 400 | Diesel | hhdt | 100 | 90 | 90 | 10 | 1
10 C.Y. Dump Truck | 500 | Diesel | hhdt | 100 | 90 | 90 | 10 | 1
Concrete Mixer Truck | 350 | Diesel | hhdt | 100 | 90 | 90 | 10 | 1
Helicopter Support Truck | 300 | Gas | delivery | 100 | 90 | 90 | 10 | 1
Splicing Lab | 300 | Diesel | passenger | 100 | 90 | 90 | 10 | 1
Fuel Truck | 300 | Diesel | hhdt | 100 | 90 | 90 | 10 | 1
Medium duty splicing lab Truck | 250 | Diesel | delivery | 100 | 90 | 90 | 10 | 1
Tool Truck | 300 | Gas | delivery | 100 | 90 | 90 | 10 | 1
Job Site Utility Cart | 90 | Diesel | passenger | 100 | 90 | 90 | 10 | 1
Foreman's Truck | 400 | Gas | passenger | 100 | 90 | 90 | 10 | 1
Low Bed Hauler | 300 | Gas | hhdt | 100 | 90 | 90 | 10 | 1
Test Truck | 300 | Gas | delivery | 100 | 90 | 90 | 10 | 1
Low Bed Equipment Hauler (5 axle) | 700 | Diesel | hhdt | 100 | 90 | 90 | 10 | 1
Low Bed Equipment Hauler (7 axle) | 800 | Diesel | hhdt | 100 | 90 | 90 | 10 | 1
8,000 Gal. Water Pull | 900 | Diesel | hhdt | 100 | 75 | 75 | 25 | 1
Low Side End Dump | 500 | Diesel | hhdt | 100 | 90 | 90 | 10 | 1
2-Ton Truck | 300 | Diesel | delivery | 100 | 90 | 90 | 10 | 1
Worker Commute | NA | Diesel | passenger | 100 | 100 | 100 | 0 | 1

## OffRoadLoadFactors
CalEEMod Category | Load Factor
Aerial Lifts | 0.31
Air Compressors | 0.48
Bore/Drill Rigs | 0.5
Cement and Mortar Mixers | 0.56
Concrete/Industrial Saws | 0.73
Cranes | 0.29
Crawler Tractors | 0.43
Crushing/Proc. Equipment | 0.78
Dumpers/Tenders | 0.38
Excavators | 0.38
Forklifts | 0.2
Generator Sets | 0.74
Graders | 0.41
Off-Highway Tractors | 0.44
Off-Highway Trucks | 0.38
Other Construction Equipment | 0.42
Other General Industrial Equipment | 0.34
Other Material Handling Equipment | 0.4
Pavers | 0.42
Paving Equipment | 0.36
Plate Compactors | 0.43
Pressure Washers | 0.3
Pumps | 0.74
Rollers | 0.38
Rough Terrain Forklifts | 0.4
Rubber Tired Dozers | 0.4
Rubber Tired Loaders | 0.36
Scrapers | 0.48
Signal Boards | 0.82
Skid Steer Loaders | 0.37
Surfacing Equipment | 0.3
Sweepers/Scrubbers | 0.46
Tractors/Loaders/Backhoes | 0.37
Trenchers | 0.5
Welders | 0.45

## OnRoadEFs
On Uncontrolled Exhaust
Vehicle Type | ROG | NOX | CO | SOX | PM10 | PM25 | CO2 | CH4 | N | 365 | 365 | W | 2.5 | 2.4
passenger | 0.0003079 | 0.0002788 | 0.003281 | 7.92e-06 | 4.75e-06 | 4.21e-06 | 0.78851 | 2.82e-05
delivery | 0.0003462 | 0.0046832 | 0.0020229 | 2.31e-05 | 0.0001496 | 0.0001431 | 2.3978 | 3e-05
hhdt | 0.0001614 | 0.0061023 | 0.0009234 | 3.08e-05 | 3.43e-05 | 3.28e-05 | 3.2334 | 1.72e-05
On Controlled Exhaust
Vehicle Type | ROG | NOX | CO | SOX | PM10 | PM25 | CO2 | CH4
passenger | 0.0003079 | 0.0002786 | 0.003281 | 7.92e-06 | 4.57e-06 | 4.21e-06 | 0.78851 | 2.82e-05
delivery | 0.0003462 | 0.0046832 | 0.0020226 | 2.31e-05 | 0.0001496 | 0.0001431 | 2.3978 | 3e-05
hhdt | 0.0001614 | 0.0061023 | 0.0009234 | 3.08e-05 | 3.43e-05 | 3.28e-05 | 3.2334 | 1.72e-05
On Uncontrolled Dust
Vehicle Type | Road Type | PM10 | PM25 | State
passenger | Paved | 0.0007597 | 0.0002014 | Nevada
delivery | Paved | 0.0009749 | 0.000292 | Nevada
hhdt | Paved | 0.0008759 | 0.0002402 | Nevada
passenger | Unpaved | 1.4718 | 0.14689 | Nevada
delivery | Unpaved | 1.472 | 0.14698 | Nevada
hhdt | Unpaved | 1.4719 | 0.14693 | Nevada
passenger | Paved | 0.0007597 | 0.0002014 | California
delivery | Paved | 0.0009749 | 0.000292 | California
hhdt | Paved | 0.0008759 | 0.0002402 | California
passenger | Unpaved | 1.4718 | 0.14689 | California
delivery | Unpaved | 1.472 | 0.14698 | California
hhdt | Unpaved | 1.4719 | 0.14693 | California
On Controlled Dust
Vehicle Type | Road Type | PM10 | PM25 | State
passenger | Paved | 0.0007597 | 0.0002014 | Nevada
delivery | Paved | 0.0009137 | 0.0002663 | Nevada
hhdt | Paved | 0.0008753 | 0.00024 | Nevada
passenger | Unpaved | 0.40556 | 0.040445 | Nevada
delivery | Unpaved | 0.40578 | 0.040535 | Nevada
hhdt | Unpaved | 0.40568 | 0.040484 | Nevada
passenger | Paved | 0.0007597 | 0.0002014 | California
delivery | Paved | 0.0009137 | 0.0002663 | California
hhdt | Paved | 0.0008753 | 0.00024 | California
passenger | Unpaved | 0.23548 | 0.023503 | California
delivery | Unpaved | 0.23552 | 0.023518 | California
hhdt | Unpaved | 0.2355 | 0.023509 | California

## HelicopterEF
Category | CO | ROG | NOX | SOX | PM10 | PM25 | CO2 | CH4
Helicopter | 2.942 | 0.468 | 2.942 | 0.744 | 1.212 | 1.0908 | 1798.572 | 0.058261

## EarthworkEFs
Uncontrolled
Category | PM10 | PM25
Soil Handling | 0.00162 | 0.000336
Grading | 1.481 | 0.308
Controlled
Category | PM10 | PM25
Soil Handling | 0.000891 | 0.0001848
Grading | 0.81455 | 0.1694