## Instructions
California Public Utilities Commission - 2011 ARRA Project Data Request
Each month PG&E, SCE, and SDG&E must provide the requested information for all RPS-eligible generation projects that the utility has executed or is negotiating a power purchase agreement with for projects that are seeking or have received ARRA funding. Also, each utility must report on the transmission projects that will support RPS-eligible generation projects that are seeking or have received funding under an ARRA program, for which the utility is the Participating Transmission Owner. - The ARRA Project Tracking Spreadsheet includes two tabs; "RPS Generation Projects" and "Transmission Projects". Please provide complete information on each tab to the greatest extent possible. - Please highlight all cells that include new or updated information. - Information provided in the ARRA Project Tracking Spreadsheet should correspond with or provide updates to the most recently filed RPS Project Development Status Report (PDSR).

## RPS Generation Projects
Confidential: for internal CPUC use
Blue - RPS project Information
Yellow - Interconnection Information | [9 empty] | updated 2/3/2011
Green - Transmission Information
Orange - Permitting Information
Pink - Updated Information |  |  |  | RPS GENERATION PROJECT INFORMATION | [6 empty] | INTERCONNECTION PROCESS | [7 empty] | TRANSMISSION UPGRADES |  |  |  |  | PERMITTING INFORMATION
Project Name & (Project Owner) | CPUC ID # | REAT List # | Contracting Utility | ARRA funding request and deadline(s) | Status of ARRA funding request(s) | Power Purchase Agreement (PPA) Status per CPUC | Technology | Project Capacity (MW) | Score from Project Viability Calculator | Project Development Roadblocks | Queue (e.g., CAISO, IID, BPA, IOU WDAT) | Queue Position | Interconnection Plan | Full Capacity or Energy Only | Feasibility Study | System Impact Study or Phase I Cluster Study | Facilities Study or Phase II Cluster Study | Interconnection Agreement Status | Permits Req'd for Interconnection Facilities | Interconnection Environmental Review Lead Agency | Permits Req'd for Network Delivery Upgrades | Are network upgrades required to make the project fully deliverable? | Transmission Roadblocks | Permit ID (e.g., CEC, BLM, County) | Status of BLM Review | Expected Date Filed (permit?) | Project Acreage | Project Acres/MW | CEC jurisdic-tional? | On BLM Fast-Track List? | County | State
High Plains Ranch II (Sunpower) | PG0711 |  | PG&E | 12/31/2011: Planning to apply for both a Treasury grant in lieu of ITC under ARRA § 1603 and a DOE loan guarantee as part of the Financial Institution Partnership Program. | DOE: under review. Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 210 | 89.82 | None identified | CAISO | 239 | CAISO Transition Cluster: Phase 2 transmission studies complete. Proposed Interconnection is PG&E's Morro Bay-Midway 230kV transmission line in PG&E service territory. | Full Capacity | Complete | Complete | Complete | Under negotiation - Expected Q1 2011. | Counterparty incorporated some interconnection facilities into its EIR. Permitting for gen-tie and most switchyard work was handled by PG&E advice Letter exemption under GO 131D. | San Luis Obispo County | Permitting for network delivery upgrades will be handled by a PG&E Advice Letter exemption under GO 131D. | Yes, generator cannot interconnect before completion of delivery upgrades. | Critical path item is the Midway-Carrizo Reconductoring Project and permitting of a revised switchyard location. | DRC2008-00097 | N/A | 1/13/2009 supplement 7/20/09 | 4,365 total (for both HPRII and HPRIII), 1,966 PV | 7.864 | No | No | San Luis Obispo | CA
High Plains Ranch III (Sunpower) | PG0824 |  | PG&E | 12/31/2011: Planning to apply for both a Treasury grant in lieu of ITC under ARRA § 1603 and a DOE loan guarantee as part of the Financial Institution Partnership Program. | DOE: under review. Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 40 | 89.82 | None identified | CAISO | 239 | CAISO Transition Cluster: Phase 2 transmission studies complete. Proposed Interconnection is PG&E's Morro Bay-Midway 230kV transmission line in PG&E service territory. | Full Capacity | Complete | Complete | Complete | Under negotiation - Expected Q1 2011. | Counterparty incorporated some interconnection facilities into its EIR. Permitting for gen-tie and most switchyard work was handled by PG&E advice Letter exemption under GO 131D. | San Luis Obispo County | Permitting for network delivery upgrades will be handled by a PG&E Advice Letter exemption under GO 131D. | Yes, generator cannot interconnect before completion of delivery upgrades. | Critical path item is the Midway-Carrizo Reconductoring Project and permitting of a revised switchyard location. | DRC2008-00097 | N/A | 1/13/2009 supplement 7/20/09 | 4,365 total (for both HPRII and HPRIII), 1,966 PV | 8 | No | No | San Luis Obispo | CA
Alpine Solar (NRG Solar Alpine LLC) | PG0714 |  | PG&E | 12/31/2011: May apply for a DOE loan guarantee as part of the Financial Institution Partnership Program. | DOE: under review. | CPUC approved | Solar PV - Ground mount | 66 | 74.75 | 2 appeals challenging issuance of the CUP without a full EIR. | CAISO | 297 | CAISO Transition Cluster: Phase 2 transmission studies complete. Proposed Interconnection is the Neenach Substation in SCE service territory. | Full Capacity | Complete | Complete | Complete | Under negotiation - Expected Q1 2011. | Counterparty incorporated interconnection facilities into its AFC application. | CEC | The unit may be able to interconnect on an energy only basis per GCOD. Full deliverability will require completion of CPCN and related network upgrades. | Yes, generator cannot interconnect before completion of delivery upgrades. | The unit may be able to interconnect on an energy only basis per GCOD. Full deliverability will require completion of CPCN and related network upgrades. | CUP - T200900158 | N/A | 2009-12-23 | 600 | 9.0909 | Yes | No | Los Angeles | CA
Agua Caliente (First Solar) | PG0810 |  | PG&E | 12/31/2011: May apply for Treasury grant in lieu of ITC under ARRA § 1603. Also applied for and will receive a DOE loan guarantee under FIPP. NEPA review complete. | DOE: issued conditional loan guarantee. Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 290 | 90.13 | None identified | CAISO | 468 | LGIA executed. Interconnection is the Palo Verde North Gila-Imperial Valley transmission line, owned by Arizona Public Service, SDG&E and IID. | Energy Only | Complete | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its Arizona permitting. | All major Arizona Permits received | No major network deliveries were indicated as a result of the LGIP, except for the 500kV Switchyard, which was permitted as part of the Arizona permitting process. | Yes, but generator has requested "energy only" status, so irrelevant. | Critical path item is the construction of the 500kV switchyard by Arizona Public Service, which begin in Q4 2010. | N/A | N/A | N/A | 3000 | 10.3448 | No | No | Yuma | AZ
AV Solar Ranch 1 (First Solar) | PG0816 |  | PG&E | 12/31/2011: May apply for Treasury grant in lieu of ITC under ARRA § 1603. Also applied for a DOE loan guarantee under FIPP. NEPA review is expected to be complete Q1 2011. | DOE: under review. Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 230 | 85.04 | None identified | CAISO | 412 | LGIA executed. Proposed interconnection to SCE's Whirlwind substation (Segment 4 of Tehachapi Renewable Transmission Project (TRTP)), part of SCE service territory. This is the critical path item. | Full Capacity | Complete | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its EIR. | Los Angeles County | SCE has received a CPCN permit from the CPUC for Segment 4 of TRTP, which will provide sufficient capacity for AV Solar Ranch to become fully deliverable. | Yes, generator cannot interconnect before completion of delivery upgrades. | Critical path item is the construction of TRTP, specifically Segment 4. | CUP - T200900026 | N/A | 2009-03-18 | 2100 | 9.1304 | No | No | Los Angeles | CA
SolarPartners II (BrightSource I ) | PG0614A |  | PG&E | 12/31/2011: Project was approved for a Treasury grant in lieu of ITC under ARRA § 1603. Also received DOE Loan guarantee as part of the Financial Institution Partnership Program | DOE: financing expected Q1 2011. Treasury grant: planning to apply at COD. | CPUC approved | Solar Thermal - Tower | 118 | 64.71 | None identified | CAISO | 162 | LGIA executed. Interconnection is the SCE Eldorado-Ivanpah transmission line in SCE service territory. | Full Capacity | Complete | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its AFC application. | CEC/BLM | SCE has applied for a CPCN for the Eldorado-Ivanpah Transmission Project, which will provide sufficient capacity for the project to become fully deliverable. | Yes, generator cannot interconnect before completion of delivery upgrades. | Critical path item is SCE's Eldorado-Ivanpah Transmission Project (EITP). | 2007-AFC-5 CACA 048668 | ROD approving the project published in the Federal Register on 10/14/2010 | 2007-08-31 | 567.7419 | 4.8114 | Yes | Yes | San Bernardino | CA
SolarPartners VIII (BrightSource II ) | PG0614D |  | PG&E | 12/31/2011: Project was approved for a Treasury grant in lieu of ITC under ARRA § 1603. Also applied for DOE Loan guarantee as part of the Financial Institution Partnership Program | DOE: under review. Treasury grant: planning to apply at COD. | CPUC approved | Solar Thermal - Tower | 130 | 61.43 | None identified | CAISO | 233 | LGIA executed. Interconnecting to the SCE Eldorado-Ivanpah transmission line in SCE service territory. | Full Capacity | Complete | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its AFC application. | CEC/BLM | SCE has applied for a CPCN for the Eldorado-Ivanpah Transmission Project, which will provide sufficient capacity for the project to become fully deliverable. | Yes, generator cannot interconnect before completion of delivery upgrades. | Critical path item is SCE's Eldorado-Ivanpah Transmission Project (EITP). | 2007-AFC-5 CACA 048668 | ROD approving the project published in the Federal Register on 10/14/2010 | 2007-08-31 | 1032.2581 | 7.9404 | Yes | Yes | San Bernardino | CA
Montezuma Wind I (NextEra) | PG0403 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of PTC under ARRA § 1603 | Treasury grant: applied. Facility became achieved COD 1/27/2011. | CPUC approved | Wind | 36.8 | 100 | Project achieved COD 1/27/2011. | CAISO | 22 | LGIA executed. Network upgrades were completed in 12/2009. PG&E service territory. | Full Capacity | Complete | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its EIR. | Solano County | None. Upgrades were completed as part of a PG&E capital project | No | None identified | LUP U-06-06 | N/A | 2006-01-23 | 1458 | 39.6196 | No | No | Solano | CA
Mojave Solar (Abengoa) | PG0717 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of ITC under ARRA § 1603. Also applied for a DOE loan guarantee under FIPP. NEPA review is expected to be complete Q1 2011. | DOE: under review. Treasury grant: planning to apply at COD. | New PPA Pending CPUC approval | Solar Thermal - Trough | 250 | 79.91 | Network upgrades | CAISO | 125 | LGIA executed. Proposed interconnection is the Kramer-Pisgah transmission line part of SCE service territory. | Energy Only until 2018. | Complete | Complete | Complete | Executed | Interconnection facilities will be permitted under an SCE 131D exemption F, plan to file Oct 1 2010. CPUC to use CEC AFC. | CEC/BLM | The unit may be able to interconnect on an energy only basis per GCOD. Need FERC approval of Special Protection System, expected Q2 2011. Full deliverability will require completion of CPCN and related network upgrades. | Yes, generator cannot interconnect before completion of delivery upgrades. | The unit may be able to interconnect on an energy only basis per GCOD. Need FERC approval of Special Protection System, expected Q2 2011. Full deliverability will require completion of CPCN and related network upgrades. | 2009-AFC-5 | N/A | 2009-08-10 | 1,765 | 7.06 | Yes | No | San Bernardino | CA
Avenal Park (Eurus) | PG0941 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of ITC under ARRA § 1603 | Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 6 | 88.82 | None identified | IOU WDAT | 20 | FERC SGIP studies complete. Project is connected to a non-CAISO controlled facility via PG&E WDT process. | Energy Only | Complete | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its EIR. | Kings County | Permitting for network delivery upgrades will be handled by a PG&E Advice Letter exemption under GO 131D. | Yes, but generator has requested "energy only" status, so irrelevant. | None identified | CUP 1002 | N/A | 2010-05-24 | 75 | 12.5 | No | No | Kings | CA
Sun City (Eurus) | PG0942 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of ITC under ARRA § 1603 | Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 20 | 93.55 | None identified | IOU WDAT | 19 | FERC SGIP studies complete. Project is connected to a non-CAISO controlled facility via PG&E WDT process. | Energy Only | Complete | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its EIR. | Kings County | None | Yes, but generator has requested "energy only" status, so irrelevant. | None identified | CUP 0908 | N/A | 2009-11-16 | 180 | 9 | No | No | Kings | CA
Sand Drag (Eurus) | PG0943 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of ITC under ARRA § 1603 | Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 19 | 86.8 | None identified | IOU WDAT | 22 | FERC SGIP studies complete. Project is connected to a non-CAISO controlled facility via PG&E WDT process. | Energy Only | Complete | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its EIR. | Kings County | None | Yes, but generator has requested "energy only" status, so irrelevant. | None identified | CUP 0909 | N/A | 2009-11-16 | 240 | 12.6316 | No | No | Kings | CA
Topaz Solar Farms, LLC (First Solar) | PG0707 |  | PG&E | 9/30/2011: Planning to apply for a DOE loan guarantee as part of the Financial Institution Partnership Program | DOE: under review. Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 550 | 82.86 | Ongoing permitting | CAISO | 166 / 194 / 242 | LGIA executed for first 210 MW and the second 190 MW, which needs to be amended. Phase II studies are complete for the remaining 150 MW and the LGIA is under negotiation. All three are interconnecting into PG&E service territory. | Full Capacity | Complete | Complete | Complete | 210MW - Executed. 190 MW - Executed. 150 MW Expected Q1 2011. | Counterparty incorporated interconnection facilities into its EIR. | San Luis Obispo County | Permitting for network delivery upgrades will be handled by a PG&E Advice Letter exemption under GO 131D. | Yes, generator cannot interconnect before completion of delivery upgrades. | None identified | DRC2008-00009 | N/A | 2008-07-30 | 5,300 | 9.6364 | No | No | San Luis Obispo | CA
Desert Sunlight (First Solar) | PG0821 |  | PG&E | 9/30/2011: Planning to apply for a DOE loan guarantee as part of the Financial Institution Partnership Program | DOE: under review. Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 300 | 82.25 | None identified | CAISO | 146 / 147 | LGIA executed. Interconnection to the proposed Red Bluff Substation in SCE service territory. | Full Capacity | Complete | Complete | Complete | Executed | SCE has filed for a PTC for the interconnection facilities. CPUC to use BLM NEPA for PTC review. | BLM | SCE applied for a CPCN for the Red Bluff substation, which will provide sufficient capacity for the project to become fully deliverable. | Yes, generator cannot interconnect before completion of delivery upgrades. | Critical path item is the construction of the Red Bluff substation. | CACA 48649 | Draft EIS published in the Federal Register on 8/27/2010 | 2006-11-07 | 7040 | 23.4667 | No | Yes | Riverside | CA
Genesis (NextEra) | PG0718 |  | PG&E | 9/30/2011: Planning to apply for a DOE loan guarantee as part of the Financial Institution Partnership Program | DOE: under review. | CPUC approved | Solar Thermal - Trough | 250 | 82.38 | None identified | CAISO | 193 | LGIA executed. Proposed interconnection is SCE's proposed Midpoint (aka Colorado River) substation in SCE territory. | Full Capacity | Complete | Complete | Complete | Executed | SCE 131 D exemption F, plan to file Oct 1 2010. CPUC to use CEC/BLM AFC. | CEC/BLM | SCE applied for a CPCN for the Midpoint substation and associated upgrades, which will provide sufficient capacity for the project to become fully deliverable. | Yes, generator cannot interconnect before completion of delivery upgrades. | Critical path item is the construction of the Midpoint substation. | 2009-AFC-8 CACA 48880 | ROD approving the project published in the Federal Register on 11/04/210 | 2009-08-31 | 4640 | 18.56 | Yes | Yes | Riverside | CA
Solar Reserve (Rice Solar) | PG0912 |  | PG&E | 9/30/2011: Planning to apply for a DOE loan guarantee as part of the Financial Institution Partnership Program | DOE: under review. | CPUC approved | Solar Thermal - Tower w/ storage | 150 | 62.31 | Counterparty withdrew from the CAISO interconnection queue. | CAISO | 431 - Withdrawn | CAISO Transition Cluster: Phase 2 transmission studies complete. Counterparty withdrew from the CAISO interconnection queue. | Full Capacity | Complete | Complete | Complete | Counterparty withdrew from the CAISO interconnection queue. | Counterparty incorporated interconnection facilities into its AFC application. These did not match upgrades reported in the CAISO studies. AFC was voted out in December. | CEC | Counterparty withdrew from the CAISO interconnection queue. | Yes, generator cannot interconnect before completion of delivery upgrades. | Counterparty withdrew from the CAISO interconnection queue. | 2009-AFC-10 | N/A | 2009-10-21 | 1500 | 10 | Yes | No | Riverside | CA
Brodie (Coram California Development) | PG0918 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of PTC under ARRA § 1603 | Treasury grant: planning to apply at COD. | CPUC approved | Wind | 102 | 90.91 |  | CAISO | 79 / 91 | LGIA Executed. Interconnection is to SCE's 230kV WindHub Substation in SCE territory. | Full Capacity | Complete | Complete | Complete | Executed | Project is located in a Kern County Wind Energy Combining District. Per Chapter 19.64 of the Kern County zoning ordinance, such a designation exempts the project and its interconnection facilities from CEQA. | N/A | No major upgrades are expected -- sufficient capacity exists for the project to become deliverable. | Yes, generator cannot interconnect before completion of delivery upgrades. | Critical path item is the completion of the interconnection facilities (gen-tie and project substation). | Project is located in a Kern County Wind Energy Combining District. Per Chapter 19.64 of the Kern County zoning ordinance, such a designation exempts the project from CEQA. | N/A | N/A | 1450 | 14.2157 | No | No | Kern | CA
Coyote Canyon (Terra-Gen Power) | PG0948 |  | PG&E | 12/31/2011: Counterparty may elect to apply for Treasury grant in lieu of ITC under ARRA § 1603, and may elect to apply for a DOE loan guarantee as part of the Financial Institution Partnership Program. | DOE: under review. Treasury grant: planning to apply at COD. | New PPA Pending CPUC approval | Geothermal | 53 | 71.66 | None identified | CAISO | 398 | CAISO Transition Cluster: Phase 2 transmission studies complete. Proposed interconnection is at SCE's Control Substation near Bishop, CA via an existing privately owned 211-mile 230kV gen-tie. Interconnection in SCE territory. | Full Capacity | Complete | Complete | Complete | Expected Q3 2011. | Project is located in Churchill County, NV. Gen-tie is existing. | Interconnection facilities will be located in and permitted in Nevada. | Phase 2 studies indicated $179 million in upgrades for all four Terra-Gen projects but this is being negotiated. | Yes, generator cannot interconnect before completion of delivery upgrades. | None identified | DOI-BLM-NV-C010-2010-0010-EA | Under Review - Expected Q1 2011 | 2010-03-10 | 7681 | 144.9245 | No | Yes | Churchill | NV
Alpaugh Solar Facility (Samsung Project Solutions / ENCO) | PG0828 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of ITC under ARRA § 1603. | Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 50 | 85.9091 | None identified | CAISO | 304 | CAISO Transition Cluster: Phase 2 transmission studies complete. Proposed interconnection is the Smyrna-Alpaugh 115 kV Line in PG&E service territory | Full Capacity | Complete | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its EIR. | Tulare County | Permitting for network delivery upgrades will be handled by a PG&E Advice Letter exemption under GO 131D. | Yes, generator cannot interconnect before completion of delivery upgrades. | None identified | N/A | N/A | 2010-04-01 | 400 | 8 | No | No | Tulare | CA
Alpaugh North (Samsung Project Solutions / ENCO) | PG0828 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of ITC under ARRA § 1603. | Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 20 | 91.3636 | None identified | CAISO | 473 | CAISO SGIP studies complete. SGIA executed. Proposed interconnection is the Smyrna-Alpaugh 115 kV Line in PG&E service territory. CPUC is requiring deliverability assessment as a condition for approval. | Full Capacity | Waived | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its EIR. | Tulare County | Permitting for network delivery upgrades will be handled by a PG&E Advice Letter exemption under GO 131D. | Yes, but generator has requested "energy only" status, so irrelevant. | The facility will be required to undergo a deliverability assessment as part of the revised CAISO GIP Procedures. | N/A | N/A | 2010-04-01 | 160 | 8 | No | No | Tulare | CA
Atwell Island (Samsung Project Solutions / ENCO) | PG0829 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of ITC under ARRA § 1603. | Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 20 | 89.9091 | None identified | CAISO | 340 | CAISO SGIP studies complete. SGIA executed. Proposed interconnection is the Smyrna-Alpaugh 115 kV Line in PG&E service territory. CPUC is requiring deliverability assessment as a condition for approval. | Full Capacity | Waived | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its EIR. | Tulare County | Permitting for network delivery upgrades will be handled by a PG&E Advice Letter exemption under GO 131D. | Yes, but generator has requested "energy only" status, so irrelevant. | The facility will be required to undergo a deliverability assessment as part of the revised CAISO GIP Procedures. | N/A | N/A | 2010-03-24 | 160 | 8 | No | No | Tulare | CA
Corcoran (Samsung Project Solutions / ENCO) | PG0830 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of ITC under ARRA § 1603. | Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 20 | 89.9091 | None identified | CAISO | 478 | CAISO SGIP studies complete. Proposed interconnection is the Smyrna-Alpaugh 115 kV Line in PG&E service territory. CPUC is requiring deliverability assessment as a condition for approval. | Full Capacity | Waived | Complete | Complete | Expected Q1 2011. | Counterparty incorporated interconnection facilities into its EIR. | Kings County | Permitting for network delivery upgrades will be handled by a PG&E Advice Letter exemption under GO 131D. | Yes, but generator has requested "energy only" status, so irrelevant. | The facility will be required to undergo a deliverability assessment as part of the revised CAISO GIP Procedures. | N/A | N/A | 2010-06-08 | 160 | 8 | No | No | Kings | CA
White River (Samsung Project Solutions / ENCO) | PG0831 |  | PG&E | 12/31/2011: Planning to apply for Treasury grant in lieu of ITC under ARRA § 1603. | Treasury grant: planning to apply at COD. | CPUC approved | Solar PV - Ground mount | 20 | 89.9091 | None identified | CAISO | 479 | CAISO SGIP studies complete. SGIA executed. Proposed interconnection is the Smyrna-Alpaugh 115 kV Line in PG&E service territory. CPUC is requiring deliverability assessment as a condition for approval. | Full Capacity | Waived | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its EIR. | Tulare County | Permitting for network delivery upgrades will be handled by a PG&E Advice Letter exemption under GO 131D. | Yes, but generator has requested "energy only" status, so irrelevant. | The facility will be required to undergo a deliverability assessment as part of the revised CAISO GIP Procedures. | N/A | N/A | 2010-04-01 | 160 | 8 | No | No | Tulare | CA
Shiloh III Wind Project (enXco) | PG0949 |  | PG&E | 12/31/2011: Counterparty may apply for both a Treasury grant in lieu of ITC under ARRA § 1603 and a DOE loan guarantee as part of the Financial Institution Partnership Program. | DOE: under review. Treasury grant: planning to apply at COD. | New PPA Pending CPUC approval | Wind | 100 | 92 | None identified | CAISO | 39 | LGIA executed, upgrades complete. Interconnection is to the Bird's Landing Switching Station in PG&E service territory. | Full Capacity | Complete | Complete | Complete | Executed | Counterparty incorporated interconnection facilities into its EIR. | Solano County | Upgrades were completed in 2009. | Yes, generator cannot interconnect before completion of delivery upgrades. | Upgrades were completed in 2009. | N/A | N/A | 2009-06-01 | 4436 | 44 - 74 | No | No | Solano | CA
Mesquite Solar (Sempra) | PG0952 |  | PG&E | 9/30/2011: May apply for a DOE loan guarantee as part of the Financial Institution Partnership Program | No reporting requirements until CPUC approval. | New PPA Pending CPUC approval | Solar PV - Ground mount | 150 | 92.36 | No reporting requirements until CPUC approval | No reporting requirements until CPUC approval | No reporting requirements until CPUC approval | CAISO LGIP Cluster Studies underway. Proposed interconnection is to the Palo Verde-North Gila-Hassayampa 500kV transmission line in Arizona. | No reporting requirements until CPUC approval | Complete | No reporting requirements until CPUC approval | No reporting requirements until CPUC approval | Under negotiation - Expected 2012. | Counterparty incorporated interconnection facilities into its Arizona permitting. | Arizona Corporation Commission | TBD - CAISO studies underway | TBD - CAISO studies underway | TBD - CAISO studies underway | N/A | N/A | N/A | tbd | tbd | No | No | Maricopa | CA
Kiara Biomass (Kiara Solar) | tbd |  | PG&E | 12/31/2011: Planning to apply for a Treasury grant in lieu of ITC under ARRA § 1603. | Treasury grant: planning to apply at COD. | New PPA Pending CPUC approval | Biomass | 5.8 | 87.41 | None identified | IOU WDAT | 90 | FERC SGIP Studies complete. Proposed interconnection is to the Jessup Substation in PG&E Service Territory | Energy Only | Waived | Complete | Complete | Under negotiation - Expected Q1 2011. | TBD | Shasta County | TBD | The facility used the FERC SGIP studies to interconnect and therefore are ineligible under the current CAISO tariff to receive a deliverability assessment. However, the facility may use the revised GIP to receive a deliverability assessment in the future. | Execution of the SGIA and installation of a Direct Trip Transfer Scheme. | N/A - existing facility. Re-start permitted through a Shasta County Authority to Construct | N/A | N/A | 25 | 4.3103 | No | No | Shasta | CA
North Star Solar (NorthLight Power) | PGE0937 |  | PG&E | 12/31/2011: May apply for a Treasury grant in lieu of ITC under ARRA § 1603. | Treasury grant: planning to apply at COD. | New PPA Pending CPUC approval | Solar PV - Ground mount | 60 | 76.93 | None identified | CAISO | 607 | CAISO LGIP Phase I study complete. Proposed interconnection is to the Mendota Substation in PG&E service territory. | Full Capacity | Complete | Complete | Not Started | Expected 2012 | TBD | Fresno County | TBD - CAISO studies underway | TBD - CAISO studies underway | TBD - CAISO studies underway | tbd | N/A | N/A | 640 | 10.6667 | No | No | Fresno | CA
Mt. Poso Cogeneration (Mt. Poso Cogeneration Company, L. P.) | PG0712 |  | PG&E | 12/31/2011: May apply for a Treasury grant in lieu of ITC under ARRA § 1603. | Treasury grant: planning to apply at COD. | CPUC approved | Biomass | 44 | 92.5 | None identified | N/A | N/A | N/A - Project is converting to biomass and is already interconnected. | Full Capacity | Complete | Complete | Complete | Executed | N/A - Project is converting to biomass and is already interconnected. | N/A | N/A | No | N/A | N/A | N/A | N/A | 5 | 0.11364 | No | No | Kern | CA
Validation Queries - Do Not Delete
| Technology |  |  |  | RPS PPA Status - CPUC
| Geothermal |  |  |  | CPUC approved
| Solar PV - Ground mount |  |  |  | New PPA Pending CPUC approval
| Solar PV - Roof top |  |  |  | PPA Amendments Pending CPUC approval
| Solar Thermal - Stirling |  |  |  | Executed - no "approval" req'd (e.g., feed-in tariff)
| Solar Thermal - Trough |  |  |  | Under Negotiation
| Solar Thermal - Trough w/ storage |  |  |  | Terminated after execution
| Solar Thermal - Tower |  |  |  | Withdrawn per utility request
| Solar Thermal - Tower w/ storage |  |  |  | Upgrades required for "fully deliverable" status?
| Wind |  |  |  | No
| Biodiesel |  |  |  | Yes, but generator has requested "energy only" status, so irrelevant.
| Biomass |  |  |  | Yes, but generator expects to be allowed a temporary early interconnection while awaiting completion of delivery upgrades.
| Conduit Hydro |  |  |  | Yes, generator cannot interconnect before completion of delivery upgrades.
Digester Gas
Fuel Cells
Landfill Gas
Muni Solid Waste
Ocean/Tidal
Small Hydro
Note on B7: Source: CPUC Project Database
Note on C7: Source: REAT list
Note on K7: Source: IOUs. Note: Information should correspond with or provide updates to the most recently filed RPS Project Development Status Report
Note on S7: Include expected date.
Note on X7: Source: IOUs Note: Information should correspond with or provide updates to the most recently filed RPS Project Development Status Report
Note on Y7: CPUC: Provide link to public docket if available.

## Transmission Projects
Confidential: for internal CPUC use
Participating Transmission Owner | Transmission Project | Capacity of Network Upgrades or Substation | General Location(s) | RPS Project(s) interconnecting with transmission project | Description of permitting, approval and construction process & milestones | Status of Transmission Project | Estimated Date for Project Completion | Available capacity without transmission project (MW) | Additional Information
PG&E | Morro Bay-Midway 230 kV Reconductoring | 1714 Amps (683 MVA) | San Luis Obispo | High Plains Ranch II and High Plains Ranch III (Sunpower); Topaz Solar Farms, LLC (First Solar) | Notice of Construction | Permitting | 2012-10-01 | 825 Amps (329 MVA) | Transmission permitting can be streamlined by leveraging generation projects’ EIR. Final EIR expected Q1 2011.