## Draft Schedule
Month / Date | [6 empty] | Key Milestones / Actions
Jan
S | M | T | W | Th | F | Sa
13 | 14 | 15 | 16 | 17 | 18 | 19 | 1/17: Planning Meeting-- review schedule plan
20 | 21 | 22 | 23 | 24 | 25 | 26 | 1/25: Mail invitation to Chairman Hersman from President Peevey
27 | 28 | 29 | 30 | 31 |  |  | 1/31: Team kickoff meeting including CPUC, PG&E, Sempra, SoWest Gas
Feb
S | M | T | W | Th | F | Sa
[5 empty] | 1 | 2 | Select venue location, sign contract and make deposit
3 | 4 | 5 | 6 | 7 | 8 | 9 | 2/8: Team conference call to discus and recommend agenda
10 | 11 | 12 | 13 | 14 | 15 | 16 | 2/15: Invite other key speakers/presenters
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 |  |  | 2/28 confirm agenda, speakers, final logistics
Mar
S | M | T | W | Th | F | Sa
[5 empty] | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9 | 3/4: Mail invitations to participants with agenda
10 | 11 | 12 | 13 | 14 | 15 | 16
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 | 29 | 30 | 3/29: Receive RSVPs confirming attendance
31
Apr
S | M | T | W | Th | F | Sa
| 1 | 2 | 3 | 4 | 5 | 6 | 4/1-2: Follow-up calls to non-respondents
7 | 8 | 9 | 10 | 11 | 12 | 13 | 4/10: Send Final Agenda, Logistics to all attendees
14 | 15 | 16 | 17 | 18 | 19 | 20
21 | 22 | 23 | 24 | 25 | 26 | 27
28 | 29 | 30
May
S | M | T | W | Th | F | Sa
|  |  | 1 | 2 | 3 | 4
5 | 6 | 7 | 8 | 9 | 10 | 11 | 5/7 1:00 -5:00 session; Chairman Hersman
6:00 social hour
7:00 dinner
5/8 8:00 - 12:00 session