## Sheet1
PG&E's Efforts Related to CPUC's Risk Assessment Unit's (RAU) list of 17 Potential Hazards that Impact Public Safety Information as of August 1, 2013 Concerning Transmission and Distribution
Issue in RAU | Operations Affected | Issues that should be addressed per RAU | Action Taken/Program Name | Document Referencing Action Taken
1. Susceptibility of older plastic pipe to premature brittle-like cracking | Distribution | “Aldyl-A” – a type of polyethylene plastic pipe now in use manufactured in the 1970s – is susceptible to premature brittle-like cracking. Other types of plastic lines manufactured prior to the mid-1980s are also susceptible to the same condition, particularly those developed by certain manufacturers and/or using certain resins. PHMSA has issued advisories to gas system operators regarding the use of these plastic pipes, but responses vary. The hazard associated with these plastic pipes will be examined by the CPUC’s Gas Safety and Reliability Branch (GSRB) through its audit review of the operators’ Distribution Integrity Management Plans. The RAU is now are preparing data requests to all gas utilities listed on the Service List of the OIR on the use of these types of plastic pipes, as well as steel pipe with certain weld seams. The RAU will report findings once the data requests are analyzed. | PG&E is analyzing and replacing Aldyl-A plastic pipelines throughout the system. PG&E replaced 23 miles of Aldyl-A in 2012, has identified 50 miles for replacement in 2013, and identified 100 miles for replacement in 2014. PG&E updated the GIS mapping system with information on more than 5,500 miles of Aldyl-A pipeline, including detailed pipeline and service attribute information. PG&E also increased the company’s ability to identify, evaluate, and rank Aldyl-A issues by working with a third-party expert to update its risk algorithm. PG&E has implemented the first iteration of the risk algorithm and has completed the second version of the risk algorithm. PG&E has been tracking tee caps as a source of leaks for more than a decade, and leak counts since 2000 show that tee caps represent a significant portion of leaks on plastic pipe. PG&E identified tee caps as a threat to its system during the leak cluster analysis in 2011, thereby requiring a separate mitigation effort as part of DIMP. This analysis was used to drive Aldyl-A replacement work through 2013. PG&E will begin its pilot for the plastic tee cap repair program in 2014.
2. Grandfathering provisions in 49 CFR Part 192 | CPUC | Recent CPUC action removed the hydrostatic test requirement exemption to establish Maximum Allowable Operating Pressure (MAOP) on pre-1970 transmission pipelines, but other exceptions and exemptions related to construction vintage in Part 192 are unaffected. As examples, Sections 192.455 and 192.457 do not require pipe coating or cathodic protection on underground steel pipelines installed before August 1, 1971. | As regulations regarding exemptions for pre-1970 pipe have changed, PG&E has complied with these changes, and the company has gone beyond the requirements in some cases. For instance, PG&E cathodically protects all of its transmission pipelines, including lines installed prior to August 1, 1971.
3. Excavation damage by third parties (dig-ins) | Transmission and Distribution | Dig-ins remain the primary cause of pipeline incidents. Dig-ins can be caused by improper marking/locating of underground pipelines by gas operators, but more commonly it is caused by third-parties operating powered excavation equipment too close to underground pipelines or ignoring the legal requirement to notify the one-call centers (811) to request the utilities to mark and locate the facilities before commencing with excavation activities. This hazard can also be considered as a jurisdictional concern since the CPUC lacks authority to fine third-parties who violate the One-call law and damage gas pipelines. This regulatory gap is, in part, currently being addressed by Assembly Bill 1514, sponsored by the CPUC, and R.11-02-019. | PG&E has numerous on-going efforts to prevent and mitigate dig-in damage by third parties, including: -A Public Awareness Plan, which targets awareness, damage prevention, and emergency response readiness. As an example, PG&E has mailed 3,800 brochures to communicate with farmers to educate them about 811/Call Before You Dig, and to promote the awareness and purpose of pipeline markers. Also, PG&E sends out a communication every other year to notify customers of their proximity to a natural gas transmission pipeline. A customer will recieve a letter if they are located along a transmission Right of Way, or if they are located within 660 feet, or within the potential impact radius (PIR), whichever is greater, from the centerline of pipeline. -A Damage Prevention Program, which comprises Public Awareness, Locate and Mark, Dig-In Mitigation, Pipeline Patrol, and Pipeline Marker components. PG&E is establishing a process that identifies contractors who have hit our underground assets on multiple occasions. A review of the information gathered determines the course of action taken. Where appropriate we meet face-to-face to develop partnerships committed to safety, and sometimes we seek other means of enforcement, such as formal complaints to the Contractors State Licensing Board, or complaints to Cal/OSHA. - PG&E plans to conduct a pilot program in the field using vibration monitor sensors. The purpose of the vibration monitor sensors is to detect excavation activity near PG&E facilities and put PG&E in a position to prevent dig-ins from companies or individuals who have failed to contact the Underground Service Alert (USA). This technology is a potential addition to the portfolio of safety tools, to be used if and where analysis shows it would provide value to enhance safety. PG&E does not expect this technology to replace other safety technology or programs, such as the USA program or the active on-site monitoring of excavations where warranted, but to augment such technologies and programs. The sensors will be tied into the new Gas Distribution Control Center. -The Pipeline Centerline Survey is intended to install or rectify pipeline markers along the pipeline centerline and PG&E's respective right-of-way. Pipeline right-of-ways that are well-marked indicate the presence of underground pipelines to the public and can help prevent damage from digging. | NTSB Update (5/16/12) - Update for P-11-29 NTSB Update (1/23/13) - Update for P-11-31 Gas Safety Plan
4. Operators unaware of the location and specification of the pipe in the ground | Transmission | Gas operators’ records do not always reflect the location and specification of the pipe in the ground. This issue is partially being addressed by recent CPUC directives requiring gas operators to validate the MAOP and other conditions of their transmission pipelines using verifiable and traceable records. However, the problem remains for many distribution lines. To further enhance pipeline identification, gas system operators also should consider developing a program to identify each segment of their respective transmission lines using Global Positioning System coordinates (longitude and latitude). | PG&E's efforts to improve knowledge of underground pipe location and specifications include: -Pipeline Safety Enhancement Plan (PSEP): the Mariner project under PSEP will substantially enhance and improve the amount and the types of information that PG&E collects and maintains electronically about its pipeline system; the business processes for collecting, validating and retaining pipeline data; the traceability of materials used in the construction and maintenance of PG&E’s natural gas transmission pipelines; and PG&E’s ability to assess and mitigate potential public safety risks. -Pipeline Centerline Survey (GPS Quality Data for Transmission Lines): PG&E is conducting a "centerline" mapping survey of its 6,750-mile gas transmission pipeline system in 2013, using highly precise mapping tools. This data, once collected, will be loaded and stored in PG&E’s central Geographic Information System (GIS) database. -Pathfinder: The Pathfinder data conversion validation project will enhance the safety of our gas system by dramatically improving the accessibility and reliability of our gas distribution (GD) asset information; validate existing data prior to converting to a "single source of truth" for GD asset data; integrate data types to facilitate risk assessments and assist with the tool selection and provide the data attributes identified by the Distribution Integrity Management team; and this improved access to data will enhance PG&E’s ability to assess risks, and identify and prioritize work on the gas system, which will directly lead to improved employee/contractor and public safety. -In addition, PG&E has made efforts to reduce its mapping department work backlog, which decreases the amount of time for work done in the field to be updated in PG&E's records. PG&E has achieved milestones such as: achieving a nine-day average for asset documentation in 2012, reducing the mapping backlog by 93 percent in 2012, increasing the staffing of the mapping organization, training hundreds of employees on a new as-built process, and conducting quality check in the field to ensure necessary documents are entered into the system and scanned appropriately. | NTSB Update (5/16/12) - Update for P-11-29 NTSB Update (1/23/12) - Update for P-11-29 Gas Safety Plan
5. Unmonitored class location change | Transmission and Distribution | Changing land use or development and other pipeline encroachment (class location) impacts a pipe segment’s MAOP determination and its maintenance requirements. This issue is being addressed in I.11-11-009, but only as it applies to Pacific Gas and Electric Company, the respondent in that proceeding. Other gas pipeline operators are not subject to this proceeding. Here, the RAU recommends determining if current regulations are sufficient for all utilities and reviewing existing definitions. | PG&E conducts both periodic and continual reviews for class location changes. PG&E’s procedures require its pipeline facilities to be patrolled regularly. When new construction is identified along a transmission pipeline PG&E evaluates the class location to determine if it is class location comensorite. In addition, an annual system-wide class location study is conducted to review and supplement the existing continuing surveillance and provides additional means, independent of patrolling, to determine whether the population density has changed adjacent to the pipelines, so as to trigger a potential change in class location. This year’s annual system-wide review of transmission pipeline class location designations is scheduled to be completed on October 31, 2013. In addition, PG&E has designated the Senior Director of Asset Knowledge Management as the person with ownership and accountability for keeping class locations current. | Gas Safety Plan Class Location OII filings
6. Aging infrastructure and interacting threats | Transmission and Distribution | Present regulations only require MAOP to be established by a hydrostatic test at the time of installation. Interacting threats affecting pipeline integrity can gradually weaken a line over many years, reducing the safety margin reflected in the MAOP. Such damaging cumulative effects can go undetected. Liquid pipelines are generally subject to 5-year repeat hydrostatic tests. Gas operators could be required to revalidate MAOP in a similar fashion, with repeat hydrostatic tests at determined intervals (e.g., 10, 15, or 20 years). | PG&E has a Transmission Integrity Management Plan in place, which has been updated to address aging infrastructure and interacting threats. In addition to the procedures that already existed for external corrosion, third party damage, design/material (including manufacturing and construction threats), incorrect operations, weather, and outside force and equipment threats, PG&E made the following changes to threat identification procedures: • Improved procedures to create separate and improved procedures for manufacturing and construction threats • Created new procedures for internal corrosion and stress corrosion cracking threats • Created new procedure addressing interacting threats (including cyclic fatigue) PG&E’s Distribution Integrity Management Program (DIMP) is foundational to PG&E’s overall gas distribution system safety, and is designed to enhance safety by identifying and reducing pipeline risks. PG&E is aggressively building its DIMP as part of a broader asset management effort, consistent with federal regulation and PAS 55. PG&E’s DIMP evaluates the risks to PG&E’s gas distribution system and proposes mitigations to address those risks. Risks are identified through subject matter expertise of employees and industry experts, historical performance of the system as indicated by leak history, and the application of various threats to PG&E’s pipeline assets using its risk algorithm. | NTSB Update (1/23/13) - Update for P-11-29 NTSB Update (6/18/13) - Update for P-11-29 Gas Saftey Plan
7. Infrastructure, maintenance, and parts | Transmission and Distribution | This refers to issues such as good work planning, the need for material traceability of spare parts and material to ensure that the correct spare parts are being used, the need for critical equipment redundancy (e.g., pressure safety valves, power supplies, etc.), and the need to ensure that pressure regulators and safety valve set points are correct. | To improve processes related to maintenance and asset management, PG&E is pursuing a best practice asset management certification offered by the British Standards Institute under its Publicly Available Specification 55 (PAS 55). PAS 55 was adopted in the United Kingdom (UK) by the UK’s Office of Gas and Electric Markets (OGEM) to ensure that public utility assets were being managed safely. PAS 55 ensures that the principles of safety, life cycle planning, risk management, cost/benefit, asset knowledge, customer focus and sustainability are actually delivered within the day-to-day activities of capital project design, implementation, operations, maintenance, and retirement/renewal. PG&E’s program will include: the Gas Operations asset base (physical plant and systems); the information needed to safeguard the assets; the people who work on the assets; the investment in the assets; and the intangible relationships associated with the assets. It also will address employees’ and contractor skills, training and performance; standards and procedures; risk management; long term investment planning; and active employee feedback / input and continuous improvement. Certification by Lloyds Register, an independent auditing firm, is targeted for 2014. To maintain certification once it is obtained, PG&E must have annual independent audits performed of its asset management processes, and an independent recertification audit every 3rd year. The Company is committed to meeting the high international standards that PAS 55 requires, and its underlying principles of sustainable safe operating processes and continuous improvement. PG&E is improving its preventive and corrective maintenance process for distribution. Along with the continuous improvement of databases and software, PG&E has advanced the rigor of the non-technical, personnel oriented, workflow processes. This includes a recent revision to its procedures to include how new equipment is added to the system. These new processes will improve the consistency of how a new equipment is added to the asset register and required maintenance plans are established. | Gas Safety Plan
8. Utility resource management and workforce development | Transmission and Distribution | Understaffing, succession planning, and an aging workforce within the utilities also cause concern. Due to hiring practices, some of California’s large gas utilities now have two large groups of employees separated by approximately 10 years in age. As the more mature group retires, a significant experience/knowledge gap will develop, potentially leading to deficiencies in operations. | PG&E is engaged in building a new gas training facility and updating its curriculum. Completion of the new gas training facility is targeted for completion in 2015. The newly developed facilities and updated curriculum will provide employees the skill and qualifications needed to perform their jobs correctly and safely the first time. See exhibit (PG&E-3) Chapter 10 Technical Training and Research and Development for a more extensive discussion related to training and curriculum development for Gas Operations employees. To address the issues of succession planning and a retiring workforce, PG&E has hired more than 300 new employees into all levels of the Gas Operations organization since January 2011, and expect to hire even more through 2014. More than 131 new training classes have been created for gas employees including leak repair, Locate and Mark, and ground patrol. In addition, PG&E is continuing to expand its PowerPathway program, partnering with educational and workforce investment systems, labor, and industry employers, to cultivate and prepare individuals for high demand positions at PG&E and throughout the energy and utility industries | 2014 filed testimony for General Rate Case (PG&E-3)
9. Ineffective or inadequate gas leak identification and response | Transmission and Distribution | Proper leak detection and accurate leak grading are key defensive and protective measures important for ensuring public safety from hazardous gas leaks. Potential public safety risks may exist since Part 192 does not specify leak grading standards. It instead leaves to the discretion of the operator to define leak grades and their corresponding remedial measures. Inaccurate/inconsistent leak grading is also a concern. Enforcement activity in this area in ongoing, but technical change is constant and vigilance is required on refinements. Other potential concerns include operator response to customer “odor in the air” complaints with no access to the property, and complaints during night/weekend hours. The RAU notes that “The Pipeline Safety Act of 2011” (H.R. 2845, Shuster) orders the Secretary of Transportation to analyze the technical limitations of current leak detection systems. A report to the Senate and House transportation committees is due in January 2013. | In an effort to address urgent customer calls in a more timely manner, in 2012, PG&E adopted a new safety standard of responding to calls reporting possible gas leaks classified as immediate response within 60 minutes 99 percent of the time, as well as responding to gas leak reports within 30 minutes 75 percent of the time upon notification. Benchmarking indicated that PG&E’s new goals are consistent with industry best practices. PG&E's goal for 2015 for emergency response is to treat all gas odor calls as immediate response, with a response time goal of 99% within 60 minutes and an average response time of approximately 20 minutes. Approximately 80 new GSRs will be needed to meet this goal. PG&E is also enhancing the SCADA information system to assist in recognizing and pinpointing the location of leaks, including line breaks, by including additional information related to pipeline pressures, valve positions and gas flow rates. In addition to the SCADA tools described above, PG&E is also implementing other improvements, including: improving SCADA display and navigation, and building a new Gas Control Center, which will co-locate the transmission control, disitribution control, gas dispatch, reliability planning, and emergency response groups. Finally, PG&E is reducing the backlog of already discovered leaks, and setting a shorter deadline to repair leaks, once they are discovered. PG&E repaired 5,295 Grade 2 leaks thus far in 2013 and is forecasting an additional 9,876 grade 2 leak repairs for the remainder of the year. PG&E accelerated repairs of Grade 2 leaks and will go beyond regulatory requirements by repairing, instead of rechecking, above-ground Grade 3 leaks on the distribution system that are due for recheck in 2013. PG&E continues to repair trace leaks at the customer’s gas meter set assembly even though they are non-gradable, very minor, and are not required to be repaired by regulation. In addition, PG&E repaired 50 percent of meter set leaks in 2012, with all currently known meter set leaks to be mostly repaired by the end of 2013; and going forward in 2014, all newly-identified meter set leaks will be repaired within three months of identification. | Gas Safety Plan NTSB Update (1/23/12) - Update for P-11-26
10. Pipe with mechanical/strength characteristics susceptible to failure | Transmission | Steel pipes manufactured before 1970 that contain low frequency electric resistance welds are susceptible to selective corrosion at the weld seams. Oxyacetylene welds are also susceptible to brittle fracture. The failure hazard associated with these types of pipe likely will remain even after the hydrostatic tests have been performed. | As PG&E has stated in its PSEP filings, PG&E has both a Transmission Pipeline Replacement Program, and a Hydrostatic Test Plan, which will test and replace pipes with, among other charateristics, low-frequency electric resistance welds (LF-ERW). These programs will address issues on pipe with potential manufacturing and other flaws. For instance, in Phase I of the Pipeline Replacement Program, PG&E plans on replacing the following types of pipe in urban areas: pipe manufactured by processes generally thought to be susceptible to produce weld seam anomalies or weld seams with poor fracture toughness, including pre-1970, low-frequency Electric Resistant Weld (ERW), flash welded, Single Submerged Arc Weld (SSAW), furnace butt welded, lap welded, and hammer welded pipe, along with pipelines constructed with welding techniques generally thought to produce low toughness or inferior designed girth welds, such as oxygen-acetylene welds, bell-bell chill ring welds, bell and spigot welds, and pre-1940 arc welds. | PSEP
11. Lack of protection redundancy | Transmission and Distribution | Certain pipeline elements, especially those that lack sufficient protection redundancy, are vulnerable to vandalism and sabotage. Pressure regulation and overpressure protection frequently do not have sufficient redundancy or geographical independence of protection backup. Some cathodic protection systems also are susceptible. | PG&E's increased focus on safety includes a Process Safety initiative. This is a comprehensive, risk-based approach to reduce the chance of low frequency, high consequence incidents from occurring. Process Safety requires understanding hazards and risks, planning and implementing layers of mitigating strategies that help manage risk, and learning from experience. The fundamental benefit of Process Safety is a safer business – for employees and the public. Key activities that PG&E will evaluate for risks include facility design and modification, operational procedures, workforce competence, human factors, emergency arrangements, protective devices, instrumentation and alarms, inspection and maintenance, permit to work, asset records and data quality, and third party activities. An example of applying Process Safety is the Pre Start-up Safety Review (PSSR) implemented by PG&E. A PSSR helps ensure that risks have been identified and addressed; there is agreement on all start-up requirements including training, drawings, spare parts and operating procedures before starting new equipment; and there are alternatives to address problems. | Gas Safety Plan
12. Lines unable to accommodate in-line inspection tools, such as smart pigs. | Transmission | Although new and replacement pipelines are required to be constructed to accommodate in-line inspection (ILI) tools (or “smart pigs”), operators are not required to update older lines to allow passage. This also is a form of grandfathering, as present regulations do not require gas operators to run smart pigs. Regulatory changes are under consideration by PHMSA in a proposed Rulemaking, issued August 2011, that will consider requiring ILI assessment, as well as expanding modification to transmission pipelines to accommodate ILI tools. | PG&E is continuing to look for ways to improve its pipelines to accomodate in-line inspection tools. In 2012, PG&E identified more than 1,600 miles of transmission pipeline to be upgraded to accommodate in-line inspection tools (or “smart pigs”) by the end of 2014. In January 2013, the company also completed analysis of nearly 2,500 additional miles of pipeline for upgrades. PG&E is participating in industry-wide Research and Development (R&D) to accelerate the development of Smart Pigs through PRCI and NYSEARCH, and is also privately funding additional ILI tool improvements. The goal is to develop ILI tools which can better transverse challenging-to-inspect pipelines consisting of multiple diameters, short-radius features (elbows, bends), low pressures and/or low flows.
13. Utility management deficiencies. | Transmission and Distribution | Effective utility management controls and safety culture, and a lack of “safety first” culture can lead to a focus on profits rather than safety. For example, the Independent Review Panel report states, “As a result of our investigation, the Panel concludes the explosion of the pipeline at San Bruno was a consequence of multiple weaknesses in PG&E’s management and oversight of the safety of its gas transmission system.” And, “Spirit of Regulatory Compliance - PG&E appears to target its efforts to comply with pipeline safety regulations. But the goals it sets for management compensation purposes, its investments and its practices do not suggest its focus is on achieving an industry leading pipeline safety and integrity program.” | PG&E has renewed its vow across the company to make “safety first,” and create a culture that places public and employee safety above all other priorities. Simultaneously, there has been a movement at PG&E to concentrate on the basics of providing safe and reliable natural gas and electric service to 15 million northern and central Californians. Since 2010, PG&E has promoted 20 employees and hired 15 external individuals to Director, Sr. Director and Officer Levels to strengthen the management and oversight throughout PG&E. Please refer to PG&E's Gas Safety Plan for an in-depth explanation of PG&E's initiatives focusing on safety. | Gas Safety Plan
14. Remote-controlled and automatic shutoff valves. | Transmission and Distribution | Remote-controlled and automatic shut off valves should be required in High Consequence Areas. This issue is being addressed on several fronts, including the CPUC and the legislature. | PG&E’s Valve Automation Program goes significantly beyond current code requirements and current industry practices. The Program is being implemented in two phases and will install or upgrade a total of 530 valves (210 valves as part of Phase 1 and 330 valves as part of Phase 2) with automated shutdown (ASV) or remote shutdown (RSV) capability on transmission pipeline in Class 3 and Class 4 locations. The transmission automated valve field site installations include new pressure and flow data being transmitted to the SCADA system providing additional information that will be utilized by new SCADA control tools and technologies to provide PG&E’s Control Room operators with better situational awareness of pipeline conditions. Upon completion, PG&E will have real-time knowledge of pipeline pressures at least every 5-8 miles on large diameter pipelines in Class 3 and 4 areas. Since 2010, PG&E has replaced, upgraded or automated a total of 74 valves through PSEP in the gas transmission system (13 valves in 2011, 46 valves in 2012, and 15 valves in 2013 as of 4/21/13. Seventy-five valves in total are planned for 2013. PG&E's newly contructed Gas Control Center (GCC) will be a cutting-edge gas control center that will have gas transmission, distribution and dispatch operators all working side-by-side 24 hours a day, seven days a week. The new GCC with give us timely and accurate information about our gas distribution and transmission pipeline systems; improve visibility and control in the gas distribution system; be a proactive and predictive vantage point; have the ability to more efficiently and effectively operate procedures during normal, abnormal and emergency conditions; and improve asset performance, service reliability and communication with public agencies and improve enviromental performance and reduce potential Notices of Violation by monitoring water and gas releases through the clearance process. | NTSB Update (5/16/12) - Update for P-11-27 PSEP Filing (8/26/11)
15. Customer-owned or operated lines | CPUC | Neither PHMSA nor the CPUC has jurisdiction on most customer-owned or operated service lines. Most of these are small gas piping systems. Examples include motels, shopping centers, university campuses, and industrial complexes. Despite the requirement in Part 192.16 (Customer Notification) that the gas operator must inform customers that the customer/owner is responsible for maintaining these systems, it remains a safety concern as the customers/owners are not required to comply with federal or state gas safety regulations. | The issues addressed in this RAU recommendation appear to targeted customer-owned lines, which are outside of PG&E control.
16. Master-metered systems not in mobile home parks | CPUC | Master-metered systems not in mobilehome parks fall under PHMSA jurisdiction, but are outside CPUC jurisdiction. Examples include shopping centers, strip malls, and large apartment complexes. PHMSA has urged the CPUC to accept oversight responsibility for these systems. | This is a legislative and regulatory recommendation, and does not directly involve PG&E's transmission and distribution operations.
17. Inadequate regulation | CPUC | This issue refers to holes or blind-spots in regulations where new legislation/rules may be necessary. For example, federal regulations and audit scope are too narrow to identify all threats to the pipeline. As examples, the National Transportation Safety Board (NTSB) report identifies numerous shortcomings in various areas. These include PHMSA regulations, inadequate audit scope, and failure to use performance based criteria in audits. Below are examples from the NTSB report: “…the PHMSA integrity management audit protocol does not formally call for a check of the completeness and accuracy of information contained in the operator’s pipeline attribute database.” “…PHMSA regulations do not require an operator to supply missing data or assumed values within any time frame. This allows incomplete or erroneous information to continue in an operator’s records indefinitely, …. PHMSA should require operators to correct data deficiencies within a specific time frame.” “The PHMSA integrity management inspection protocol includes inspection item C.03.c for inspectors to verify that the operator uses a feedback mechanism to ensure that its risk model is subject to continuous validation and improvement. However, the PHMSA inspection protocol placed insufficient emphasis on continuous validation and improvement of risk models.” “… PHMSA should develop an oversight model that allows auditors to more accurately measure the success of a performance-based pipeline integrity management program. …... Such metrics would allow a comparison of current performance against previous performance.” “… PHMSA integrity management inspection protocols are inadequate. Therefore, the NTSB recommends that PHMSA revise its integrity management inspection protocol to (1) incorporate a review of meaningful metrics; (2) require auditors to verify that the operator has a procedure in place for ensuring the completeness and accuracy of underlying information; (3) require auditors to review all integrity management performance measures reported to PHMSA and compare the leak, failure, and incident measures to the operator’s risk model; and (4) require setting performance goals for pipeline operators at each audit and follow up on those goals at subsequent audits.” | This is a legislative and regulatory recommendation, and does not directly involve PG&E's transmission and distribution operations.