## Sheet1
PPP DAILY SNAPSHOT
Engaged | Communications Established with City (only for Program Engagement)
Available | OK to proceed, no work started | [5 empty] | Revised: | 2014-07-09
Active | Work In-Progress/Local Outreach Team and RLT-DLT Briefed
On-Hold | No Work Until Further Notice
None | No Projects/Data Not Available
Completed | Completed
| Program Engagement |  | City Tree MOU | Construction (P1 & P2) | Vegetation |  | Protected Trees
CITY | Gov Rel | Land |  | Private Property | Private Property | Franchise | Private Property | Franchise
Airport (CDP) | Active | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Alamo | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Antioch | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Atwater | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Avenal | Engaged | Engaged |  | None | Available | On-Hold | On-Hold | On-Hold
Bakersfield City | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Bay Point | Engaged | On-Hold |  | Completed | On-Hold | On-Hold | On-Hold | On-Hold
Bear Valley Springs (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Boron (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Bystrom (CDP) | Active | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Ceres | Active | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Chowchilla | Engaged | Engaged | x | Active | Active | Active | Active | Active
Coalinga | Engaged | Engaged | n/a | none | Active | None | none | none
Concord | Engaged | Engaged(In-Progress Only) |  | Active(In-Progress Only) | On-Hold | On-Hold | On-Hold | On-Hold
Danville | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Davis | None | Engaged(P1 Only) |  | Available | None | None | None | None
Delhi (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Dublin | Engaged | Engaged(Commercial Only) |  | Available(Commercial Only) | On-Hold | On-Hold | On-Hold | On-Hold
Fairfield | None | Engaged(P1 Only) |  | Active | On-Hold | None | On-Hold | None
Firebaugh | Engaged | Engaged | x | Active | Active | None | None | None
Fremont | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Fresno | Engaged | Engaged | x | Active | Active | Active | Active | Active
Fresno County (rural) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Greenacres (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Greenbrae | None | Engaged(P1 Only) |  | Active | None | None | None | None
Gustine | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Hayward | Engaged | Engaged(Commercial Only) |  | Available(Commercial Only) | On-Hold | On-Hold | On-Hold | On-Hold
Hilmar-Irwin CDP | Active | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Hughson | Active | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Kern County (rural) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Kings County (rural) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Lafayette | Engaged | Engaged(P1 Only) |  | Available | On-Hold | On-Hold | On-Hold | On-Hold
Livermore | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Livingston | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Lodi | None | Engaged(P1 Only) |  | Available | Available | Available | Available | Available
Los Banos | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Madera | Engaged | Engaged | x | Active | Active | Active | Active | Active
Madera County (rural) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Martinez | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Mendota | Engaged | Engaged | x | Active | Active | Active | None | None
Menlo Park | None | Engaged(P1 Only) |  | Available | On-Hold | On-Hold | On-Hold | On-Hold
Merced | None | Engaged(P1 Only) |  | Available | None | None | None | None
Merced County (rural) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Modesto City | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Mountain View | Engaged | On-Hold |  | On-Hold | None | None | None | None
Newman | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
North Highlands | None | Engaged(P1 Only) |  | Available | None | None | None | None
Novato | None | Engaged(P1 Only) |  | Available | On-Hold | None | On-Hold | None
Oakland | None | Engaged(P1 Only) |  | Completed(P1) | On-Hold | On-Hold | On-Hold | On-Hold
Oakley | None | Engaged (1-Off) |  | Available | None | None | None | None
Oildale (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Pacheco | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Patterson | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Pittsburg | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Pleasant Hill | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Pleasanton | Engaged | Engaged(Commercial Only) |  | Available(Commercial Only) | On-Hold | On-Hold | On-Hold | On-Hold
Ripon | Engaged | Engaged |  | Active | Active | Active | Active | Active
Riverdale Park (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Rodeo | None | Engaged(P1 Only) |  | Available | None | None | None | None
Rosedale (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Sacramento | None | Engaged(P1 Only) |  | Available | None | None | None | None
Salida (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
San Jouquin City | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
San Jose | None | Engaged(P1 Only) |  | Completed(P1) | None | None | None | None
San Lorenzo | Engaged | On-Hold |  | On-Hold | None | None | None | None
San Ramon | Engaged | Engaged(Commercial Only) |  | Available(Commercial Only) | On-Hold | On-Hold | On-Hold | On-Hold
Santa Cruz | None | Engaged(P1 Only) |  | Completed(P1) | None | None | None | None
Santa Nella (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
South Dos Palos (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Stanislaus County (rural) | Active | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Sunnyvale | Engaged | Engaged |  | Available | Available | On-Hold | Available | On-Hold
Sunol | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Thornton | None | Engaged(P1 Only) |  | Active | None | None | None | None
Tres Pinos | Engaged | Engaged(Base) |  | Active | Active | Active | Active | Active
Turlock | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Union City | Engaged | Engaged(Commercial Only) |  | Available(Commercial Only) | On-Hold | On-Hold | On-Hold | On-Hold
Volta (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Walnut Creek | Engaged | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
West Modesto City (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Westley (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Willits | None | Engaged (Base) |  | Active | Active | None | Active | None
Winton (CDP) | None | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold
Yuba City | Active | On-Hold |  | On-Hold | On-Hold | On-Hold | On-Hold | On-Hold