## Developing Projects
CPUC ID | Project Name | PDSR Site Owner | EIR Lead Agency | BLM Application | Permit Type | Permitting Status | Actual/Expected Permitting Completion Date | Permitting Completion Year
PG1034 | ABEC Bidart-Old River LLC | Unknown | Kern County | N/A | ATC | On Schedule | 2013-07-31 | 2013
PG5103 | Agua Caliente Solar Project | Private | Yuma County | N/A | SUP | Complete | 2009-09-09 | 2009
| Alamo Solar (Alamo Solar) - RAM 2 | Private | San Bernardino County | N/A | CUP | On Schedule | 2014-02-01 | 2014
| Apex Greenworks LLC - RAM 3 | Private | Los Angeles County | N/A | CUP | On Schedule | 2013-07-31 | 2013
PG5084 | AV Solar Ranch One | Private | Los Angeles County | N/A | CUP | Complete | 2011-01-09 | 2011
PG7036 | Blackspring Ridge IA | Private | Alberta Utility Commission | N/A | PTC | Complete | 2011-03-09 | 2011
PG7037 | Blackspring Ridge IB | Private | Alberta Utility Commission | N/A | PTC | Complete | 2011-03-09 | 2011
| Blackwell Solar | Private | Kern County | N/A | CUP | Complete | 2010-11-01 | 2010
PG3012 | Bottle Rock Power (2nd Amended & Restated) | Unknown | Lake County | N/A | CUP | Complete | 2011-04-12 | 2011
| Columbia Solar (Columbia) - RAM 2 | Private | City of Pittsburgh | N/A | TBD | Complete | 2013-06-07 | 2013
PG5115 | Copper Mountain Solar 2 | Private | Boulder City | N/A | PTC | Complete | 2012-02-28 | 2012
PG5088 | Corcoran | Other Ownership Type | Kings County | N/A | CUP | Complete | 2011-11-07 | 2011
| Corcoran Irrigation District Solar PV Project (Corcoran) - RAM 2 | Private | Kings County | N/A | CUP | Complete | 2013-05-06 | 2013
PG5116 | Cuyama Solar Array | Private | Santa Barbara County | N/A | CUP | On Schedule | 2014-01-31 | 2014
PG5089 | Desert Center Solar Farm | BLM | BLM | CACA 48649 | ROD/ROW | Complete | 2011-08-11 | 2011
PG2028 | DTE Stockton | Private | San Joaquin Valley Air Pollution Control District | N/A | Air Permit | Complete | 2011-06-10 | 2011
| Foothill Farmington 2MW PV Project (2) (2012 PV RFO - 1) | County and Private | San Joaquin county | n/a | CUP | Potential for Delay | 2013-09-30 | 2013
| GASNA 27P (GASNA 27P) - RAM 2 | Private | Solano County | N/A | CUP | On Schedule | 2014-04-01 | 2014
| GASNA 31P, LLC (Twisselman 1 Solar) - RAM 3 | TBD | Kern County | N/A | CUP | On Schedule | 2014-04-30 | 2014
PG6000 | Genesis Solar Energy Project | BLM | CEC | CACA 048880 | ROD/ROW | Complete | 2010-11-04 | 2010
PG5121 | Henrietta Solar PV | Private | Kings County | N/A | CUP | Complete | 2012-09-06 | 2012
PG5097 | High Plains Ranch II | Private | San Luis Obispo County | N/A | CUP | Complete | 2011-04-30 | 2011
PG6004 | Ivanpah Unit 1 | BLM | Joint BLM-CEC | CACA 48668 | AFC and ROD/ROW | Complete | 2010-10-07 | 2010
PG6005 | Ivanpah Unit 3 | BLM | Joint BLM-CEC | CACA 48668 | AFC and ROD/ROW | Complete | 2010-10-07 | 2010
PG5127 | Kansas | Private | Kings County | N/A | CUP | Complete | 2012-05-07 | 2012
PG5130 | Lost Hills Solar | Private | Kern County | N/A | CUP | Complete | 2010-10-26 | 2010
| Mammoth G1 (Ormat) - RAM 2 | Unknown | N/A - Existing project | N/A | N/A - Existing project | Complete | N/A - Existing project
PG6013 | Mojave Solar Project | Private | CEC | N/A | AFC | Complete | 2010-10-08 | 2010
PG5131 | North Star Solar 1 | Private | Fresno County | N/A | CUP | Complete | 2012-05-02 | 2012
PG5024 | Orion Solar 1, LLC | Private | Kern County | N/A | CUP | Complete | 2013-04-23 | 2013
PG1046 | Potrero Hills Landfill | Private | Bay Area Air Quality Management District | N/A | Air Permit | Potential for Delay | 2012-04-01 | 2012
| RE Kent South LLC (4) (2012 PV RFO - 1) | Private | Kings County | N/A | CUP | Complete | 2012-08-28 | 2012
| RE Old River One LLC - RAM 3 | Unknown | Kern County | N/A | CUP | Complete | 2012-11-13 | 2012
PG6003 | Rice Solar Energy Amended and Restated | Private | CEC | N/A | AFC | Complete | 2010-12-15 | 2010
| Sand Hill Wind, LLC -RAM 3 | Unknown | N/A - Existing project | N/A | CUP | Complete | N/A - Existing project
| Shafter Solar - RAM 3 | Unknown | City of Shafter | N/A | CUP | Complete | 2011-02-09 | 2011
| SKIC Solar 1 (1) (2012 PV RFO - 1) | Private | Kern County | N/A | CUP | Complete | 2011-08-25 | 2011
PG6007 | Solar Partners XXII (Palen SEGS. BrightSource PPA 6) | BLM | CEC and BLM | CACA #48810 | Joint CEC BLM | On Schedule | 2013-09-30 | 2013
PG6008 | Solar Partners XXIII (Palen, BrightSource PPA 7) | Site Not Yet Identified | CEC | TBD | TBD | On Schedule | 2013-12-31 | 2013
PG2047 | SPI Biomass Portfolio | Private | N/A - Existing project | N/A | N/A - Existing project | Delayed | Unknown
PG5147 | SPS, White River West (SPS) - RAM 2 | Private | Tulare County | N/A | SUP | On Schedule | 2013-08-31 | 2013
PG1049 | Sunshine Landfill | Private | South Coast Air Quality Management District; SEIR | N/A | Air Permit | Complete | 2012-07-17 | 2012
PG5098 | Topaz Solar Farm | Private | San Luis Obispo County | N/A | CUP | Complete | 2011-11-18 | 2011
| West Antelope - RAM 1 | Private | Los Angeles County | N/A | CUP | On Schedule | 2013-09-30 | 2013
| Western Antelope Blue Sky Ranch A (Silverado) - RAM 1 | Private | Los Angeles County | N/A | CUP | On Schedule | 2013-07-31 | 2013
| Western Antelope Dry Ranch Addition LLC - RAM 3 | Private | City of Lancaster | N/A | CUP | On Schedule | 2013-07-31 | 2013
PG5080 | Westlands Solar Farms PV1 | Private | Fresno County | N/A | CUP | Complete | 2011-10-20 | 2011
| Wind Resource II (CalWind) - RAM 2 | Unknown | N/A - Existing project | N/A | N/A - Existing project | Complete | N/A - Existing project