## 2016 Appendix F
CPUC ID | Project Name | EIR Lead Agency | BLM Application | Permit Type | Permitting Status | Actual/Expected Permitting Completion Date
PG5130 | Lost Hills Solar | Kern County | N/A | CUP | Complete | 2010-10-26
PG5116 | Cuyama Solar Array | Santa Barbara County | N/A | CUP | Complete | 2014-09-30
PG5158 | Blackwell Solar | Kern County | N/A | CUP | Complete | 2010-10-26
PG5121 | Henrietta Solar | Kings County | N/A | CUP | Complete | 2012-09-06
PG50021 | CED Lost Hills Solar | Kern County | N/A | CUP | Delayed | 2016-08-03
PG5155 | RE Astoria | Kern County | N/A | CUP | Complete | 2014-12-02
PG5150 | Midway Solar Farm I | Imperial County | N/A | CUP | Complete | 2012-08-21
PG5156 | California Flats Solar Project | Monterey County | N/A | CUP | Complete | 2015-06-12
PG50048 | Maricopa West Solar | Kern County | N/A | CUP | Complete | 2015-04-07
PG50049 | Portal Ridge Solar C Project | City of Lancaster | N/A | CUP | Complete | 2011-02-11
PG50050 | SR Solis Oro Loma Teresina Solar Project A | Fresno County | N/A | CUP | Complete | 2015-08-01
PG50051 | Sunray 20 | San Bernardino County | N/A | CUP | Delayed | 2016-09-01
PG50052 | Avenal Solar Project A | Kings County | N/A | CUP | Complete | 2015-08-01
PG50053 | SR Solis Oro Loma Teresina Solar Project B | Fresno County | N/A | CUP | Complete | 2015-08-01
PG70039 | Altech III | City of Palm Springs/BLM | N/A | CUP/ROD | Potential for Delay | 2016-10-01
PG50054 | Avenal Solar Project B | Kings County | N/A | CUP | Complete | 2015-08-01
PG50059 | CED Corcoran Solar 3 | Kings County | N/A | CUP | Complete | 2015-07-01
PG50060 | Westside Solar | Fresno County | N/A | CUP | Complete | 2015-09-30
PG50061 | Aspiration Solar G | Fresno County | N/A | CUP | On Schedule | 2016-10-01
PG50067 | Bakersfield PV 1 | Kern County | N/A | CUP | Complete | 2015-02-10
PG50068 | Bayshore Solar A | Los Angeles County | N/A | CUP | On Schedule | 2017-03-01
PG50069 | Bayshore Solar B | Los Angeles County | N/A | CUP | On Schedule | 2017-03-01
PG50070 | Bayshore Solar C | Los Angeles County | N/A | CUP | On Schedule | 2017-03-01
PG50071 | San Joaquin 1B | Fresno County | N/A | CUP | Complete | 2016-04-19
PG50072 | San Joaquin 1A | Fresno County | N/A | CUP | Complete | 2016-04-19
PG50073 | Bakersfield Industrial 1 | Kern County | N/A | CUP | On Schedule | 2016-07-31
PG50074 | Delano Land 1 | Kern County | N/A | CUP | On Schedule | 2016-07-31
PG50075 | Manteca Land 1 | San Joaquin County | N/A | CUP | On Schedule | 2016-07-31
PG50076 | Merced 1 | Merced County | N/A | CUP | Complete | 2016-02-01
PG50077 | RE Tranquillity 8 Amarillo | Fresno County | N/A | CUP | On Schedule | 2017-07-01
PG50078 | Java Solar | Kings County | N/A | CUP | On Schedule | 2017-03-31
PG50079 | 54KR 8me LLC | Kern County | N/A | CUP | On Schedule | 2016-08-15
* Data current as of 7/25/16.