## Project Development Status
As of August 15, 2016
Project Status | Project ID | Project Name | Contract Status | Site Control Status | Permit Type | Permit Status | Expected or Actual permitting completion date
In Construction | 1238 | Republic Services of Sonoma | Approved | Land Secured | US EPA Title V Permit, Major Facility Review Permit, Bay Area Air Quality Management District Permit to Operate, CalRecycle Solid Waster Facility Permit, Sonoma County CUP | Complete | 2015-12-18
In Development | 4316 | Walnut Valley Water District | No Approval Needed | Land Secured | NA | Not Applicable | Not Applicable
In Construction | 5218 | Desert Stateline | Approved | Land Secured | FLPMA ROW Grant, CWA, Construction | Complete | Q4 2014
Pre-Construction | 5219 | Mirasol Murrieta 1 | Approved | Rooftop Secured | CUP | TBD | Q3 2016
Pre-Construction | 5220 | Mirasol Pomona 1 | Approved | Rooftop Secured | CUP | TBD | Q3 2016
Pre-Construction | 5222 | SunE (Bell Tustin) | Approved | Land Secured | Bulding Permit, Electrical Permit | TBD | TBD
Pre-Construction | 5223 | SunE (Red Hill) | Approved | Land Secured | Bulding Permit, Electrical Permit | TBD | TBD
Pre-Construction | 5226 | Caliente Springs, LLC | No approval needed | Land Secured | CUP and construction | TBD | Q3 2016
In process | 5245 | RE: Walker Pass | Approved | Land secured | CUP | IN process | 2017-08-31
In process | 5246 | RE: Tranquility 8 | Approved | Land secured | CUP | IN process | 2017-08-31
Pre-Construction | 5251 | Milestone Wildomar, LLC | No Approval Needed | Land Secured | CUP | In-progress | Q1, 2017
In Construction | 5261 | Windhub Solar, LLC | Pending CPUC Approval | Land Secured | CUP | On Schedule | 2018-04-30
In Construction | 5262 | Antelope DSR 3, LLC | Pending CPUC Approval | Land Secured | CUP | On Schedule | 2019-02-05
In Construction | 5284 | Silver State Solar Power, LLC | Approved | Land Secured | BLM ROD/ROW / AFC | Complete | Q4 2014
In Construction | 5405 | SUNRAY SEGS I | Approved | Land Secured | San Bernardino CUP, Building Permit | Alteration of approved CUP Site Plan will require additional county approval. | Q4, 2016
Pre Construction | 5468 | North Lancaster Ranch, LLC (A&R) | Approved | Land Secured | CEQA, CUP | Complete | 2015-09-21
In Development | 5485 | Nicolis, LLC (Weldon Solar) | Approved | Land Secured | CUP, Construction, grading | Complete | 2014-10-22
In Development | 5490 | Tropico, LLC (Great Lakes) | Approved | Land Secured | CUP, Construction, grading | Complete | 2014-10-22
In Construction | 5519 | One Ten Partners, LLC | Approved | Land Secured | TBD | TBD | TBD
In Construction | 5625 | US Topco Energy, Inc. (Soccer Center) | Approved | Land Secured | CUP | Complete | 2015-07-10
Pre-Construction | 5744 | PVNavigator, LLC | Approved | Land Secured | CUP, Construction & Building | On Schedule | 2016-08-31
Pre-Construction | 5747 | AVS Phase 2 | Approved | Land Secured | CUP | On Schedule | 2018-01-01
Pre Construction | 5748 | Lancaster WAD B, LLC | Approved | Land Secured | CUP | Complete | 2014-09-24
Pre Construction | 5762 | Central Antelope Dry Ranch B, LLC | Approved | Land Secured | CUP | Complete | 2014-06-16
In Construction | 5788 | Lancaster Solar 1 | Approved | Land Secured | CUP | Complete | 2014-12-31
In Construction | 5804 | Copper Mountain Solar 4, LLC | Approved | Land Secured | Nevada Utility Environmental Protection Act Order | Complete | 2014-10-29
Pre-Construction | 5805 | 88FT 8ME LLC (Mount Signal II) | Approved | Land Secured | CUP, IID Encroachment Agreement, Construction & Building | Complete | 2015-06-15
Pre-Construction | 5808 | 93LF 8ME LLC (Mount Signal V) | Approved | Land Secured | CUP, IID Encroachment Agreement, Construction & Building | Complete | 2015-06-15
Pre-Construction | 5810 | 41MB 8ME LLC | Approved | Land Secured | CUP, Construction & Building | TBD | TBD
In process | 5811 | RE Tranquillity LLC | Approved | Land secured | CUP | IN process | 2015-07-30
Pre-Construction | 5813 | Tribal Solar, LLC | Approved | Land Secured | UEPA/BLM ROW/SUP/ESA/CHR/404/DCP | On schedule | 2018-07-01
Pre-Construction | 5814 | North Rosamond Solar, LLC | Pending CPUC Approval | Land Secured | CUP | On schedule | Q4 2017
In Construction | 5816 | Panoche Valley Solar, LLC | Approved | Land Secured | CUP | Complete | 2106-06-14
Already built | 5817 | Luz Solar Partners Ltd, III (SEGS III) (f/k/a 5017) | Not yet approved | Land Secured | n/a | Complete | N/A
Already built | 5818 | Luz Solar Partners Ltd, IV (SEGS IV) (f/k/a 5018) | Not yet approved | Land Secured | n/a | Complete | N/A
Already built | 5819 | Luz Solar Partners Ltd, V (SEGS V) (f/k/a 5019) | Not yet approved | Land Secured | n/a | Complete | N/A
Pre Construction | 5822 | Longboat Solar, LLC | Approved | Land Secured | CUP | Complete | 2015-12-29
In Construction | 5823 | Algonquin SKIC 10 Solar, LLC | Approved | Land Secured | CUP | Complete | 2015-12-16
Pre-Construction | 5826 | Portal Ridge Solar B, LLC | Approved | Land Secured | CUP/Building Permit/EWG FERC cert | On schedule | 2016-11-01
In Construction | 5827 | Rio Bravo Solar I, LLC | Approved | Land Secured | Material | Complete | 2016-04-29
In Construction | 5828 | Rio Bravo Solar II, LLC | Approved | Land Secured | Material | Complete | 2016-04-29
In Construction | 5829 | Wildwood Solar II, LLC | Approved | Land Secured | Material | Complete | 2016-04-29
Pre-Construction | 5833 | Jacumba Solar, LLC | Approved | Land Secured | CUP | TBD | Q3 2016
In process | 5834 | RE Garland A, LLC | Approved | Land secured | CUP | Complete | 2016-06-29
In Construction | 5835 | CED Ducor 1, LLC | Approved | Land Secured | CUP | On Schedule | December, 2015
In Construction | 5836 | CED Ducor 2, LLC | Approved | Land Secured | CUP | On Schedule | December, 2015
In Construction | 5837 | CED Ducor 4, LLC | Approved | Land Secured | CUP | On Schedule | December, 2015
In Construction | 5838 | CED Ducor 3, LLC | Approved | Land Secured | CUP | On Schedule | December, 2015
Pre-Construction | 5840 | Joshua Tree Solar Farm, LLC | Approved | Land Secured | CUP | TBD | Q3 2016
In process | 5844 | SunE- Victorville | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In process | 5845 | SunE- Elm Fontana | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In process | 5846 | SunE- Cherry Fontana | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
Pending Termination | 5847 | SunE- Fontana | Pending Termination | Pending Termiantion | TBD | Pending Termination | Pending Termination
In process | 5859 | Boomer Solar 2 | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In process | 5860 | Boomer Solar 6 | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In process | 5861 | Boomer Solar 7 | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In process | 5865 | Boomer Solar 12 | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In process | 5867 | Boomer Solar 15 | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In process | 5869 | Boomer Solar 17 | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In process | 5870 | Boomer Solar 18 | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In process | 5871 | Boomer Solar 22 | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In process | 5872 | SunE- Quarry Corona | Approved | Rooftop Secured | Building, Electrical | In process Seeking extension | end Q2 2016
In Construction | 5874 | Golden Springs Building F | Approved | Land Secured | City, AHJ Building | On Schedule | 2015-10-01
In Construction | 5875 | Golden Springs Building G | Approved | Land Secured | City, AHJ Building | On Schedule | 2015-10-01
In Construction | 5876 | Golden Springs Building L | Approved | Land Secured | City, AHJ Building | On Schedule | 2015-10-01
In Construction | 5877 | Freeway Springs | Approved | Land Secured | City, AHJ Building | On Schedule | 2015-11-01
In Construction | 5878 | Dulles | Approved | Land Secured | City, AHJ Building | On Schedule | 2015-11-01
In Construction | 5880 | Mesquite Solar 2 | Approved | Land Secured | Special Use Permit | Complete | 2015-12-31
Pre-Construction | 5882 | Sun Streams, LLC | Pending CPUC Approval | Land Secured | SUP/CEC | On schedule | Q4 2017
Pre-Construction | 5883 | Willow Springs Solar, LLC | Pending CPUC Approval | Land Secured | CUP | On schedule | 2018-06-01
Pre-Construction | 5884 | Sunshine Valley Solar, LLC | Pending CPUC Approval | Land Secured | Nye County Dev. Agreement/UEPA/US FWSH | On schedule | 2018-12-31
In Construction | 5885 | Blythe Solar II, LLC | Approved | Land Secured | Construction | Complete | Q1 2016
Pre-Construction | 5886 | Valentine Solar, LLC | Pending Approval | Land Secured | CUP | Not Started | 2019-07-04
In process | 5888 | RE Garland, LLC | Approved | Land secured | CUP | Complete | 2016-03-31
Pre-Construction | 5889 | Blythe Solar III, LLC | Approved | Land Secured | Construction | TBD | Q1 2019
Pre-Construction | 6368 | Broadview Energy KW, LLC | Approved | Land Secured | Construction | Complete | Q3 2016
Pre-Construction | 6369 | El Cabo Wind, LLC | Approved | Land Secured | CUP, Construction & Building | On Schedule | Q2 2017
Pre-Construction | 6372 | Tule Wind | Approved | Land Secured | CUP, Construction & Building | On Schedule | Q2 2017
Pre-Construction | 6379 | Broadview Energy JN, LLC | Approved | Land Secured | Construction | Complete | Q3 2016
Pre-Construction | 6380 | Voyager Wind I, LLC | Approved | Land Secured | CUP, Construction & Building | On Schedule | Q3 2017