## Sheet1
Web Development Team
Daily Check-in - Website post go-live
| Date | 2021-07-15
| Time | 9am -
| Location | WebEx
| Meeting Purpose: | Address daily website issues
| Facilitator: | Harsharan Kaeley
Meeting Attendees
| Attendees | Organization/Division |  | Attendees | Organization/Division
| Fred Gomez | ITSD |  | Terrie Prosper | NOO
| Mike Bonner | ITSD |  | Julie HallX | NOO
| Harsharan KaeleyX | ITSD |  | Jill Walker | NOO
| Charles PoeX | ITSD |  | Jaime Elder | NOO
| Calvin LeeX | ITSD
| Harveen GosalX | ITSD |  | X - Indicates Attendee was present
# | Agenda Topic
1 | Address daily upcoming issue
2
3
# | Assigned to | Assigned Date | Completed DT | Action
1 | Harsharan Kaeley | 2021-07-14 |  | Discuss FTP issue with Infrastructure teem. Can ask Calvin for details.
2 | Harsharan Kaeley | 2021-07-14 |  | Ask Symsoft if they configured Sitecore to show sitemap and if not, add it.
3 | Calvin Lee | 2021-07-14 |  | Setup meeting with Michelle cook to demo associating content to multiple entity
4 | Charles Poe | 2021-07-14 |  | Test associating content and components so user only needs to edit 1 and not both
5 | Mike Bonner | 2021-07-14 |  | Will schedule webtraining syncing
6 | Charles Poe | 2021-07-14 |  | Have users with error messages in sitecore create tickets with screenshot example and details. Create Symsoft ticket to review
7 | Harsharan Kaeley | 2021-07-14 |  | Someone needs to be able to backup Charles Poe on Sitecore when Harveen goes on maternity leave
8 | Charles Poe | 2021-07-14 |  | Ask Symsoft about removing an item from draft without publishing it or deleting the version?
9 | Charles Poe | 2021-07-15 |  | Show how to add new version of media
10 | Harsharan Kaeley | 2021-07-15 |  | Ask mike about M&O contract with Symsoft
11 | Harsharan Kaeley | 2021-07-15 |  | Ask Nick if someone from his team should be available for the webtraining sync to prod
12 | Charles Poe | 2021-07-15 |  | Create Sitecore approvers guide for approvers
13 | Harveen Gosal | 2021-07-15 | 2021-07-15 | Add shared document authors and approvers list to shared location (Sharepoint)
14
15
16