## Sheet1
Web Development Team
Daily Check-in - Website post go-live
| Date | 2021-07-20
| Time | 9am -
| Location | WebEx
| Meeting Purpose: | Address daily website issues
| Facilitator: | Harsharan Kaeley
Meeting Attendees
| Attendees | Organization/Division |  | Attendees | Organization/Division
| Fred Gomez | ITSD |  | Terrie Prosper | NOO
| Mike BonnerX | ITSD |  | Julie HallX | NOO
| Harsharan KaeleyX | ITSD |  | Jill WalkerX | NOO
| Charles PoeX | ITSD |  | Jaime Elder | NOO
| Calvin LeeX | ITSD
| Harveen GosalX | ITSD |  | X - Indicates Attendee was present
# | Agenda Topic
1 | Address daily upcoming issue
2
3
# | Assigned to | Assigned Date | Completed DT | Priority | Action | comments
1 | Harsharan Kaeley | 2021-07-14 |  |  | Discuss FTP issue with Infrastructure teem. Can ask Calvin for details.
2 | Harsharan Kaeley | 2021-07-14 |  |  | Ask Symsoft if they configured Sitecore to show sitemap and if not, add it. | Mike talked To Symsoft. There is not built in tool. There are tools in the market place. Mike and Harsharan said they still have to discuss
3 | Charles Poe | 2021-07-14 |  |  | Setup meeting with Michelle cook to demo associating content to multiple entity | add Harveen
4 | Charles Poe | 2021-07-14 |  |  | Test associating content and components so user only needs to edit 1 and not both | we did this in a meeting
5 | Mike Bonner | 2021-07-14 |  |  | Will schedule webtraining syncing
6 | Charles Poe | 2021-07-14 |  |  | Have users with error messages in sitecore create tickets with screenshot example and details. Create Symsoft ticket to review
7 | Harsharan Kaeley | 2021-07-14 |  |  | Someone needs to be able to backup Charles Poe on Sitecore when Harveen goes on maternity leave
8 | Charles Poe | 2021-07-14 |  |  | Ask Symsoft about removing an item from draft without publishing it or deleting the version?
9 | Charles Poe | 2021-07-15 | 2021-07-15 |  | Show how to add new version of media
10 | Harsharan Kaeley | 2021-07-15 |  |  | Ask mike about M&O contract with Symsoft | 5/2022 ENDS
11 | Harsharan Kaeley | 2021-07-15 |  |  | Ask Nick if someone from his team should be available for the webtraining sync to prod
12 | Charles Poe | 2021-07-15 |  |  | Create Sitecore approvers guide for approvers
13 | Harveen Gosal | 2021-07-15 | 2021-07-15 |  | Add shared document authors and approvers list to shared location (Sharepoint)
14 | Harsharan Kaeley | 2021-07-16 |  |  | discuss with management or network team taking restrictions (internal) off of webproda sitecore authoring temporarily when VPN and VDI issues are jhappnening organization wide. This will allow authors to fulfill (legal) obligations of making website changes
15 | Calvin Lee | 2021-07-16 |  |  | Forms how to guide
16 | Calvin Lee | 2021-07-16 | 2021-07-19 |  | Alias how to guide
17 | Charles Poe | 2021-07-16 |  |  | Followup on time zone issue (PCT) INC0021547
18 | Charles Poe | 2021-07-16 |  |  | Open a ticket with Symsoft. We want to review how we can add additional @ tokens to the email messages and/or what @ tokens are supported.
19 | Calvin Lee | 2021-07-16 |  |  | Compile a list of FAQ from webmaster emails
20 | Calvin Lee | 2021-07-16 |  |  | Google web master tools rebranded - developers.google.com/search (go in there and request that they recrawl the website
21 | Mike Bonner | 2021-07-16 |  |  | Version Upgrade discussed in sitecore weekly meeting with Symsoft
22 | Charles Poe | 2021-07-16 |  |  | Send list of errors and warning users have collect to Symsoft for review
23 | Calvin Lee | 2021-07-20 |  |  | Fix issue when form emailing of the checkbox answer
24 | Calvin Lee | 2021-07-20 |  |  | Who has access to create alias and will that change in the future?
25 | Harsharan Kaeley | 2021-07-19 |  |  | The calendar control is custom code Symsoft wrote and just populates with title and teaser | Discussed via email