ADVANCED METERING INFRASTRUCTURE

Action Recommended

It is recommended that the Boards of Directors of PG&E Corporation and Pacific Gas and Electric Company (PG&E) approve expenditures of $1.47 billion over six years for the deployment of Advanced Metering Infrastructure (AMI).  These expenditures will not be made unless and until the California Public Utilities Commission (CPUC) establishes an acceptable cost recovery mechanism for the project and provides any necessary project approvals.

## Reasons for Recommendation

Based on extensive internal analysis and information obtained from vendors, PG&E has determined that installation of AMI on its system would provide significant operational and customer benefits.  Operational cost savings to PG&E are expected to cover 90 percent of the cost of deploying, operating, and maintaining AMI over its expected 20-year life.  The other 10 percent of the cost is expected to be covered through reduced electricity procurement costs due to reduced peak demand by customers on PG&E’s system in response to dynamic (time-varying) critical peak pricing made available by AMI.

This recommendation is the least-cost alternative for delivering automated metering to enable PG&E to offer dynamic electric rates to all residential customers as directed by the CPUC.  In addition, customer service will be improved through fewer estimated meter reads, fewer delayed bills, faster response time to service outages, and more timely access for customers to information regarding energy usage and costs.

Background

In 2002 the CPUC initiated a proceeding to consider the role that dynamic electric rates (among other measures) using advanced metering technology could have in reducing the future electricity demand in California.  In addition, PG&E has explored the use of advanced metering technology as a means of improving customer service, especially in the areas of outage information and restoration, billing, and generally communicating with our customers faster and more cost-effectively.  PG&E plans to file an application with the CPUC in June 2005 requesting approval of the project and ratemaking to fully recover the capital and operating costs of the project.

PG&E conducted a Request for Proposal (RFP) process over the last nine months to evaluate and ultimately select vendor proposals for alternative AMI technologies.  AMI will be deployed to all customer meter locations (except the largest gas customers) over a five-year deployment, subject to receiving from the CPUC approval of the project and an acceptable cost recovery mechanism.  PG&E intends to enter into contracts with project vendors by the end of this summer. The vendor contracts will be subject to appropriate management approval, acceptable contract terms and conditions (including warranties and performance standards), and termination rights in the event of CPUC disapproval of the project or vendor non-performance.

Description of Recommendation

The AMI project consists of retrofitting all electric and gas meters with a transmitting device that will communicate meter read data through a powerline carrier for electric meters and radio frequency communication for gas meters.

The recommendation is for expenditures to purchase and install a transmitting module at each electric and gas meter device, including related systems and communication links, to provide the automated metering.  The following is a summary of these expenditures over the project deployment:

| Project Expenditures (in millions): | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- |
| Capital | $23 | $167 | $264 | $301 | $326 | $178 |
| Expense | $26 | $ 63 | $ 22 | $ 34 | $ 38 | $ 28 |
| Total expenditures | $49 | $230 | $286 | $335 | $364 | $206 |

Financial Impact

The $1.47 billion proposed expenditure consists of $1.259 billion capital and $211 million expense. Operational cost savings to PG&E are expected to cover 90 percent of the cost of deploying, operating, and maintaining the AMI system over its expected 20-year life.  The other 10 percent in savings are expected to be obtained through reduced electricity procurement costs due to reduced peak demand by customers on PG&E’s system in response to dynamic critical peak pricing made available by AMI.

The net result of revenue requirement impacts due to increase in electric and gas distribution investment are:

| Revenue Requirement Impacts (in millions): | 2005 | 2006 | 2007 | 2008 | 2009 | 2015 |
| --- | --- | --- | --- | --- | --- | --- |
| Electric | $24 | $78 | $55 | $66 | $73 | $(10) |
| Gas | $15 | $35 | $29 | $40 | $53 | $23 |

EPS impacts are calculated relative to repurchasing common stock with the incremental equity capital.

The expected incremental results of operations associated with PG&E’s investment in AMI are:

| Earnings Impact: | 2005 | 2006 | 2007 | 2008 | 2009 |
| --- | --- | --- | --- | --- | --- |
| Incremental (in millions) | $0.9 | $6.6 | $18.5 | $33.7 | $49.3 |
| Earnings per share | $0.00 | $0.00 | $0.02 | $0.04 | $0.05 |

Accounting Treatment

The project is comprised of a variety of capital asset purchases with book and regulatory depreciation lives of between 15 and 27 years.  Approximately 75 percent of the project expenditures are for meters and meter modules including capitalized installation labor.  The expected economic life for the AMI meters and modules is between 15 and 20 years; therefore, book depreciation and regulatory recovery periods are expected to be set to 15 years.

Tax Treatment

There is no current specific authority governing the tax treatment of AMI meters or modules.  Therefore, the tax treatment of the AMI meters and modules may be classified as traditional meters for tax purposes with a 20-year recovery period.  Should authority for alternative treatment materialize, PG&E will pursue a shorter tax depreciation life.

Environmental Impact

PG&E has conducted a preliminary analysis of the environmental aspects of AMI and does not believe that the project will have a significant adverse impact on the environment.

Key Issues and Risks

Risk of exceeding estimated project costs:  PG&E has developed key strategies for the AMI project management plan.  These strategies include using vendor contract terms and conditions to leverage risk to vendors for non-performance, using a system integrator with financial accountability for successful implementation, and the management of cost contingencies.  A risk-based cost contingency of $129 million or approximately 10 percent of the project cost is included in the cost estimate to ensure that the risks are taken into account in the cost justification.  In the event the actual costs are higher than the original projections, PG&E may seek additional cost recovery through rates.

Risk of vendor failure to perform:  Only vendors with production-ready products or proven commercial capability were considered for contracts.  Vendors were screened on their prior record of successful delivery of AMI systems to current customers and their ability to deliver in the future. Contract terms have been specifically designed to ensure that the vendors provide appropriate warranties and have a financial stake in the technology performing in accordance with contractual terms and conditions over the 20-year economic life of the AMI system.  All vendors will meet financial and credit standards demonstrating their ability to perform on their contracts.

Risk of metering technology obsolescence or failure:  Vendors were selected based on criteria that included the contractual requirement that any future enhancements to their product must be compatible with the equipment purchased by PG&E.  The equipment selected is expected to meet all of the current and foreseeable needs of the company to realize the expected operational benefits.  PG&E is recommending the purchase of standard production products from vendors, thus reducing any requirements for customization.  In addition, PG&E has assessed alternative technologies that are commercially available or that are reasonably foreseeable to be commercially available in the next few years, and has structured the AMI project to mitigate risks that its chosen AMI technologies and equipment will be technologically obsolete and uneconomic prior to the end of their economic lives.

Risk of billing system disruption:  Implementation of a new information technology system is required to drive the functionality of AMI.  This new system will require a substantial number of interfaces with existing systems.  PG&E will not move forward with AMI until all systems are proven to work without risk of a billing system interruption.

Risk of negative customer response:  PG&E will request a voluntary program for customers to choose dynamic pricing tariffs rather than a program which forces all customers to participate in those rates.  It is expected that other customer service benefits of better information availability, better outage response capabilities, fewer estimated bills, fewer delayed bills, and other customer service improvements will significantly enhance the benefits that AMI provides to customers.

Risk of cost recovery:  The CPUC and state energy policymakers have endorsed the overall concept of implementing AMI.  PG&E does not intend to move forward with AMI project deployment unless and until the CPUC approves the project and provides an acceptable recovery mechanism for the costs of the project.  PG&E plans to incur $49 million of costs ($23 million capital, $26 million expense) in 2005 to move forward with some project pre-deployment activities to get ready for full deployment, but only with appropriate ratemaking mechanisms or cost controls to mitigate any adverse impacts on the 2005 approved capital and expense budgets should formal CPUC approval of the overall project not be received.  For project costs incurred in 2011 and beyond (primarily maintenance costs, depreciation, and return), PG&E expects to recover the revenue requirements net of operational benefits through General Rate Case applications.

Risk of employee opposition:  A labor strategy has been crafted to minimize impacts to the meter reading workforce.  As a result of a full rollout of AMI, approximately 1,000 employees occupying positions related to meter reading will be displaced.  While elimination of these positions does not require union approval, PG&E has informed the union of the project.  We fully intend to abide by our union agreement and provide all displacement and severance rights under the agreement. In addition, we will engage in good faith efforts and work with the union to develop meaningful options for displaced employees beyond those required under the agreement.

The $1.47 billion project cost for which Board approval is requested includes approximately $49 million in pre-deployment costs to be incurred in 2005.  PG&E has requested separate ratemaking approval for the pre-deployment costs.

The $23 million capital portion of the $49 million of 2005 AMI costs is not included in the 2005 overall utility capital expenditure budget reflected in the 2005 Financial Performance Plan presented to the Boards in December 2004.