Confirmation Number:

Program Title:  Statewide Residential Retrofit Home Energy Efficiency Survey

Name (Contact Person):  Jay Luo

Address:	Pacific Gas and Electric Company

Mail Code B9A

P. O. Box 770000

San Francisco, CA   94177

Telephone #:  (415) 973-9203

Email address:  XXL1@pge.com

List of all other programs proposed.

Appliance Recycling

Single Family Energy Efficiency Rebate

Multifamily Energy Efficiency Rebate

Home Energy Efficiency Survey

Education and Training

CA Energy Star® New Homes Program

Standard Performance Contract

Express Efficiency

Upstream HVAC and Motors

Energy Audits

Energy Efficiency Training and Certification for Building Operators

Codes and Standards Advocacy

Emerging Technologies

Savings By Design

Energenius

Schools Resource Program

Pacific Energy Center

Food Service Technology Center

Partnership Proposals

PG&E Local Government Partnership:  Local Government Initiative

PG&E Local Government Partnership:  Bakersfield/Kern Energy Watch Partnership

PG&E Local Government Partnership:  City of Fresno

PG&E Local Government Partnership:  City of Stockton

PG&E Local Government Partnership:  City of West Sacramento

PG&E Local Government Partnership:  East Bay Energy Partnership

PG&E Local Government Partnership:  El Dorado County

PG&E Local Government Partnership:  Silicon Valley Energy Partnership

UC/CSU/IOU Energy Efficiency Partnership

Third Party Innovative Partnerships

PY2004/PY2005

Energy Efficiency Program Proposal

R. 01-08-028

Statewide Residential Retrofit

Home Energy Efficiency Survey

September 2003

Section I.	Program Overview	1

A.	Program Concept	1

B.	Program Rationale	1

C.	Program Objectives	2

Section II.	Program Process	5

A.	Program Implementation	5

B.	Marketing Plan	5

C.	Customer Enrollment	7

D.	Materials	8

E.	Payment of Incentives	8

F.	Staff and Subcontractor Responsibilities	8

G.	Work Plan and Timeline for Program Implementation	12

Section III.	Customer Description	13

A.	Customer Description	13

B.	Customer Eligibility	14

C.	Customer Complaint Resolution	14

D.	Geographic Area	14

Section IV.	Measure and Activity Descriptions	15

A.	Energy Savings Assumptions	15

B.	Deviations in Standard Cost-effectiveness Values	15

C.	Rebate Amounts	15

D.	Activities Description	15

Section V.	Goals	15

Section VI.	Program Evaluation, Measurement and Verification (EM&V)	16

General Approach to Evaluating Program Success	16

Approach to Measurement and Verification of Energy and Peak Demand Savings	16

Approach to Evaluation Program Success	16

Potential EM&V Contractors	17

Section VII.	Qualifications	17

A.	Primary Implementer	17

B.	Subcontractors	19

C.	Resumes or Description of Experience	20

Section VIII.	Budget	22

Section I.	Program Overview

A.	Program Concept

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options: Mail In, On Line and In Home.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have participated less.  All three delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency, and what additional resources and programs are available to help reduce energy use.

B.	Program Rationale

During the 2002 program year, over 52,000 customers completed the Mail In Survey and over 21,000 customers completed the On Line Survey in all four investor-owned utilities (IOU) service areas.  With a high response rate of between 8 percent to 19 percent for the direct mail solicitations, the program continues to be popular with customers who can access information on energy efficiency and conservation in a variety of formats and languages.  The program has sought to achieve equity through translating the survey into multiple languages.  The Mail In survey includes targeted direct mailings in English and Spanish in all IOU service areas; in Chinese in Pacific Gas and Electric Company (PG&E), Southern California Gas Company (SCG), and Southern California Edison Company (SCE) service areas; and in Vietnamese in San Diego Gas and Electric Company (SDG&E) service area.  With the translation of the HEES into two additional Asian languages, which is planned for 2004 –2005, the program will reach even more customers for whom language has been the market barrier preventing their participation.

PG&E has offered the HEES to residential customers for more than 10 years.  As an experienced program administrator, PG&E has accomplished many program goals in the past years.  All accomplishments listed below demonstrate that the HEES program is a successful program and should continue:

Statewide HEES program accomplishments in 2002-2003:

In 2002, the IOUs jointly designed a single statewide consistent English language version of the Mail In survey;

In 2002, each IOU posted the Spanish and one Asian language version of the Mail In survey on their Web sites; and

During the second quarter of 2003, utilities held several statewide conference calls to coordinate program delivery and implemented the new statewide pricing structure for Mail In surveys.  The IOUs also developed a statewide mailing schedule and standard statewide reporting requirements to improve program delivery;

PG&E’s HEES program accomplishments in 2002-2003:

Accomplished the completed survey goals in 2002.  The 2003 goals were accomplished by the third quarter of 2003;

Completed more than 1,700 Mail In Spanish surveys and 1,600 Mail In Chinese surveys in 2003;

Successfully promoted the On Line Spanish interactive survey by providing customers with compact fluorescent lamps that further lower customers’ energy use; and

Accomplished the 2002 and 2003 hard-to-reach goals.

The IOUs will continue to focus on improving the current program by increasing customer participation and accessibility with the inclusion of surveys in two new Asian languages, Vietnamese and Korean in PG&E’s, SoCalGas’, and SCE’s service areas, and Chinese and Korean versions in SDG&E’s service area.

Plans are underway to update the questions and answers on the Mail In survey.  The goal is to modify the existing survey so that it reflects energy efficiency developments.  This new survey will have the original statewide format and design and questions and answers with the following information updated:

New energy efficiency equipment (two speed pool pump, advanced whole house evaporative cooler, whole house fan);

New energy efficiency technologies (TXV-valve, advanced programmable thermostat, LED Lighting);

Energy saving calculation; and

Energy saving recommendations.

C.	Program Objectives

The infrastructure set up for this program makes it possible to achieve the major goal for this program, providing valuable information that helps customers to:

Save energy and money;

Make their homes more comfortable; and

Discover additional resources and programs available to help reduce energy use.

The statewide HEES program is a free program that provides customers with valuable information to assist them with understanding, controlling and reducing energy use in their homes.  The IOUs will continue to expand efforts to include hard-to-reach (HTR) customers who have yet to take advantages of the many IOU programs and energy efficiency services.

IOUs will continue to focus on improving the current program by increasing customer accessibility to the survey through minimizing market barriers to participation, ensuring customer equity, providing innovative approaches to program participation, and by coordinating with other existing programs to maximize program efficiency.

1)	Market Barriers

The HEES program clearly addresses a lack of customer information about energy efficiency benefits by providing three comprehensive no cost energy surveys, which unlike other services or products, require customer participation and ownership for energy usage and behavioral patterns.  Absent the HEES program, customers would be forced to search out information through a variety of vendors and service providers, who may be limited to providing information on one product or service.  Under the HEES program, customers receive objective information on a multitude of energy products, energy services and available rebate programs.  By coordinating with other program implementers to present information and energy saving recommendations that would encourage participation in the incentive programs, the HEES was able to overcome the market barriers of customer lack of knowledge about energy efficiency and lack of customer participation in the rebate programs.

Lack of customer interest and participation have been major market barriers in the HEES program.  To improve survey equity and overcome the market barrier to increase participation, a pencil was added to all the solicitation packages that were sent to customers in 2003.  The pencil enabled customers to complete the Mail In survey as soon as they received it and provided customers options and flexibility about where they could complete the survey.    Not only was this a cost effective solution, but it also helped overcome the market barrier of participation.  In addition, it helped to increase the program response rate and to lower overall printing and mailing costs.

Energy efficiency information should be constantly updated to reflect these changes.  Plans are underway to update the questions and answers on the Mail In survey in 2003.  Not only can customers benefit from the accurate information the HEES program provides, but they will be more likely to implement the energy savings recommendations when the HEES information is refreshed, technologically accurate, and reflects current practices.

2)	Customer Equity

The HEES program addresses customer equity by 1) offering three survey choices, Mail In, On Line, or In Home, thus increasing the likelihood of participation; and 2) providing survey options in different languages, thus making the service available to those customers who typically had less access to energy efficiency information due to a language barrier.  The Mail In Survey is currently available in English and Spanish in all four IOU service areas, in Chinese in PG&E’s, SCE’s, and SoCalGas’s service areas, and in Vietnamese in SDG&E’s service area.  With the translation of the HEES into two additional Asian languages planned in 2004 –2005, the program will reach even more customers for whom language has been the market barrier preventing their participation.  The equity goals for hard-to-reach participants in 2004 and 2005 will be 50 percent of all participants, which will ensure the HEES program continues to achieve equity in its survey offerings by reaching out to target markets throughout its service area.

3)	Innovation

With the introduction of interactive on-line services, the HEES program has kept up with customer trends toward increased access to the Internet.  The On Line Interactive survey, which is available in English and Spanish, satisfies customer demands for more and quicker information and provides IOUs with an easy venue for presenting new ideas, new delivery mechanisms, and updated information on rebates, products and services.  Innovation is key in the HEES ability to offer surveys that meet customers’ needs.  In 2002, Spanish and one Asian language were added to the English only HEES Mail In survey list.  In 2003, the Spanish survey was upgraded from a downloadable pdf file format to an On Line Interactive survey that provides instant survey results to customers.  In 2004 and 2005, the HEES program will again increase the program’s diversity by adding two more Asian languages in order to reach more non-English speaking hard-to-reach customers.  In an innovative approach to market this informational program to potential participants, PG&E will offer the In Home survey to customers in targeted areas in 2004-2005.

4)	Coordination with other programs

The HEES program will continue to work closely with other existing statewide programs to maximize program efficiency.  The program’s current design coordinates cross marketing of other information, service and rebate programs to include statewide marketing and outreach programs.

Because of its comprehensive approach, the HEES program can effectively target customers while communicating and cross-selling other energy efficiency programs and services.  All three surveys will be coordinated with the other residential energy efficiency programs offered by PG&E. Customized messages on energy efficiency programs, rebates, promotional Web page, and links will be added to specific energy savings recommendations in the Mail In and On Line surveys. Once customers complete the surveys, reports back to customers include information on the customers’ home energy use, available energy efficiency products, services and information on rebate programs offered by PG&E. Customers seeking additional information are directed to PG&E’s Web site. The energy savings recommendations motivate customers with a customized message that tells them how to implement the recommendations and what type of assistance the utility provides to help them implement the recommendations.

The HEES program will be coordinating with many programs including but not limited to PG&E’s Energenius® Program, the Appliance Recycling Program and the Multifamily Rebate Program, etc. The Energenius® program educates students, teachers, energy management staff, custodial staff, and parents on energy efficiency and electric and gas safety that helps shape their energy use behavior at home, at school and at work.  Students are encouraged to discuss savings recommendations with their parents after completing the On Line HEES on PG&E Website. Plans are underway to use On Line and/or Mail In HEES and customized energy savings recommendations to educate both students and their parents.  This is an especially effective means of communicating information to non-English speaking parents via bilingual students.

Section II.	Program Process

A.	Program Implementation

The Mail In survey is distributed to customers via direct mail marketing efforts, as handouts through in-home visits and public events, and through customer requests.  Participating customers are given a survey and materials explaining the value of the program.  Once completed, the survey is mailed back to the statewide Mail In survey vendor for processing.  Completed surveys are analyzed against the customer’s actual energy usage, and a report representing actual energy usage in graph form is mailed to the customer.  Reports include information on energy efficiency products and services, rebate programs, and other energy-related information to encourage adoption of energy efficiency measures identified through the energy survey.  On Line survey provides customers easy access via IOUs’ Web sites.  The interactive feature allows customers to obtain immediate results by answering specific questions regarding their home energy use on line.  This On Line home energy analysis only takesa few minutes to complete, and provides an analysis of energy use in their home as well as energy-saving recommendations.  The In Home survey program will provide customers an energy audit by a trained energy auditor. Unlike SCE and SDG&E, PG&E will only offer the In Home survey to targeted areas.

Each IOU may provide different incentives to residential customers who completed the on line HEES in order to increase customers’ response rate to solicitation materials.  In addition, IOUs will increase program visibility and accessibility through coordination of existing rebate programs with marketing partnerships. Details on any pilot marketing promotions will be report in each IOU’s quarterly reports to the Commission.

B.	Marketing Plan

The program will incorporate a variety of marketing approaches to promote its availability and increase outreach.  Because utility service areas and customer segments are unique, marketing efforts may be tailored by each utility to obtain maximum effectiveness and the highest response rate.  Where practical, IOUs will jointly launch marketing efforts, and will explore opportunities to coordinate with community-based-organizations (CBOs) in outreach to traditionally HTR areas.  These CBOs may include churches, community centers, adult schools and senior centers.   Similarly, IOUs will continue to coordinate closely with the Flex Your Power campaign and the statewide marketing agencies as designated by the Commissions.

The following provides an estimate of the types and cost of various marketing efforts that are planned:

Pacific Gas and Electric Company 2004 Marketing Materials

| Marketing Materials | Quantity | Method of Distribution | Estimated Cost of Materials |
| --- | --- | --- | --- |
| Direct Mailings | 360,000 | Direct mail to targeted customers | $160,000 |
| Utility Call Centers | N/A | CSR direct customer to On Line survey | $5,000 |
| Utility Bill inserts | 4.3 million | Promote On Line survey | $50,000 |
| Utility Web site - banners and buttons | Ongoing | Promote On Line survey | $5,000 |
| Local Newspapers (Ethic media) | TBD (To be determine) | Promote non-English On Line and Mail In surveys | $5,000-$40,000 |
| Local Radio | TBD | Promote On Line survey | $20,000-$50,000 |
| Utility newsletters and/or Electronic newsletter | TBD | Promote On Line survey | $2,000-$8,000 |
| Promotional incentives ( i.e. gift cards ) | TBD | Promote On Line survey | $10,000-50,000 |
| Local CBO”s | TBD | Promote non-English On Line and Mail In surveys | $5,000-$40,000 |

Pacific Gas and Electric Company 2005 Marketing Materials

| Marketing Materials | Quantity | Method of Distribution | Estimated Cost of Materials |
| --- | --- | --- | --- |
| Direct Mailings | 360,000 | Direct mail to targeted customers | $160,000 |
| Utility Call Centers | N/A | CSR direct customer to On Line survey | $5,000 |
| Utility Bill inserts | 4.3 million | Promote On Line survey | $40,000 |
| Utility Web site - banners and buttons | Ongoing | Promote On Line survey | $5,000 |
| Local Newspapers (Ethic media) | TBD (To be determine) | Promote non-English On Line and Mail In surveys | $5,000-$40,000 |
| Local Radio | TBD | Promote On Line survey | $20,000-$40,000 |
| Utility newsletters and/or Electronic newsletter | TBD | Promote On Line survey | $2,000-$6,000 |
| Promotional incentives ( i.e. gift cards ) | TBD | Promote On Line survey | $10,000-40,000 |
| Local CBO”s | TBD | Promote non-English On Line and Mail In surveys | $5,000-$40,000 |

C.	Customer Enrollment

Mail In

Participating customers receive a survey either through direct mail, contacting their local utility, or by printing a hardcopy on-line. Customers mail completed surveys to a statewide Mail In survey contractor for processing.  Once received, surveys are analyzed against customer billing data to produce an energy analysis report containing customer-specific results. Reports include 1) an end-use breakdown of electricity, 2) monthly usage trend graph, and 3) a set of recommendations, with corresponding estimated savings that are appropriate for each customer based on their survey responses. Additionally, reports include information on energy efficiency products and services, rebate programs, and other energy-related information to encourage adoption of energy efficiency measures identified through the energy survey.

On Line

On Line survey provides customers easy access via the IOU’s Web sites.  The interactive feature allows customers to obtain immediate results by answering specific questions regarding their home energy use on line.  This On Line home energy analysis only takes a few minutes to complete and provides an analysis of energy use in their homes as well as energy-saving recommendations.  The On Line HEES are available in both the short and extensive version.

In Home Survey

Customers in PG&E, SCE and SDG&E service areas may participate in this component by contacting their local utility.  This approach provides customers, particularly hard-to-reach customers who do not respond to Internet and Mail In survey options, with a more personalized, face-to-face energy survey option.  A specially trained energy auditor inspects the home and can provide the customer with immediate answers to basic questions as well as specific recommendations on how customers can save energy and manage cost based on their homes and lifestyles.

PG&E proposes to develop an In Home energy efficiency survey in 2004 as a pilot program. It is likely that hard-to-reach customers such as non-English speaking customers, multifamily renters and customers who live outside of the nine Bay Area Counties will be targeted in this pilot program. Details and accomplishment of this pilot In Home survey will be reported in the quarterly reports to the Commission.

D.	Materials

Not applicable

E.	Payment of Incentives

Not applicable

F.	Staff and Subcontractor Responsibilities

2004 Utility Staff Responsibilities-Pacific Gas and Electric Company

| Job Title | Utility Staff No. | Responsibilities | Estimate work hours per week |
| --- | --- | --- | --- |
| Manager | 1 | Supervise Team Leads and Program Managers | 4 |
| Team Lead | 1 | Supervise Program Managers and oversee residential energy efficiency programs | 12 |
| Project Manager | 1 | Coordinates and manages all activities for HEES program. | 80 |

2004 Subcontractor-Kema-Xenergy, Statewide direct-mail HEES vendor

| Position | Sub Contractor Staff No. | Responsibilities | Estimate work hours per week |
| --- | --- | --- | --- |
|  |  |  | PG&E | SCE | SoCal Gas | SDG&E |
| Sr. Project Manager | 1 | Coordinates and manages all activities on these programs and acts as liaison between utilities and Kema-XENERGY | 18 | 11 | 5 | 3 |
| Technical Product Specialist | 1 | Oversees and maintains quality and production of analysis and report functions of software and related hardware functions | 18 | 11 | 5 | 3 |
| Quality Control Engineers | 2.5 | Examine analysis output and quality control functions of residential energy consumption software as well as maintenance of measures, formatting of reports | 45 | 27.5 | 12.5 | 7.5 |
| Production Coordinator | 1 | Manages work of 5 production assistants overseeing all processes regarding processing paper surveys, mailing customer reports, filing and maintaining surveys and processing billing data | 16 | 13 | 5 | 2 |
| Data Specialist | 1 | Processes incoming billing data, provides reporting for monthly invoicing and for client requests, assists with problem accounts, maintains internal program record keeping | 11 | 7 | 4 | 2 |
| Production Assistants | 5 | Assist in processing all incoming surveys and mailing all outgoing reports. Assist with 800 line calls, and maintaining processed surveys, fulfilling client/customer requests for materials | 90 | 55 | 25 | 15 |

2004 Subcontractor-Nexus* software, PG&E on line HEES vendor

| Job Title | Sub Contractor Staff No. | Responsibilities | Estimate work hours per week** |
| --- | --- | --- | --- |
| Project Manager | 1 | Coordinates and manages all activities for all projects and acts as liaison between Nexus and the Utility Partner | 10 |
| Sales Manager | 1 | Manages all activities leading up to the signing of a contractual agreement between Nexus and the Utility Partner. Continues to stay involved in regards to contract renewals and selling of additional products and services. | 5 |
| Engineer | 3 | Responsible for software functionality. | 3 |
| Product Manager | 1 | Responsible for new and ongoing software design and providing scope of work for custom software functionality. | 3 |
| Contractor (For translations of products in other languages) | 2 | Vendor #1: Does large-scale translations of our English products into other languages. Vendor #2: Does smaller translation projects and last-minute translations | 3 |
| *Nexus provides variable amounts of hours each month for the implementation and maintenance of the various products that PG&E has purchased. We provide Time and Materials estimates for specific projects, based on the scope of work involved. |
| **Estimated weekly work hours were provided by utility Program Manager |  |

2005 Utility Staff Responsibilities-Pacific Gas and Electric Company

| Job Title | Utility Staff No. | Responsibilities | Estimate work hours per week |
| --- | --- | --- | --- |
| Manager | 1 | Supervise Team Leads and Program Managers | 4 |
| Team Lead | 1 | Supervise Program Managers and oversee residential energy efficiency programs | 12 |
| Project Manager | 1 | Coordinates and manages all activities for HEES program. | 80 |

2005 Subcontractor-Kema-Xenergy, Statewide direct-mail HEES vendor

| Position | Sub Contractor Staff No. | Responsibilities | Estimate work hours per week |
| --- | --- | --- | --- |
|  |  |  | PG&E | SCE | SoCal Gas | SDG&E |
| Sr. Project Manager | 1 | Coordinates and manages all activities on these programs and acts as liaison between utilities and Kema-XENERGY | 18 | 11 | 5 | 3 |
| Technical Product Specialist | 1 | Oversees and maintains quality and production of analysis and report functions of software and related hardware functions | 18 | 11 | 5 | 3 |
| Quality Control Engineers | 2.5 | Examine analysis output and quality control functions of residential energy consumption software as well as maintenance of measures, formatting of reports | 45 | 27.5 | 12.5 | 7.5 |
| Production Coordinator | 1 | Manages work of 5 production assistants overseeing all processes regarding processing paper surveys, mailing customer reports, filing and maintaining surveys and processing billing data | 16 | 13 | 5 | 2 |
| Data Specialist | 1 | Processes incoming billing data, provides reporting for monthly invoicing and for client requests, assists with problem accounts, maintains internal program record keeping | 11 | 7 | 4 | 2 |
| Production Assistants | 5 | Assist in processing all incoming surveys and mailing all outgoing reports. Assist with 800 line calls, maintaining processed surveys, and fulfilling client/customer requests for materials | 90 | 55 | 25 | 15 |

2005 Subcontractor-Nexus* software, PG&E on line HEES vendor

| Job Title | Sub Contractor Staff No. | Responsibilities | Estimate work hours per week** |
| --- | --- | --- | --- |
| Project Manager | 1 | Coordinates and manages all activities for all projects and acts as liaison between Nexus and the Utility Partner | 10 |
| Sales Manager | 1 | Manages all activities leading up to the signing of a contractual agreement between Nexus and the Utility Partner. Continues to stay involved in regards to contract renewals and selling of additional products and services. | 5 |
| Engineer | 3 | Responsible for software functionality. | 3 |
| Product Manager | 1 | Responsible for new and ongoing software design and providing scope of work for custom software functionality. | 3 |
| Contractor (For translations of products in other languages) | 2 | Vendor #1: Does large-scale translations of our English products into other languages. Vendor #2: Does smaller translation projects and last-minute translations | 3 |
| *Nexus provides variable amounts of hours each month for the implementation and maintenance of the various products that PG&E has purchased. We provide Time and Materials estimates for specific projects, based on the scope of work involved. |
| **Estimated weekly work hours were provided by utility Program Manager |  |

G.	Work Plan and Timeline for Program Implementation

2004 Activity Table

| Statewide IOU Activity | Estimated Start Date | Estimated Completion Date |
| --- | --- | --- |
| Program launch (Continue existing program) | January 1, 2004 | December 31, 2004 |
| Update the Mail In survey questions and energy efficiency recommendations report | Second quarter | Fourth quarter |
| Add two Asian language survey | First quarter | Second quarter |
| Utility Specific Activity | Estimated Start Date | Estimated Completion Date |
| Collaborate with CBOs | First quarter | Fourth quarter |
| Offer In Home survey to targeted area or leveraging with other energy efficiency program | First quarter | Fourth quarter |
| Special Promotion for non-English on line survey | Second quarter | Third quarter |

2005 Activity Table

| Statewide IOU Activity | Estimated Start Date | Estimated Completion Date |
| --- | --- | --- |
| Program launch (Continue existing program) | January 1, 2005 | December 31, 2005 |
| Update the Mail In survey questions and energy efficiency recommendations report | Second quarter | Fourth quarter |
| Utility Specific Activity | Estimated Start Date | Estimated Completion Date |
| Collaborate with CBOs | First quarter | Fourth quarter |
| Offer In Home survey to targeted area or leveraging with other energy efficiency program | First quarter | Fourth quarter |
| Special Promotion for non-English on line survey | Second quarter | Third quarter |

Section III.	Customer Description

A.	Customer Description

The program targets residential customers in three distinct market segments:  1) customers with frequent Internet access, at home and work; 2) customers with limited on line access; and 3) hard-to-reach customers with limited or no on line access who prefer a more personalized face to face In Home survey option.

1)	Customers with frequent Internet access, at home and work:

The On Line survey provides customers who frequently access the Internet with an interactive feature easily accessible on utility Web sites, which allows customers to obtain immediate results by answering specific questions regarding their home energy use on line.  This On Line home energy analysis only takes few minutes to complete and provides an analysis of energy use in their home as well as energy-saving recommendations.

2)	Customers with limited on line access:

The written version of the survey is currently available in English and Spanish in all four IOU service areas, in Chinese in PG&E, SoCalGas, and SCE service areas, and in Vietnamese in SDG&E’s service area.  This Mail In survey version allows customers with limited or no on line access the flexibility of an easy-to-complete mail-back format.  Surveys are distributed to customers via direct mail marketing efforts, as handouts through In Home visits and public events, and through customer requests.  Participating customers are given a survey and materials explaining the value of the program. Once completed, the survey is mailed back to the statewide Mail In survey vendor for processing.  Completed surveys are analyzed against the customer’s actual energy usage, and a report representing actual energy usage in graph form is mailed to the customer.  Reports include information on energy efficiency products and services, rebate programs, and other energy-related information to encourage adoption of energy efficiency measures identified through the energy survey. During 2004-2005, each IOU will add two additional Mail In Asian languages to increase program participation within this community.

3)	Hard-to-reach customers with limited or no on line access:

Residential customers residing in SCE and SDG&E service areas may participate in the In Home survey program component by contacting their local utility.  This approach provides customers, particularly hard-to-reach customers who may not respond to Internet and Mail In survey options, with a more personalized, face-to-face energy survey alternative.

PG&E will offer the In Home survey only to targeted area.  When customers with limited or no on-line access request a survey, a Mail In survey will be sent to the customer for completion.

B.	Customer Eligibility

The HEES program On Line and Mail In Survey components are available to residential customers residing in PG&E, SCE, SoCalGas, or SDG&E service areas.  The In Home Survey component is available in SCE and SDG&E service areas, and in limited areas in PG&E’s service area.

C.	Customer Complaint Resolution

PG&E believes that one of the key elements to make the program successful is to be responsive to customer questions, complaints, and resolve program or performance disputes with program participants.  Customer satisfaction has been a priority of the HEES program and PG&E will continue to deliver this program that builds on the success of the growing infrastructure put in place during the last 10 years.  The following resources were allocated to resolve any customer inquiry and complaint:

Mail In survey – Direct mail survey vendor maintains a toll free telephone line to assist customers with any survey questions. Telephone representatives are trained to discuss survey results with customers, provide support for and conduct surveys in Spanish and Chinese, respond to requests for a second survey, and, when necessary, provide referrals to other PG&E programs.

On Line survey – A “Contact Us” button is located on the upper right corner of the screen in the on line survey. By clicking this button, customer can contact PG&E by email with any survey or energy efficiency questions.

Smarter Energy Line – Customers can also call PG&E’s toll free Smarter Energy Line to talk to an energy efficiency advisor on any survey questions. All of the energy efficiency advisors are trained to discuss questions on HEES with customers, provide support for and conduct surveys in multiple languages.

Any customer questions that cannot be answered by the survey vendor or the energy efficiency advisor of Smarter Energy Line, and all customer complaints, are referred to the IOU’s Program Manager.  The IOU Program Manager logs each incident and contacts each customer to answer questions or resolve disputes.  The log is updated to reflect results of the customer contact.  Unresolved disputes are referred to the Manager of Residential Programs for the respective IOU.

D.	Geographic Area

PG&E provides electricity and gas to approximately 13 million people throughout its 70,000-square-mile service area in northern and central California. The service area ranges approximately from Eureka to Bakersfield.  The HEES program will be available throughout the service area.

The two transmission constraints area identified by the California ISO are the City of San Francisco and the southern Fresno district in PG&E service area. Extra marketing will occur as a result of the transmission constraints in these two areas to address customers’ needs. Since there is a significant Hispanic and Asian populations in these two cities, HEES will be offered to targeted area in these two cities in Spanish, Chinese, Vietnamese and Korean to increase customer participation.

Section IV.	Measure and Activity Descriptions

A.	Energy Savings Assumptions

Pacific Gas and Electric Company Specific:

| Number of Audits | Peak kW | Annual kWh | Annual therms |
| --- | --- | --- | --- |
| 43,500 | 1,889.64 kW | 10,440,000 kWh | 896,100 therms |

Although the HEES program is an information only program, the potential energy savings resulting from the actions customers take after receiving an energy survey has been estimated based on the “Impact Evaluation of Pacific Gas Electric Company's 1997 Residential Energy Management Services Programs,” Study ID Number 397, March 1, 1999.

B.	Deviations in Standard Cost-effectiveness Values

Not applicable

C.	Rebate Amounts

Not applicable

D.	Activities Description

Mail In survey-- The Mail In survey is distributed to customers via direct mail marketing efforts, as handouts through In Home visits and public events, and through customer requests.

On Line survey--The interactive On Line survey allows customers to obtain immediate results by answering specific questions regarding their home energy use on line and is available on the IOU’s Web site.

In Home survey-- The In Home survey program will provide customers an on site energy audit by a trained energy auditor.

Section V.	Goals

2004 Program goals

| Utility | Number of Completed Surveys - Direct Mail & Customer Request | Number of Completed On Line Surveys | Number of Completed In Home Audits | Number of Participating Hard to Reach Customers |
| --- | --- | --- | --- | --- |
| PG&E | 29,000 | 13,500* | 1,000 | 14,500 |
| * On Line goal was increased to reflect the additional implementation budget. |

2005 Program goals

| Utility | Number of Completed Surveys - Direct Mail & Customer Request | Number of Completed On Line Surveys | Number of Completed In Home Audits | Number of Participating Hard to Reach Customers |
| --- | --- | --- | --- | --- |
| PG&E | 29,000 | 13,500* | 1,000 | 14,500 |
| * On Line goal was increased to reflect the additional implementation budget. |

Section VI.	Program Evaluation, Measurement and Verification (EM&V)

General Approach to Evaluating Program Success

This EM&V plan will meet the objectives of the Commission as outlined in the Energy Efficiency Policy Manual by evaluating the success of the Statewide Home Energy Efficiency Survey (HEES) Program through multiple EM&V activities.  This is an information program that needs to be assessed using a combination of approaches evaluating the impact of various elements of the program.  Accordingly, this evaluation study entails an assessment of the Mail In, In Home and On Line components of the program by obtaining the necessary customer information needed to evaluate the effectiveness of these surveys.  The information obtained in this evaluation can then be used in conjunction with information gathered from previous evaluations of the HEES Program to provide an assessment of the different options for offering energy efficiency surveys and their impact on various customer groups.  Using such an approach, the EM&V will also be able to provide quantifiable results that will support potential energy impacts from this program, such as quantifying net-to-gross inputs, energy efficiency measure implementation rates, and specific information to inform affects of this information program on adoption rates for other residential programs.

Approach to Measurement and Verification of Energy and Peak Demand Savings

Since this is an information program, the Measurement and Verification approach for Energy and Peak Demand Savings is not required according to guidelines provided by the Policy Manual.  The program accomplishments will be measured in the form of a number of audits completed in the three IOU service territories and will be verified by an independent EM&V consultant.  In addition, data will be gathered and analyzed for potential energy impacts of the program based on a methodology recommended by a previous evaluation study for this program.

Approach to Evaluation Program Success

Other important aspects of evaluating this program that addresses the EM&V objectives of the Commission are as follows:

Market Assessment and Customer Behavior Analyses:  These activities assist with assessing customer awareness, behaviors and practices given their participation in the program.  A survey will be conducted of the general customer population, which may include previous program participants and non-participants, in order to continue assessing awareness and barriers to participation for the HEES program by customers of the three IOU service territories.  The market assessment will involve use of statewide and utility-specific data to assess the program’s impact on customer awareness and knowledge of energy efficiency opportunities in customer homes.

Process Evaluations:  Survey of program participants and nonparticipants conducted as part of the market assessment activities will also help in determining effective means to improve program design, and targeting and tracking of customer participation, including underserved populations.

Potential EM&V Contractors

The contractors listed below can objectively and effectively evaluate program success.  As a group, their work includes impact evaluation, measurement and verification, process evaluation, market assessments, and verification of program accomplishments. These firms have a track record of completing high quality, objective studies of energy efficiency programs either for the California investor-owned utilities or for other entities whose studies we have been able to review. This list does not include all of the qualified evaluators who could objectively evaluate program success.

| ADM Associates | Megdal & Associates |
| --- | --- |
| Aspen Systems Corp. | Opinion Dynamics |
| Energy Market Innovations | Quantec LLC |
| Equipoise Consulting | Quantum Consulting |
| Frontier Associates | Ridge and Associates |
| Global Energy Partners | PA Consulting Group |
| ICF Consulting | Research Into Action |
| Itron (RER) | TecMKT Works |
| KEMA-XENERGY | Vanward Consulting |
| KVDR Consulting | Wirtshafter Associates |

Section VII.	Qualifications

A.	Primary Implementer

PG&E has provided residential and nonresidential customers with energy efficiency programs at the direction of the Commission since 1976.  Early programs provided information to residential customers on energy efficient appliances, home insulation, heating and air conditioning while providing commercial customers detailed, on-site energy analysis (audits).  Programs and services for both markets evolved into information programs coupled with equipment rebate programs, loan programs and incentives for new building construction by the early 1980s.  These programs have grown, contracted or been redirected based on the changing goals of the Commission, the needs of the marketplace and the input from the many community stakeholders in the energy efficiency industry.

Surveys of customers indicate that PG&E has remained the most trusted source for unbiased energy efficiency information, services and programs.  Customers continue to look to PG&E for assistance in managing their energy use and costs.

Teams of PG&E engineers, marketing professionals and customer service specialists have demonstrated significant competencies in a variety of essential areas of program design and deployment, reporting/accountability program measurement, assessment and evaluation.

PG&E has been helping residential customers control their energy costs for over 24 years and will use its knowledge, experience and external relationships to provide maximum value through the program.  The program’s foundation relationships are established with the federal government’s Energy Star( program, the statewide Flex Your Power campaign and California’s other large private and public utility companies.  The IOUs have offered the HEES program for more than 10 years, each year increasing customer participation, outreach and achievement for long-term energy savings.

Program Design

Responsive, timely action characterizes the PG&E team approach to program design.  Commission priorities, changing markets, technologies, and priorities of interested stakeholders require the flexibility to respond to a wide variety of needs within the annual program cycles.  PG&E’s design team has demonstrated its ability to move rapidly and effectively, from the resource acquisition emphasis of the pre-1998 programs to the market transformation focus of the California Board for Energy Efficiency.  PG&E’s program design team also met the challenge of rapidly responding to the 2000 energy crisis by designing programs that not only saved energy but also encouraged customers to change behavior and business practices.

Program Deployment

A solid program infrastructure combined with the participation of key market actors and experienced service providers have ensured PG&E success in program deployment for the last three decades.  Successes are evident year after year by the accomplishment of the goals and milestones set in place through Commission and PG&E agreements.  PG&E’s staff has nurtured relations with the entire spectrum of parties whose joint efforts are necessary both to capture the interest and enthusiasm needed for a new program and to responsibly remove barriers to deployment.

Reporting/Accountability

Responding to the more rigorous reporting and accountability requirements from the Commission over the last 10 years, PG&E has developed increasingly sophisticated procedures and competencies to meet the new levels of precision required in these areas.  PG&E has been able to provide thorough, reliable reporting as the needs and goals of the Commission have changed from the simple semi-annual and annual reports of the 1980s, to the complex reporting and net benefit accountability over the 10 year time period required of the pre-1998 programs.  PG&E reports on programs using both the pre-1998 methodology and the subsequent reporting requirements for monthly, quarterly and annual reports as well as responding to data requests from the Energy Division, administrative law judges of various proceedings and interested parties in proceedings.

Measurement, Assessment and Evaluation

PG&E’s current measurement, assessment and evaluation (MA&E) capabilities are especially suited to meet the requirements of the Commission’s present directives.  The MA&E team members have worked closely with regulatory agencies and other IOUs, as well as other interested stakeholders, in establishing and coordinating the California Measurement Advisory Council (CALMAC) and the earlier California Demand Side Management Measurement Advisory Council (CADMAC).  The MA&E team has participated and/or led many statewide measurement, assessment and evaluation studies as well as studies focused on local programs and issues.

PG&E’s energy efficiency staff has the strength and commitment to provide the Commission with successful programs responsive to both the goals of the Commission and the needs of customers.

B.	Subcontractors

Statewide Mail In Survey vendor:

Kema-Xenergy has been the statewide Mail In survey vendor since 2000.  They are responsible for printing, mailing, and processing all the Mail In surveys in different languages.  Kema-Xenergy is an energy services and consulting company with a 27-year history of providing advanced technical and information-based solutions for the energy marketplace.

Kema-Xenergy

492 Ninth Street, Suite 220

Oakland, CA 94607

PG&E On Line Survey vendor:

Nexus software has been the PG&E On Line Survey vendor since 2002.  They are responsible for hosting, managing, and maintaining all the Nexus on line energy analysis tools in the PG&E Web site.  Nexus is a provider of software applications and expertise to enhance communications between energy companies and their customers.  More than 40 utilities nationwide are working with Nexus to upgrade their on line customer support, contact center systems and processes, and electronic billing systems.

Nexus software

4025 S. McClintock Drive, Suite 202

Tempe, AZ 85282

The utility does not contract with any consultants and/or subcontractors for management of its HEES programs.

- Resumes or Description of Experience

Albert K. Chiu

| Career Summary | Over 3 years energy efficiency experience at PG&E. |
| --- | --- |
| Employment History | 2001 - Present REM Program Manager Design and manage the HEES program. Design marketing materials for the program. Conduct project activities, monitor the budget, and provide research for various projects. Analyze research data using simple and/or multivariate statistical methods. Manage the contract bid process to ensure competitive bids for each project. Communicate with external suppliers/vendors on energy efficiency programs policies and procedures. Assist external suppliers/vendors to complete programs requirements. Manage the multifamily element of the 2000 Residential Contractor Program. Support other programs as needed. 2000 - 2000 REM Program Manager Assistant Assisted Program Managers to perform the above tasks. Supervised summer intern who worked on project. Developed list of swimming pool services contractors in Pacific Gas and Electric Company service area. 1999 - 2001 Smarter Energy Customer Service Representative Certified Energy Auditor for PG&E. Answered phone calls on energy efficiency, electricity safety, PG&E’s programs, and home appliances information. |
| Education | San Jose State University, San Jose, CA, BS Environmental Studies-December 2000 Concentration in Energy with an emphasis on urban planning and Geographic Information Systems (GIS) |
| Associations and Affiliations | Member of PG&E’s Speakers Bureau, made presentations on PG&E’s energy efficiency programs to Chinese speaking public. Member of PG&E’s Asian Employee Association (AEA). Active member in AEA scholarship committee. |

Section VIII.	Budget