Confirmation Number:

Program Title:  Statewide Nonresidential New Construction Savings By Design

Name (Contact Person):  Jay Luo

Address:	Pacific Gas and Electric Company

Mail Code B9A

P.  O.  Box 770000

San Francisco, CA   94177

Telephone #:  (415) 973-9203

Email address:  XXL1@pge.com

List of all other programs proposed.

Appliance Recycling

Single Family Energy Efficiency Rebate

Multifamily Energy Efficiency Rebate

Home Energy Efficiency Survey

Education and Training

CA Energy Star® New Homes Program

Standard Performance Contract

Express Efficiency

Upstream HVAC and Motors

Energy Audits

Energy Efficiency Training and Certification for Building Operators

Codes and Standards Advocacy

Emerging Technologies

Savings By Design

Energenius

Schools Resource Program

Pacific Energy Center

Food Service Technology Center

Partnership Proposals

PG&E Local Government Partnership:  Local Government Initiative

PG&E Local Government Partnership:  Bakersfield/Kern Energy Watch Partnership

PG&E Local Government Partnership:  City of Fresno

PG&E Local Government Partnership:  City of Stockton

PG&E Local Government Partnership:  City of West Sacramento

PG&E Local Government Partnership:  East Bay Energy Partnership

PG&E Local Government Partnership:  El Dorado County

PG&E Local Government Partnership:  Silicon Valley Energy Partnership

UC/CSU/IOU Energy Efficiency Partnership

Third Party Innovative Partnerships

PY2004/PY2005

Energy Efficiency Program Proposal

R. 01-08-028

Statewide Nonresidential

New Construction

Savings By Design

September 2003

Section I.	Program Overview	1

A.	Program Concept	1

B.	Program Rationale	1

C.	Program Objectives	4

Section II.	Program Process	7

A.	Program Implementation	7

B.	Marketing Plan	9

C.	Customer Enrollment	14

D.	Materials	15

E.	Payment of Incentives	15

F.	Staff and Subcontractor Responsibilities	15

G.	Work Plan and Timeline for Program Implementation	17

Section III.	Customer Description	19

A.	Customer Description	19

B.	Customer Eligibility	20

C.	Customer Complaint Resolution	21

D.	Geographic Area	21

Section IV.	Measure and Activity Descriptions	22

A.	Energy Savings Assumptions	22

B.	Deviations in Standard Cost-effectiveness Values	23

C.	Rebate Amounts	25

D.	Activities Description	25

Section V.	Goals	25

Section VI.	Program Evaluation, Measurement and Verification (EM&V)	25

Section VII.	Qualifications	29

A.	Primary Implementer	29

B.	Subcontractors	31

C.	Resumes or Description of Experience	31

Section VIII.	Budget	42

Section I.	Program Overview

A.	Program Concept

Savings By Design (SBD) is an energy efficiency program for the nonresidential new construction industry started by the investor-owned utilities (IOUs) in 1999 to provide statewide consistency, program stability, and savings persistence to the new construction market.  SBD builds on the best elements of successful new construction programs run by the investor owned utilities since the early 1990’s.  The program promotes integrated design and emphasizes early design involvement by offering building owners and their design teams a wide range of services including education, design assistance, and owner incentives as well as design team incentives.

B.	Program Rationale

When a building or process is built correctly from the outset, excess electrical and gas demand never impact the electric and gas transmission and distribution systems, assuring both energy savings and savings persistence.  By providing the technical and financial means to influence the basic design of commercial and industrial projects, SBD assures that these projects are designed and constructed correctly the first time.  Because the program is delivered before a building or process is constructed, energy savings are achieved when they create the greatest benefit and are most cost-effective for the owner.  SBD interventions avoid the missed opportunities that result when energy efficient measures and strategies are not incorporated into a project during the construction phase and the project has to be retrofitted later at higher cost.  The SBD program has consistently met and, in 2004 and 2005, will continue to meet the California Public Utilities Commission’s (Commission) goals and objectives for energy efficiency programs for the new construction market.  SBD delivers cost-effective, verifiable, long-term energy savings and peak demand reduction, with Commission-established Effective Useful Lives (EULs) of between 16 and 20 years (depending on end-use).  The EULs applied to the SBD program far exceed the Commission’s minimum target of three years.

Since 1999 the statewide SBD program has involved thousands of participants and projects and has worked with scores of design teams.  SBD field personnel at all participating utilities have influenced 2471 projects that have enrolled in the program, of these 1544 have received incentives for their energy efficiency improvements and 927 projects are currently pending construction completion.  SBD implementation staff is currently working with owners, architects, and engineers to maximize the energy efficiency of more than 1,258 additional projects for eventual inclusion in the program.  The program’s innovative educational elements and implementation strategies successfully overcome market barriers and failures that inhibit adoption of cost-effective energy efficiency measures while providing lead sources for future project involvement.  Specific barriers addressed include:

Split Incentives - Building and systems design is the purview of engineers and architects who will not be responsible for the energy costs arising from their designs.  By engaging both owners and design teams, SBD provides an information loop for project-specific energy cost information to reach owners.  Furthermore, by providing incentives to design teams, engineers and architects, they are given a financial stake in the projects energy efficiency characteristics.

Performance Uncertainties – Lack of confidence in the cost-effectiveness of increased efficiency, concerns over performance of high efficiency products and design strategies, and routine over-sizing of systems to limit potential liability from design error are common in the nonresidential new construction market.  SBD provides proven intervention strategies such as one-on-one project recommendations and education to all participating market actors to allay these concerns.

Asymmetric Information and Information Search Costs – Manufacturers’ claims may be confusing and are not necessarily reliable.  New design practices require study prior to implementation.  Architects and engineers are the primary source of information on energy and sometimes limit the flow of that information to owners in order to retain control of project parameters and schedules.  To overcome these informational asymmetries, SBD provides considered, balanced, unbiased information and recommendations directly to owners as well as to architects and engineers.

Hassle or Transaction Costs – Costs in time and money associated with an owner or designer identifying efficient practices and technologies - along with the hassle and time to convince the owner or developer to upgrade efficiency features - often precludes energy efficient design and construction, even when such design changes are simple and cost-effective.  SBD incentives and project-specific information motivate owners and design teams to consider and implement energy efficiency improvements.

Opportunism - Manufacturers provide the design community with tools which speed and aid the design process, but they may also subtly manipulate results to favor designs or equipment types specific to that manufacturer – without regard to maximizing efficiency or even the suitability of the equipment for the application.  SBD analysis tools and assistance provide unbiased recommendations based on best practice, overcoming such opportunism.

Service Unavailability – Often, designers offer energy efficiency services to only the most sophisticated clients while energy service companies rarely offer energy efficiency services in the new construction marketplace due to long build-outs for projects and the difficulties in establishing baselines.  To counter this, SBD offers design assistance and analysis for all customers.  The simplified Systems Approach helps smaller and less sophisticated clients quantify, understand, and capture energy savings based on integrated design.

Bounded Rationality –Designers and contractors use commodity-based approaches including standardized design practice, energy rules of thumb, and short cuts - often sacrificing quality for expedience and low first-cost.  SBD provides integrated design assistance, strategies, information, and tools that allow market actors at all levels to accurately evaluate, understand, and size their projects.

Hidden Costs – Inefficient buildings and processes result in not only higher operating costs, but also higher maintenance costs, less comfort, shorter equipment life and less environmental quality.  SBD provides project-specific cost information to decision makers and trains design teams in the use of analysis tools that allow decision makers to understand and evaluate their own costs.

Confusion Regarding Minimum Energy Code – Many industry decision-makers are unaware that building energy codes actually represent the highest allowable energy consumption possible for buildings in California.  Building owners and even design team members often confuse meeting minimum Title 24 energy code requirements with energy efficiency.  SBD tools and analysis demonstrate that the energy code is only a reference point from which to evaluate cost-effective and truly energy efficient designs.

From inception, SBD innovations have produced a program that not only addresses market needs, barriers, and failures, but which has also evolved in response to the changing needs of the California new construction market.  These innovations will continue with the 2004-2005 program.  In addition to ongoing changes to the program to account for the triennial tightening of Title 24 building standards, the program is annually re-evaluated and modified to support and enhance the momentum of emerging technical, operational, and best practice trends in the new construction industry.

SBD innovations allow it to adjust to emerging building trends so that it can stay relevant and cutting-edge, encouraging design teams, building owners and entire industries to be innovative.  The program pursues continuous improvement of its own materials and approaches in order to supply owners and design teams with resources that will support and develop their skills related to energy efficient design.  As a matter of fact, in a national competition during 2002, Savings By Design was awarded first place for its innovative approach in the category of “Achievement in Energy Services Practice” by the Association of Energy Services Professionals (AESP).  Examples of SBD’s innovative approach follow:

In response to a lack of an energy efficiency code for industrial and agricultural customers, SBD has evaluated standard practice in various industries and industrial processes in order to establish baselines for program participation.  To date these include wastewater treatment plants, dairies, clean-rooms, and wineries, as well as motor and compressed air systems.

As an increasing number of design team members become interested in energy modeling, SBD sponsored trainings and expanded incentives for design teams who choose to submit their own project modeling results.

In response to the growing awareness and value associated with green design and the U.  S.  Green Building Council’s Leadership in Energy and Environmental Design (LEED) program as well as the Collaborative for High Performance Schools (CHPS) certification, SBD expanded its marketing strategy to coordinate with these programs, both supporting the energy components for teams pursuing these certifications and directing other design teams participating in SBD toward LEED and CHPS.

As gas supply and prices are expected to experience increasing volatility over the next few years, SBD has responded by increasing its gas incentive for gas saving energy efficiency measures.

In anticipation of a new focus on Time Dependent Valuation (TDV) in the next round of building energy codes, SBD will expand its calculation and incentive methodologies to accommodate and value peak electric kW demand reduction.

Other innovations and program changes that relate to specific objectives and deliverables as delineated in section I.  C.

Finally, it is important to note that program stability is a paramount concern for SBD participants.  Because in-depth energy efficiency analyses leading to substantive design and construction changes involve risk and the possibility of increased costs, programs supporting the new construction industry must provide consistency and must accommodate industry timelines—and those timelines are long.  An expedited new construction project may take three or more years from concept to build-out, while standard new construction timelines run four to seven years, and institutional, hospital, or nonstandard projects can take a decade or more.

C.	Program Objectives

The SBD program seeks to optimize energy efficiency and reduce peak electric and gas demand of nonresidential new construction projects, prepare the market for upcoming building energy code change, and promote the acceptance of energy efficiency within the new construction market by providing tools and resources to standardize energy efficient design processes.  To ensure program equity, SBD will also actively reach out to market actors and customer classes that have had lower program participation, i.e., areas and customer classes designated as hard-to-reach.

In order to optimize the energy efficiency of individual projects, the SBD program influences nonresidential building owners, tenants and design teams to exceed current Title 24 energy efficiency standards (or other established standards for industrial and specialty processes) by 10 percent or more for their new construction or renovation/remodeling projects.  SBD coordinates resources from industry relationships, strategic alliances, and other public purpose programs such as the PG&E Pacific Energy Center (PEC), other energy centers, the Emerging Technologies program and the Food Services Technology Center, a PG&E local program, to accomplish the goals of energy savings, peak demand reduction, and long-term market change.  Over a sustained period of time, these interventions impact market practice and flatten projected procurement demand, while continuing to nurture commercial and industrial project development within the new construction market.

To enhance program impact and provide continuity and consistency, the utilities will:

Coordinate program implementation with owners, designers, and others in multiple service areas;

Continue to develop and employ alternative delivery models that enable a broader scope of customer participation;

Coordinate and share design analysis assumptions and baselines;

Provide referrals to the appropriate utility for potential projects encountered that fall outside their own service areas;

Conduct onsite installation verification for all completed projects;

Collect, track, and compile comparable project information and results;

Provide quarterly and annual progress updates detailing program accomplishments and status.  Reports in 2004–2005 will comply with the Energy Division’s Reporting Instructions.

A core component of the SBD mission is to prepare the new construction industry for changes to Title 24 energy code.  SBD has consulted with the California Energy Commission (CEC) on potential program strategies to prepare market actors for code change in advance of the 2005 round of standards, currently anticipated to take effect in January 2006.  The program will continue to serve the needs of project owners and design teams in 2004 and 2005 with specific innovations and enhancements intended to help prepare the market for the upcoming code change.  Key innovations and changes include:

The inclusion of energy efficient outdoor lighting technology and design practice in the 2004-2005 SBD incentive structure (in advance of mandated standards in 2006);

Aligning 2004-2005 program rules with the new Federal Air Conditioner and Water Heater Standards per CEC recommendation;

Promoting SBD for currently unregulated occupancies (facilities or occupancies not now included in Title 24) that will be subject to Title 24 in the next round of code change (e.g., lighting in unconditioned spaces);

Development of educational and training programs for industry professionals and market actors in advance of building energy code adoption to provide information on code change specifics, the implications of those changes to construction practice, and strategies for maximizing code compliance margins;

Staged introduction of incentives for various code requirements in advance of code change;

Staged adoption of certain 2005 code elements as prerequisites for program participation.

Increase in minimum incentive levels for industrial processes to $ 0.10/kWh and $0.60/therm to cover a greater portion of incremental measure costsand increase program participation among industrial and agricultural customers.

SBD supports the adoption of integrated design techniques and energy efficient design practice as standard industry procedure by providing tools and education to the design community.  In 2004 and 2005, SBD will continue efforts to develop new, innovative design tools and information through Energy Design Resources.  Continued development of the EDR program may include new and updated design briefs, case studies, and pilot projects.  These resources will be developed to provide owners, architects, and engineers with the information and design tools they need to make the best possible energy efficiency design decisions.  Program resources will be development through a third party, open-bid process to best encourage creative solutions from key market actors and agents.  Additionally, EDR program management will work closely with the California Energy Commission to develop specific elements and classes to train and prepare all market actors for 2005 Title 24 code changes (again, scheduled for implementation in January 2006).

Traditionally, smaller customers and those in non-urban areas have participated in the SBD program at a lower rate than larger and urban customers.  In order to assure greater equity, the program will expand efforts to reach out to these customers in 2004 and 2005.  Specific activities will include:

Establishing relationships with, and providing promotional materials through, local building permitting offices;

Offering on-site education and training classes at regular meetings of regionally-based architectural, engineering, professional organizations, and trade groups including promotion of SBD design assistance and incentives;

Continued development of liaisons with specific organizations representing small and medium size businesses;

Expanding relationships with agricultural business organizations to provide industry-specific information to members;

Outreach through Local Community Initiatives that will seek greater participation by supporting outreach efforts of local governments with information and program materials.

Working through utility-local government partnership programs to provide outreach that is organized and directed by local government and targeted to each community’s highest-potential small and medium sized businesses.

Section II.	Program Process

A.	Program Implementation

A coordinated array of intervention strategies is necessary to overcome the various market barriers standing in the way of sizable net benefits available from an integrated, comprehensive building design.  The SBD approach targets the primary decision makers in new construction projects.  Design assistance and incentives target owners, architects, and engineers, contractors, and project managers with information and financial stimulus to encourage maximum effort in pursuit of comprehensive savings.  The SBD program relies on three basic elements:  the Whole-Building Approach, the Systems Approach, and education and outreach.

SBD’s core strategy centers on an integrated design approach to optimize energy efficiency, known as the Whole-Building Approach.  In the Whole Building Approach, design teams work closely to integrate the energy systems in buildings with complex system interactions and in large, multi-use facilities.  The Whole Building Approach attempts to target all primary decision-makers in new construction projects.  Information, technical assistance, and financial incentives for owners, architects, engineers, vendors, and contractors help transform existing organizational practices.  Design assistance, design analysis, and economic analysis target architects and engineers with the information they need.  Financial incentives to building owners help offset the incremental cost of high-efficiency technologies and incentives to design teams motivate them to evaluate energy efficiency options on behalf of their clients.

For participants who would not normally consider or cannot use a fully integrated design approach, the Systems Approach provides a simplified, performance-based method that moves owners and design teams far beyond simple prescriptive approaches.  The Systems Approach is appropriate for small buildings with simple system interactions, or for projects where the design of the energy systems is done at different phases, where one energy system predominates, or where program intervention occurs late in the design.  The Systems Approach targets the subset of decision-makers involved with smaller or simpler buildings and the narrower range of efficiency options available for those buildings (e.g., a narrower range of efficiency options and fewer choices within that range).  This approach provides informational resources to building owners, their engineers and contractors, targeted design assistance to architects and engineers, and incentives to owners.

Finally, program education and outreach strategies, delivered through SBD’s Energy Design Resources (EDR) component, address market barriers by providing owners and designers with information, education, and tools to help them make the best possible energy efficiency choices.  EDR also compliments project-specific outreach with Web-based design resources and training.  All three elements include strategies that support the CEC’s goals for market transition to the 2005 Title 24 building energy code revisions.

Delivery strategies to bring the three elements to the market utilize the training, educational, outreach, and tool development capabilities of the Pacific Energy Center (PEC).  The capabilities of the PEC are integral to program design as are alliances with organizations promoting energy efficiency and integrated design for the new construction industry.  In pursuit of these ends, SBD will coordinate with numerous organizations and agencies including, but not limited to:

The U. S. Green Building Council’s (USGBC) Leadership in Energy and Environmental Design (LEED) program through development of SBD materials that are used directly to substantiate the energy points component of the LEED scoring system;

The American Institute of Architects, California Council (AIACC) through support of the Desert Practice and Monterrey Design conferences as well as the SBD-AIACC Energy Integration Design Awards

The Collaborative for High Performance Schools (CHPS) through funding for, and leadership of, the organization as well as presentation and hosting of CHPS classes and seminars and the distribution of CHPS materials;

The California Commissioning Collaborative (CCC) through support for and chairmanship of the organization, project commissioning support through EDR resources and the implementation of building commissioning strategies in project development and industry practices;

The Coalition for Adequate Schools Housing (CASH) through membership and annual meeting presentations and program support;

Consortium for Energy Efficiency (CEE) through support for equipment standards development, commercial building guidelines, and wastewater treatment efficiency efforts;

The American Society of Heating, Refrigerating, and Air Conditioning Engineers (ASHRAE) through presentations and support at local chapter meetings as well as involvement in major conferences and events;

The California Energy Commission (CEC) through support of codes and standards and market preparation for adoption of 2005 Title 24 code;

The Department of the State Architect (DSA) through ongoing collaboration regarding public school design;

The California Integrated Waste Management Board through efforts and programs to improve portable classrooms;

The University of California (UC) and California State University (CSU) Systems through SBD involvement in multiple campus projects, support for sustainable development of the new UC Merced Campus, along with support for the LABS 21 energy efficient laboratories project; and

The Building Owner’s and Manager’s Association (BOMA) through provision of commercial energy efficiency information and program support to members.

SBD’s intervention strategies also coordinate with, and complement, separate utility and non-utility programs which seek to drive emerging technologies, transform equipment replacements markets, promote lighting efficiency investments driven by facility remodeling and rehabilitation, and support retrofit programs.  Such programs include the U.  S.  Environmental Protection Agency’s programs for commercial and industrial buildings, National Fenestration Rating Council efforts to improve code requirements for windows, and utility Codes and Standards programs, among others.  Studies funded by SBD’s education and outreach element (Energy Design Resources) substantiate technology uptake and provide a foundation for energy efficiency codes and standards efforts, while SBD prepares the market for those codes.

B.	Marketing Plan

Statewide Marketing

For 2004 and 2005, the statewide SBD implementation team will market to architects, engineers, energy design professionals, building owners, facility managers, professional and industry associations, and contractors.  Marketing efforts include but are not limited to:

The development and distribution of program brochures, informational inserts, industry-specific marketing pieces, and design guidelines addressed to specific market actors;

Delivery of these materials through trade and professional organizations, design conferences, trade shows, and educational seminars and classes including Energy Design Resources training in integrated design practice, industrial energy efficiency seminars, as well as classes specific to Title 24 and future code requirements;

Promotion of sector-specific information and supplemental design stipends to architects and engineers to encourage financial analyses including building simulation modeling for decision-maker use;

Continuation of support for, and outreach efforts through, CHPS, CCC, CASH, AIACC, ASHRAE, and the CEC for meetings, programs, conferences, and activities that promote energy efficiency and integrated design for nonresidential buildings and processes to owners, design and energy professionals, government agencies, and other key market actors;

Statewide development of Energy Design Resources including energy simulation tools, financial analysis tools, Web-based resources, continued industry standard-practice benchmarking, development and delivery of tools, training, and demonstration projects with media promotion for those efforts;

Continued development of the SBD and Energy Design Resources Web sites.

Table 1.  Statewide Marketing Materials

| Marketing Material | Quantity | Method of Distribution | Projected Cost/ Marketing Effort |
| --- | --- | --- | --- |
| Program overview (2 page informational flyer) | 6,500 (2004 quantity /PG&E order) | Trade shows, direct contact, classes, seminars, mail, industry events, conferences | $15,000 |
| Program Brochures, Brochure Inserts | 6,500 (2004 quantity /PG&E order) | Direct customer contact and program promotion, classes, seminars, mail, tradeshows, industry events, conferences | $40,000 |
| Design Guidelines | 5,000 (2004 quantity /PG&E order) | Direct customer contact and program promotion, classes, seminars, | $20,000 |
| Statewide Call for Entries and SBD Energy Efficiency Integration Awards/Promotion of Winners | 4,500 | Targeted mailing/award ceremony/promotional outreach | $50,000 |
| Energy Design Resources CD ROM /Printed Volumes | 2,500 (2004 quantity /PG&E order) | Direct customer contact and program promotion, classes, seminars, | $35,000 |
| Program overview (2 page informational flyer) | 6,500 (2005 quantity /PG&E order) | Trade shows, direct contact, classes, seminars, mail, industry events, conferences | $15,000 |
| Program Brochures, Brochure Inserts | 6,500 (2005 quantity /PG&E order) | Direct customer contact and program promotion, classes, seminars, mail, trade shows, industry events, conferences | $40,000 |
| Design Guidelines | 5,000 (2005 quantity /PG&E order) | Direct customer contact and program promotion, classes, seminars, | $20,000 |
| 2005 Statewide Call for Entries and SBD Energy Efficiency Integration Awards/Promotion of Winners | 4,500 | Targeted mailing/award ceremony/promotional outreach | $50,000 |
| Energy Design Resources CD ROM /Printed Volumes | 2,500 (2005 quantity /PG&E order) | Direct customer contact and program promotion, classes, seminars, | $35,000 |

PG&E Marketing

In addition to statewide marketing activities, PG&E will undertake targeted marketing efforts oriented toward high-potential market sectors or actors including retail, industrial, and institutional customers among others.  Efforts will include, but are not limited to:

Development and distribution of industry-specific case studies and testimonials relating to the value of energy efficiency in terms meaningful to specific market actors;

Promotion of energy efficiency and integrated design analysis through trade advertising, general and project-specific classes, and stakeholder meetings, and building on long-established PG&E customer relationships;

Expanded outreach to multiple-site retailers (chain stores)

Promotion of technical and project-specific design assistance to owners, design teams, builders, and contractors;

Utility-specific promotions through media, one-on-one project outreach, routine calls on industry professionals, as well as through established customer relationships with building and process owners;

Inclusion of SBD promotional information at all Stockton Energy Training Center and PEC/EDR classes oriented toward new construction market actors;

Support of, and marketing through Silicon Valley Manufacturer’s Group; AIACC, USGBC Northern California Chapter, agricultural industry trade and professional organizations, facility managers’ organizations and shows.

Table 2.  PG&E Marketing Materials

| Marketing Material | Quantity | Method of Distribution | Projected Cost/ Marketing Effort |
| --- | --- | --- | --- |
| Industry-specific case study/testimonials | 6,000 | Direct contact, mail, website, trade shows, industry events | $12,000 |
| Advertisement -2004 | Development of two advertisements for two placements in two trade publications | San Jose Business Journal/Structures, San Francisco Business Times | $10,000 |
| Advertisement -2004 | Annual, full-page outreach to architectural and design professionals | Book of Lists | $15,000 |
| Advertisement/Promotion | 4,500 | PG&E’s Current Issues newsletter for business customers | N/A |
| Advertisement/Promotion | 37,000 | PG&E’s For Your Business newsletter for business customers | N/A |
| Promotion | Various | Placement of news stories related to value of new construction energy efficiency with print, television, and electronic media | $15,000 |
| Promotion/Advertising | Various | Targeted marketing outreach using media and one-on-one contacts with Architects / Engineers / Owners of projects in transmission constrained areas | $20,000 |
| Update and additions to industry-specific case study/testimonials for 2005 | 5,000 | Direct contact, Mail, website, trade shows, industry events | $10,000 |
| Advertisement - 2005 | Development of two advertisements for two placements in two trade publications | San Jose Business Journal/Structures, San Francisco Business Times | $10,000 |
| Advertisement - 2005 | Annual, full-page outreach to architectural and design professionals | Book of Lists | $15,000 |
| Advertisement/Promotion- 2005 | 4,500 | PG&E’s Current Issues newsletter for business customers | N/A |
| Advertisement/Promotion - 2005 | 37,000 | PG&E’s For Your Business newsletter for business customers | N/A |
| Promotion - 2005 | Various | Placement of news stories related to value of new construction energy efficiency with print, television, and electronic media | $15,000 |
| Promotion/Advertising - 2005 | Various | Targeted mktg/ outreach w/media and one-on-one contacts: Architects / Engineers / Owners of projects in transmission constrained areas | $20,000 |

C.	Customer Enrollment

Savings By Design’s Participant Process:

Owners, architects, designers, engineers, contractors, or SBD representatives may initiate contact to begin project participation.

Once contact has been made and a qualifying project identified, the building or process owner submits a completed Participation Letter/Letter of Interest (using the appropriate form(s) provided by the utility) indicating their interest in the program.  When applicable, the design team must complete a design team Application during the preliminary or schematic design phase to establish their interest in participating, which will be reviewed and approved by the utility.

An SBD representative will work with the participants to determine which program path applies and how to optimize the energy efficiency of the project.

After evaluation, selection, and design of energy efficiency enhancements is finalized, the SBD representative issues an Incentive Agreement to the owner/design team delineating the proposed project details, estimated incentive amounts, and terms and conditions.

The owner/design team signs, dates, and returns the Agreement to the SBD Representative.  By signing the Agreement, the owner/design team acknowledges that they have read and agree to all program eligibility requirements.  The utility’s counter-signature and date indicate funds have been reserved for the project for a period of 48 months.  Program funding is on a first-come, first-served basis.

If the design team participates in the Whole Building integrated design analysis and life cycle cost reporting component of the program (Whole Building, Track B), on completion of the project analysis and commitment by the owner to the energy efficiency improvements analyzed, the design team is paid 50 percent of the design team incentive along with a $3,500 integrated analysis stipend.

As the building is constructed, energy efficiency enhancements are included in the project as described in the participant agreement.

Once construction is substantially complete, the owner contacts the SBD representative for the project to request an on-site verification.

If the project is built as agreed and the project meets all program requirements, the incentive will be paid.  If the completed design differs from that outlined in the Incentive Agreement, the incentive amount will be recalculated, and may be adjusted (up or down) to reflect the revised, estimated building performance.

The appropriate incentive amount is provided to the building or process owner in a single check.  The design team also receives the incentive in a single payment for participating in Whole Building Approach, Track A or the updated, remaining balance of the design team incentive for those design teams participating in Track B.

D.	Materials

Customers are solely responsible for the design, selection, purchase, and ownership of the qualifying equipment, processes, and structures.  Most measures and processes will require contractor installation.  All equipment must be new and must meet the terms of the technical product specifications requirements.  Used or rebuilt equipment is not eligible for incentives.  Measures must be installed and structures constructed according to applicable codes, standards, regulations, and manufacturers instructions.  Quality installation/construction of materials, equipment, and structures is considered to be as critical to efficiency performance as the inherent efficiency of the device or structure itself.

E.	Payment of Incentives

Please refer to Section C, “Customer Enrollment”, above, for a detailed description of the SBD process for incentive payment to customers.

F.	Staff and Subcontractor Responsibilities

Table 3.  Staffing Structure 2004-2005

| Position | Responsibilities | Project Work Hours |
| --- | --- | --- |
| Nonresidential Programs Manager | Responsible for general oversight of all Nonresidential Energy Management programs including Savings By Design | 0.2 Full Time Equivalent (FTE) |
| Reporting and Tracking Senior Project Manager | Budget, internal, and external reporting | 0.25 FTE |
| Nonresidential New Construction Program Supervisor | The Nonresidential New Construction Supervisor is responsible for all aspects of program oversight including budget, schedules, deliverables, and supervision of program managers, project managers, and field implementation staff. | 0.80 FTE |
| Industrial, Commercial, and Education and Outreach Program Managers | The program managers are responsible for the oversight of specific program elements, including development, implementation, budget, daily operations, and tracking of program progress and achievement of program goals. | 3 FTE’s |
| Project Manager | Data and data systems management, contract management, resources management and deployment | 1 FTE |
| Project Engineers/Sr. Technical Project Managers / Technical Supervision and Management | Project Engineers and Senior Technical Project Managers are responsible for developing industry relationships, advising project management staff on technical issues, providing project oversight as described below for high-potential and specialty projects, managing the post-construction project inspection and verification process | 7.2 FTE’s |
| Project Manager/Sr. Project Managers | Project Managers and Senior Project Managers are responsible for maintaining industry relationships, maintaining and developing databases, pursuing leads, contacting owners and design teams, analyzing projects, providing design analysis and assistance, advising customers and design teams, acquiring/developing program documentation and calculations, obtaining customer agreement, monitoring project development, reporting progress, verifying project completion and adherence to agreement, entering project /incentive information into the database, and conducting customer follow-up | 8.0 FTE’s |
| Project Technical Review and Quality Assurance Specialists | Review projects for adherence to program guidelines, code requirements, engineering and architectural soundness, and verify energy savings calculations | 3 FTE’s |
| Project Processing Technician | Receive projects, review for adherence to procedural and documentation requirements, route as appropriate, prepare owner and design team agreements for signature, ready projects for commitment of funds and subsequently for project payment | 2 FTE’s |
| Administrative/Technical Administrative | Provide administrative and clerical support to entire nonresidential new construction operation | 1 FTE |

PG&E also plans to use a third party to assist in marketing and delivery of SBD’s refrigeration component to the nonresidential new construction market.  Refrigerated warehouses, industrial plants, supermarkets, convenience stores, big box retail stores and similar businesses are significant energy users with unique needs.  These customers require attention from highly qualified and knowledgeable industry providers who have deep vertical knowledge of refrigeration technologies and broad contacts and influence within the industries.  This effort will be met through open competitive bid.

G.	Work Plan and Timeline for Program Implementation

Energy efficiency interventions for nonresidential new construction projects happen over extended periods of time.  To overcome market barriers and issues discussed in Section I. B. relating to risk and industry time frames, SBD acts as a pipeline, continuously contacting customers, gaining trust, determining eligibility, analyzing projects, influencing energy efficiency choices, and then feeding projects into the program.  In order to retain customer confidence in the reliability of the pipeline, the 2004-2005 SBD program must be available on January 1, 2004 or immediately upon Commission approval of this proposal if that date occurs after January 1, 2004.  The following timetable reflects critical dates in the SBD program cycle:

Timeline for 2004-2005 Program Implementation

| Activity/Event | Target Date |
| --- | --- |
| Program Launch | January 1, 2004 |
| Customer Call Center referral update | January 2, 2004 |
| SBD and EDR statewide website update | January 2, 2004 |
| PG&E internal website update | January 5, 2004 |
| Program brochures and inserts printed and available for distribution | January 5, 2004 |
| Calculation methodology for 2004 program changes standardized and available | January 5, 2004 |
| 2004 program changes introduced to all internal program stakeholders/promoters | January 5, 2004 |
| International Air Conditioning Heating and Refrigeration (AHR) Expo | January 26-28, 2004 |
| EDR education and outreach trainings at PEC, Stockton Training Center, Various Customer/Other Sites | Ongoing January, 2004 through December 2005 |
| IOU Statewide SBD team meetings | Quarterly or more frequently through December 2005 |
| USGBC and locality-specific environmental events | Ongoing January, 2004 through December 2005 |
| CASH Annual Meeting | February 23-26, 2004 |
| Complete program rollout meetings with internal and external stakeholders throughout PG&E service area | February 27, 2004 |
| SBD participation in PG&E customer forums | February-May 2004 |
| Business Times real estate advertisement | April 1, 2004 |
| CASH Workshops | April – September 2004 |
| National Conference on Building Commissioning Presentation | May, 2004 |
| Final agreement between CEC, IOU’s, stakeholders on format, timelines for 2005 Title 24 informational materials/classes | May 31, 2004 |
| International Facility Management Association Presentation | June 4, 2004 |
| Inter-utility agreement on time table/methods for integration of additional CEC requested program modifications | June 30, 2004 |
| AIACC-SBD Energy Integration Design Awards | July 1, 2004 |
| Staged introduction and presentation 2005 Title 24 informational materials/classes | August 15, 2004 through December 2005 |
| American Council for an Energy Efficient Economy (ACEEE) Comm’l. Conference | August 22-27, 2004 |
| Business Times architecture Ad | October 1, 2004 |
| AIACC Desert Practice Conference | October 29-31, 2004 |
| Calculations and documentation for 2005 Title 24 code impacts complete | October 31, 2004 |
| Final Utility-CEC discussion and agreement for 2nd round program upgrades to reflect Title 24 code change | November 15, 2004 |
| 2005 Title 24 code-based energy analysis calculation engine modifications complete for 2005 rollout | December 15, 2004 |
| Introduction of additional SBD program changes in anticipation of code change | January 3, 2005 |
| Customer Call Center referral updates | January 3, 2005 |
| SBD and EDR statewide website update | January 3, 2005 |
| PG&E internal website update | January 3, 2005 |
| Product brochures and inserts printed and available for distribution | January 3, 2005 |
| Calculation methodology for 2005 program upgrade standardized and available | January 3, 2005 |
| Program changes introduced to all internal program stakeholders/promoters | January 15, 2005 |
| CASH Annual Meeting | February 1, 2005 |
| Complete program update meetings with internal and external stakeholders throughout PG&E service area | March 1, 2005 |
| SBD Participation in PG&E customer forums | February-May 2005 |
| Business Times real estate advertisement | April 1, 2005 |
| CASH Workshops | April – September 2005 |
| National Conference on Building Commissioning Presentation | May 1, 2005 |
| ACEEE – Industrial Conference | August 1, 2005 |
| AIACC – Monterey Design Conference | September 1, 2005 |

Section III.	Customer Description

A.	Customer Description

Participants in the SBD program span the spectrum of nonresidential occupancies and processes.  They can include all commercial, industrial, and agricultural owners as well as their support teams of designers, developers, contractors, and energy professionals.  In each market segment and geographical area, participants range from very small to extremely large.  Throughout these market sectors and areas, owners and support teams share certain needs while having others that are unique to industry, geography, market sector, or size.

B.	Customer Eligibility

To be eligible for SBD, projects must be:

Located in the service area of a participating utility and subject to payment of the Public Goods Charge (PGC) for electric service and/or the Gas Surcharge for natural gas service as administered by the Commission;

A project in the commercial, industrial, or agricultural market segment, and either:

A new construction, addition, or expansion project, or

A major renovation/remodel project, which involves building system redesign, load increase, or change of occupancy.

At a point where design changes are feasible, preferably in the programming or schematic design phase.

Meet minimum SBD program requirements.

To be eligible for Savings By Design participants must:

Complete and return a “Participation Letter/Letter of Interest” to indicate the owner’s interest in the program;

Complete a “Design Team Incentive Application” to indicate a design team’s interest to participate and to establish a design team leader for eligible Whole Building projects;

Be willing to consider energy efficiency recommendations, which will improve building or system performance significantly beyond Title 24 (or other reference baseline) requirements;

Provide all required documentation, including, but not limited to: selected construction documents, Title-24 documentation, integrated design analysis reports, manufacturer specifications, equipment cut sheets, and incremental cost verification, as requested;

Sign the appropriate completed “Savings By Design Incentive Agreement(s)” prior to installing the selected energy efficient options;

Agree to allow access to the completed facility for on-site verification and, if selected, participate in measurement and evaluation studies; and

Agree that they will not apply for or receive any other incentive, rebates, or financing supplied using Commission Public Goods Charge funds for measures covered under SBD whether offered by vendors, local or state entities, or another utility.

C.	Customer Complaint Resolution

If a customer has a question, concern or dispute related to program policies, rules, or procedures, a program office representative will evaluate the issue and seek to resolve the dispute consistent with program rules, policies, and procedures.  If a customer has a dispute related to work performed by a licensed contractor, PG&E will refer the customer to the Contractor State Licensing Board or, if related to a non-licensed contractor, PG&E will recommend that the customer work directly with the contractor to resolve the dispute.

D.	Geographic Area

The SBD program is available throughout the service areas of PG&E, SCE, SDG&E, and SoCal Gas.  PG&E will also pursue high-impact peak demand reduction for new construction projects in transmission-constrained areas of Humboldt County, San Joaquin Valley (Fresno), San Francisco, and the San Francisco Peninsula through:

Direct project outreach to project owners;

Local government liaisons;

Supplemental marketing efforts through local chapters of AIACC, ASHRAE, and BOMA with emphasis on:

Promotion of sky-lighting systems, perimeter lighting control systems, and air conditioning systems efficiency, as well as

Analysis of possible added incentives (“kickers”) for peak demand reduction in constrained areas for future program inclusion.

Figure 1. 	Savings By Design - Area Served

Section IV.	Measure and Activity Descriptions

A.	Energy Savings Assumptions

| Measure | Gross Energy Savings Per Unit (kWh) | Gross Peak Demand Reduction Per Unit (kW) | Gross Therms Per Unit | NTG Ratio | Useful Life | Gross Incremental Measure Cost | Rebate Per Unit | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Whole Building-Owner Incentive-Electric | 1 | 0.0001 - .001 | N/A | .82 | 16 | $.19/kwh | $.06-.18/kwh | 1,2,3,4,5,6 |
| Whole Building-Owner Incentive-Gas | N/A | N/A | 1 | .82 | 16 | $3.03/therm | $.34-.80/therm | 1,2,3,4,7,6 |
| Whole Building-Design Team Incentive-Electric | N/A | N/A | N/A | .82 | 16 | N/A | $.03-.06/kwh | 1,2,3,4,6 |
| Whole Building-Design Team Incentive-Gas | N/A | N/A | N/A | .82 | 16 | N/A | $.15-.27/therm | 1,2,3,4,6 |
| Day Lighting | 1 | 0.0003 - .0005 | N/A | .82 | 16 | $.15/kwh | $.04/kwh | 1,2,3,4,5,6 |
| Lighting Power Density Reductions | 1 | 0.0002 - .0004 | N/A | .82 | 16 | $.16/kwh | $.06/kwh | 1,2,3,4,5,6 |
| Heating Ventilation and Air Conditioning | 1 | 0.0003 - .001 | N/A | .82 | 15 | $.21/kwh & 3.03/therm | $.12/kwh | 1,2,3,4,5,7,6 |
| Refrigeration | 1 | 0.0001 - .0003 | N/A | .82 | 14 | $.16/kwh | $.05-.08/kwh | 1,2,3,4,5,6 |
| Service Hot Water | N/A | N/A | 1 | .82 | 20 | $2.32/therm | $.34/therm | 1,2,3,4,8,6 |
| Space Heating/Boilers | N/A | N/A | 1 | .82 | 20 | $3.03/therm | $.34/therm | 1,2,3,4,7,6 |
| Process-Electric | 1 | 0.0001 - .0003 | N/A | .94 | 20 | $0.22/kwh | $.10/kwh | 1,2,3,4,5,6 |
| Process-Gas | N/A | N/A | 1 | .94 | 20 | $2.53/therm | $.60/therm | 1,2,3,4,5,9 |

Notes:

| 1) The kwh or therm value is the basis for paying incentive for this measure. 2) The kw value is determined by DOE2 derivitive models, such as Energy Pro, eQuest, and Visual DOE, of each project. These are likely ranges from past projects. |
| --- |
| 3) The net-to-gross value is from the Energy Efficiency Policy Manual, Version 2, Table 4.2. |  |  |  |  |  |
| 4) The estimated useful life value is from the Energy Efficiency Policy Manual, Version 2, Table 4.1. The Whole Building measure life is an average. |  |
| 5) The incremental cost is based on the 2001 DEER study and the 1996 Measure Cost Study using weighted averages derived from historical program data. |
| 6) Rebates are based on incremental costs and market assessment. |  |  |  |  |  |  |  |
| 7) The incremental cost is based on Equipoise's summary, Exhibit 8 average, which is associated with the "Southern California Gas Company's Commercial Gas Water Heaters in the Savings By Design Program-Whole Building and Systems Approach", Equipoise Consulting Incorporated, October 10, 2000. |
| 8) The incremental cost is based on Equipoise's summary, Exhibit 6 weighted average, which is associated with the "Southern California Gas Company's Commercial Gas Water Heaters in the Savings By Design Program-Whole Building and Systems Approach", Equipoise Consulting Incorporated, October 10, 2000. |
| 9) The incremental cost is based on Equipoise's summary, Exhibit 8 Large Boiler-Steam, which is associated with the "Southern California Gas Company's Commercial Gas Water Heaters in the Savings By Design Program-Whole Building and Systems Approach", Equipoise Consulting Incorporated, October 10, 2000. |

B.	Deviations in Standard Cost-effectiveness Values

See A, above.

C.	Incentive Amounts

See A, above.

D.	Activities Description

Education, information, and outreach efforts are necessary to the successful delivery of the SBD program.  While the portion of the budget dedicated to this purpose is delineated at varying levels within the budget tables depending on the IOU, tracking and reporting for these activities will follow the same statewide procedure.  SBD will track and report:

Online courses completed at the Energy Design Resources’ Web site, with the goal of increasing completions by at least 10 percent over 2003 results; and

Custom project outreach efforts including design assistance, design charettes, on-site seminars, and project-specific integrated design training with the goal of maintaining 2003 training levels despite reduced budget allocation for 2004-2005 (when viewed on an annual basis).

Section V.	Goals

The Savings By Design Program at PG&E will realize:

|  | Peak Demand Reduction (Net kW) | Annualized Electric Energy Savings (Net kWh) | Annualized Gas Energy Savings (Net Therms) |
| --- | --- | --- | --- |
| Savings By Design | 19,786 | 81,960,177 | 605,905 |

PG&E’s target for participation from market actors classified as hard-to-reach (rural and small business) is 30 percent of committed Savings By Design program projects.

Section VI.	Program Evaluation, Measurement and Verification (EM&V)

General Approach to Evaluating Program Success

This statewide EM&V plan is based on the Commission’s objectives as outlined in the Energy Efficiency Policy Manual (EE Policy Manual) and adheres to the guidelines in the International Performance Measurement and Verification Protocol (IPMVP).  This plan will continue to use the existing EE Policy Manual and established EM&V methods while the EM&V Protocols and Framework are being completed.  At such time, a detailed EM&V plan will defer to the EM&V Protocols and framework as appropriate to evaluate the program’s success.

The EM&V activities will be carried out in two studies:  the Building Efficiency Assessment Study (BEA) and the Market Characterization and Program Activity Tracking Project (MCPAT).

The 2004-2005 BEA study will build on the Nonresidential New Construction (NRNC) Building Efficiency Assessment (BEA) Studies from PY 2000 to PY 2002, and it will use a similar reporting format.  (2003 plans have been submitted for continuation of this study.)  This ongoing study has assessed the energy efficiency of Savings By Design (SBD) program participants and non-participants since the program’s inception in 1999.

The primary focus of this study in evaluating the program’s success will be to provide measured results in the form of levels of energy and peak demand savings achieved by the program.  The success of the program is also gauged by an on-going process evaluation that assesses market actor attitudes and design practices and assesses participant satisfaction.

The MCPAT study will build on the previous work performed by the past MCPAT and Savings By Design studies.  The MCPAT study has collected and reported data on nonresidential new construction market activity and Savings By Design (SBD) program activity in 2000, 2001 and 2002.  This on-going project provides biennial reports of statewide NRNC market and program activity.  Savings By Design program tracking information is available from the IOU partners implementing the program.  Program and market characteristics, by building type, are reported at the utility level, the county level and the statewide level.  These data are tracked on an on-going basis and developed into standardized reports to allow for assessment of the NRNC market over time.

The two main purposes of this study are to provide information for refining program design and for assessing program accomplishments.  The study is important because evaluation of energy efficiency initiatives requires knowledge of baseline market conditions and changes relative to that specific baseline over time.  The value of this activity will increase over time as time-series data accumulate.

The results provide timely feedback to program managers and policymakers and facilitate incremental improvements to program process and operations.  The results also help identify changes in design practices as a result of program operation.

Approach to Measuring and Verifying Energy and Peak Demand Savings

In regards to the EM&V activities for the BEA study, this on-going study quantifies the whole-building and end-use energy savings and efficiencies of both participant and non-participant buildings.  The approach to developing these data has been used for evaluating statewide commercial new construction since 1999 and the results can be referenced back to previous data to develop time-series trends.  The study calculates savings by the end-use of systems improvements, as well as by whole building integrated design.  The information developed helps assess the success of NRNC program designs and implementation activities.

The 2004/5 BEA Study will produce gross and net program impacts.  The net-to-gross analysis will attempt to estimate the portion of the savings that can be directly credited to the program.  The results of the gross and net analysis will be discussed in an interim report.  The report will describe the analysis methodologies and summarize the results.  An annual report will be prepared that combines the various interim reports and other intermediate deliverables required in the Study, incorporating reviewers’ comments on the earlier reports, and rewriting as necessary to provide continuity and final conclusions.  For continuity, the final report will have the same structure as the PY2000-2002 reports.

The MCPAT study provides information on the full market of new construction projects.  These data are used by the BEA study to contact and assess representative samples of projects that do not participate in the Savings By Design program.

Approach to Evaluating Program Success

The BEA project tracks program participant attitudes and responses to the program, including information on program design, the application process, the design assistance services provided by the programs, the timing of program events relative to project events, etc.

The study approach will be consistent with the BEA 2000-2002 approach, with modifications made as necessary to further investigate results and trends.  Specifically, the study will include the following steps:

Conduct in-depth decision-maker interviews to assess program acceptance, and participant attitudes towards energy efficiency and to solicit feedback on program design.

Develop quantifiable information on the changes in building efficiency attributable to the Savings By Design program influences.  Information about the new Title 24 requirements should also be developed for a similar population of non-participating buildings.

Investigate trends in energy savings, characteristics and/or decision-maker attitudes.

The MCPAT study will continue to provide information for the following two areas:

NRNC market characteristics: construction value and volume, types of buildings, design team characteristics, etc.  This information is needed so that NRNC market activities can adapt and prioritize their efforts to meet the needs of the different segments.  Data will be collected describing the construction value and volume of the NRNC market, types of buildings, sizes of buildings, types of owners, and design team characteristics.  The characteristics of the NRNC market including the actions and changes that occur over time will be tracked.

NRNC Savings By Design (SBD) program activity tracking and penetration in the NRNC market.  Data collected will include the number of program participants, type of participants, number of projects signed up for the program, type and size of projects, type of measures installed, and geographic locations.  This information is drawn from each of the Partner utilities’ internal tracking systems.  Similar to the activities conducted in PY2000-2002, the data will be integrated to support statewide and cross-utility analyses.

Using the SBD program activity data and the NRNC market characterization data, semi-annual SBD Program Tracking and Penetration Analysis Reports are prepared.  The reports will categorize and analyze the SBD program activity according to number of participants in the program, number of projects signed up for the program, type and size of projects, and energy savings.  The reports will analyze the relative penetration of the SBD program activities in the different NRNC market segments and service territories.  The reports will also document trends over time, as the Program extends its activity in the NRNC market.  Program penetration will be calculated as the fraction of total NRNC projects that participated in the SBD program.

Potential EM&V Contractors

The contractors listed below can objectively and effectively evaluate program success.  As a group, their work includes impact evaluation, measurement and verification, process evaluation, market assessments, and verification of program accomplishments.  These firms have a track record of completing high quality, objective studies of energy efficiency programs either for the California investor-owned utilities or for other entities whose studies we have been able to review.  This list does not include all of the qualified evaluators who could objectively evaluate program success.  The final list of evaluation consultants will be based on several factors including future Commission decisions, the mix of approved programs and the experience of the evaluation consultants.

| ADM Associates | KVDR Consulting |
| --- | --- |
| Aloha Systems | Megdal & Associates |
| Alternative Energy Systems Consulting (AESC) | Nexant |
| Applied Management Sciences Group | Opinion Dynamics |
| Architectural Energy Corporation (AEC) | Quantec LLC |
| ASW Engineering Management | Quantum Consulting |
| Aspen Systems Corporation | Ridge and Associates |
| EcoNorthwest | PA Consulting Group |
| Energy & Environmental Economics | Research Into Action |
| Energy Market Innovations | RLW Analytics |
| Equipoise Consulting | Robert Mowris & Associates |
| Freeman Sullivan & Co. | SBW Engineering |
| Frontier Associates | Science Applications International Corp. (SAIC) |
| GDS Associates | Skumatz Economic Research Associates (SERA) |
| Global Energy Partners | Summit Blue Consulting |
| Heschong-Mahone Group | TecMRKT Works |
| ICF Consulting | Vanward Consulting |
| Itron (RER) | Wirtshafter Associates |
| KEMA-Xenergy, Inc |  |

SBD will also undertake discussions with the CEC, the Commission, and CALMAC regarding the application and update of measurement and evaluation procedures, energy and peak demand calculation procedures, as well as the applicability to the current program of certain new construction definitions, specifically, free-ridership, and spillover.  SBD will seek to apply the results of these discussions to the 2004-2005 SBD program.

Section VII.	Qualifications

A.	Primary Implementer

PG&E has provided residential and nonresidential customers with energy efficiency programs at the direction of the Commission since 1976.  Early programs provided information to residential customers on energy efficient appliances, home insulation, heating and air conditioning while providing commercial customers detailed, on-site energy analysis (audits).  Programs and services for both markets evolved into information programs coupled with equipment rebate programs, loan programs and incentives for new building construction by the early 1980s.  These programs have grown, contracted or been redirected based on the changing goals of the Commission, the needs of the marketplace and the input from the many community stakeholders in the energy efficiency industry.

Surveys of customers indicate that PG&E has remained the most trusted source for unbiased energy efficiency information, services and programs.  Customers continue to look to PG&E for assistance in managing their energy use and costs.

Teams of PG&E engineers, marketing professionals and customer service specialists have demonstrated significant competencies in a variety of essential areas of program design and deployment, reporting/accountability program measurement, assessment and evaluation.

PG&E has offered successful new construction programs based on the Title 24 energy code since 1989.  Early programs relied on simple, prescriptive activities to drive energy-efficient equipment and technology uptake for new construction projects.  Starting early in the 1990s, program managers became aware of the huge energy efficiency potential that integrated design techniques could add to prescriptive activities.  Program managers pushed program boundaries and the program evolved to include Whole Building evaluation through performance-based analysis.  The current Savings By Design program is the culmination of these efforts.  In 2002, the Association of Energy Service Professionals recognized the SBD program as the model energy efficiency program of its type.

Teams of utility managers, engineers, marketing professionals, and customer service specialists with a demonstrated background in the new construction industry have proven competence in all vital areas of:

program design;

program deployment;

project impact;

influence on industry practice;

reporting and accountability; and

program measurement, assessment, and evaluation.

Program designs at the IOUs have provided SBD with broad, well-founded program elements that meet market needs while providing the quantifiable savings valued by the Commission.  SBD program managers have repeatedly proven their capability to deploy the program rapidly and flexibly in light of Commission priorities.  In a market that has experienced two successive boom-and-bust growth cycles in little over a decade, utility new construction programs have consistently maintained a high record of success in an energy-efficiency market rarely targeted by private industry due to its complexity.

Program Design

Responsive, timely, action characterizes the PG&E team approach to program design.  Commission priorities, changing markets, technologies, and priorities of interested stakeholders require the flexibility to respond to the wide variety of needs within the annual program cycles.  PG&E’s design team has demonstrated its ability to move rapidly and effectively, from the resource acquisition emphasis of the pre-1998 programs to the market transformation focus of the California Board for Energy Efficiency.  PG&E’s program design team also met the challenge of rapidly responding to the 2000 energy crisis by designing programs that not only saved energy but also encouraged customers to change behavior and business practices.

Program Deployment

A solid program infrastructure combined with the participation of key market actors and experienced service providers have ensured PG&E success in program deployment for the last three decades.  Successes are evinced year after year by the accomplishment of the goals and milestones set in place through Commission and PG&E agreements.  PG&E’s staff has nurtured relationships with the entire spectrum of parties whose joint efforts are necessary both to capture the interest and enthusiasm needed for a new program and to responsibly remove barriers to deployment.

Reporting/Accountability

Responding to the more rigorous reporting and accountability requirements from the Commission over the last 10 years, PG&E has developed increasingly sophisticated procedures and competencies to meet the new levels of precision required in these areas.  PG&E has been able to provide thorough, reliable reporting as the needs and goals of the Commission have changed from the simple semi-annual and annual reports of the 1980s to the complex reporting and net benefit accountability over the 10 year time period required of the pre-1998 programs.  PG&E reports on programs using both the pre-1998 methodology and the subsequent reporting requirements for monthly, quarterly and annual reports as well as responding to data requests from the Energy Division, administrative law judges of various proceedings and interested parties in proceedings.

Measurement, Assessment and Evaluation

PG&E’s current measurement, assessment and evaluation (MA&E) capabilities are especially suited to meet the requirements of the Commission’s present directives.  The MA&E team members have worked closely with regulatory agencies and other IOUs, as well as other interested stakeholders, in establishing and coordinating the California Measurement Advisory Council (CALMAC) and the earlier California Demand Side Management Measurement Advisory Council (CADMAC).  The MA&E team has participated and/or led many statewide measurement, assessment and evaluation studies as well as studies focused on local programs and issues.

PG&E’s energy efficiency staff has the strength and commitment to provide the Commission with successful programs responsive to both the goals of the Commission and the needs of customers.

B.	Subcontractors

Subcontractors to be determined by an open bid process

C.	Resumes or Description of Experience

Grant Duhon

CAREER SUMMARY

Grant’s experience includes twenty-seven years of progressively responsible experience in construction-related positions, twenty-two years of which involve energy efficiency, conservation, and management.  Grant has succeeded in a range of challenging and complex assignments, from technical project support and planning to integrated program design and personnel management.  For over ten years, Grant has been employed by, or on behalf of, PG&E, promoting energy efficiency within the new construction marketplace, developing programs, and managing development and implementation staff.  His career has allowed him to establish close working relationships among energy-efficiency professionals as well as with government agencies, industry associations, and the design and development communities.  Grant brings considerable construction–industry skills and know-how to his position and has demonstrated his ability to design - and implement - marketing programs, demand-side management and resource acquisition programs, as well as market-transformational energy efficiency programs.  Grant has thorough understanding of the nonresidential new construction market and market actor practices.  In his career, he has managed projects, programs, teams, and branch offices with responsibilities for scopes, project and contract development, and total operations management including oversight of personnel, financial planning, budgets, and profitability

EMPLOYMENT HISTORY

10/99 - Present     	   Pacific Gas & Electric Co 	San Francisco, Ca	Program Manager Supervisor

6/93 - 10/99	            Granite Energy Svcs/PG&E 	San Francisco, Ca	Program Manager &

Project Manager

8/90 - 6/93              	Lennox Industries           	San Francisco Bay Area, Ca	Territory Manager

1/90 - 8/90      	        G.P.M.  Corp.                  	Auburn/Sacramento, Ca	Independent Representative

2/88 - 11/89            Milmac, Inc.	Sacramento, Ca 	Outside Representative

5/87 - 12/87            Gardner Engineering       	Reno/Las Vegas, Nv.	Energy Svcs.  Sales/Mgt.

3/85 - 4/87              Wallis Trane Company          	Reno, Nv. / Sacramento, Ca	No.  Nevada Team Leader

3/79 - 1/85              Washoe Medical Cr.        	Reno, Nv	H.V.A.C.  Lead Journeyman

7/76 - 3/79    	          DuAll Services		Reno, Nv		Contractor/Co-owner

EDUCATION

Undergraduate Degree:

General Studies, Emphasis Env.  Sciences and Agricultural Mgt.  Truckee Meadows College, Reno, Nevada, 1985

Continuing Education:

Personnel Supervision & Management Certification

American Management Association

ASSOCIATIONS AND AFFILIATIONS

Co-Developer, Savings By Design Program

Past Co-Chair, Board Member Alternate, Collaborative for High Performance Schools

Chair, California Commissioning Collaborative

Representative Member, Eagle Forum, AIACC

Member, California Association of Building Energy Consultants

Member, United States Green Building Council

Member, Building Commissioning Association

Past/Associate Member, ASHRAE, SMACNA, BOMA

Oliver Kesting

CAREER SUMMARY

More than twelve years experience in the field of energy efficiency, including involvement with schools, commercial / industrial facilities, building code updates, measurement and evaluation, energy modeling, and management of large-scale retrofit projects, and technical design review of new construction.

EMPLOYMENT HISTORY

Pacific Gas and Electric Company – San Francisco, California

2000 – Present	Program Manager

Program Manager - Develop and focus elements of the Commercial component of the Savings By Design program to meet the needs of building owners, and the building design community.  Coordinate activities of various stakeholder groups including inter-utility group and the Collaborative for High Performance Schools.  Develop and manage contracts for external resources to provide technical expertise and develop supporting program materials.  Manage updates of commercial energy baselines to lead adoption of code changes.  Assure project compliance with program and corporate goals, policies and procedures.  Develop supporting resource plans, budgets, and schedules.

City and County of San Francisco – Hetch Hetchy Water and Power:  Bureau of Energy Conservation

1997 – 2000

Energy Specialist – Evaluated, implemented, and monitored energy conservation programs in the municipal sector.  Managed large-scale retrofit projects.  Developed distributed generation within the city of San Francisco.  Directed contractors and consultants in support of energy efficiency analysis.  Conducted energy audits and recommended energy saving projects in City facilities.  Worked closely with City architects and engineers to facilitate energy efficient designs.  Managed energy tracking system for all municipal facilities.

Quantum Consulting, Inc.

1996 – 1997

Analyst – Collected and evaluated data to quantify savings for utility demand side management programs.  Performed on-site auditing, developed engineering algorithms and modeling procedures, developed Department of Energy (DOE-2) energy models, and conducted data quality control.  Supervised a team of on-site auditors.  Utilized automatic meter reading equipment, end-use data loggers, monthly energy billing data, and detailed site information.

Honeywell DMC Energy Services

1995 – 1996

Project Analyst - Technical consultant to Pacific Gas and Electric’s Energy Efficiency Resource Center.  Designed energy audit and analysis materials for PG&E’s commercial energy efficiency programs.  Provided technical energy efficiency support to PG&E employees and customers.

Energy Calc Company

1994 – 1995

Energy Consultant - Aided architects and builders in creating energy efficient designs to meet California’s energy code.   Acted as liaison between designers and state officials.  Performed reviews of blueprints and computer analysis of building plans.  Verified building code compliance and provided documentation of compliance for the building industry.

Pacific Gas and Electric

1991 – 1992

Commercial Auditor – Conducted energy audits focusing on lighting and HVAC retrofits.  Calculated potential energy savings and payback periods for commercial and industrial customers.  Formulated recommendations and made presentations to business owners.  Helped design strategies for PG&E’s 1992 Retrofit Program.

# EDUCATION

B.S., San Jose State University, San Jose, California – Environmental Studies / Energy Management

Certificate in Energy Management and Design, Sonoma State University, Sonoma, California

Certified Energy Manager – Association of Energy Engineers

PROFESSIONAL REGISTRATION / AFFILIATION

Member, Collaborative for High Performance Schools

Member, Association of Energy Engineers

Patricia Dugger

CAREER SUMMARY

More than six years experience developing, implementing and managing energy efficiency programs, with emphasis on small / medium commercial retrofit, residential retrofit, and commercial, industrial and agricultural new construction.

EMPLOYMENT HISTORY

Pacific Gas and Electric Company – San Francisco, California

2002 – Present		Program Manager

Program Manager - Develop and implement the Industrial and Agricultural (I&A) component of Savings By Design.  Communicate program policy and strategies to the field staff and customers.  Provide oversight for the customer reports and design assistance provided to customers.  Administer third party contracts for program delivery to the refrigeration, wastewater and hi-tech sectors.  Guide the development of I&A sector new construction energy baselines, including for dairies, cleanrooms, wastewater treatment plants, compressed air, and wineries.  Collaborate with industry groups and utilities on program component development.  Coordinate with internal, inter-utility and external stakeholder groups regarding the I&A component of SBD for marketing and program development purposes.

2001 – 2002		Project Manager

Project Manager – Managed the development and enhancements to the Savings By Design (SBD) project database.  Wrote and administered contracts for SBD, Energy Design Resources (EDR), and Collaborative for High Performance Schools (CHPS).  Acted as a liaison between SBD field staff and others on software, marketing, training, and program policy.  Supported inter-utility development and enhancement efforts for the SBD California New Construction Calculator (CaNCcalc) software.  Supported SBD through planning, logistics and marketing, and website maintenance.  Developed, ran and distributed monthly Account Services goal and budget reports for Savings By Design.

AllBusiness.com – San Francisco, CA

1999 – 2000

Channel Manager – Managed content, services, marketing and business development for four topical areas on a leading small business web portal owned by NBCi.  Created and published the first telecommunications channel on the website.  Developed and published the bi-weekly Internet & E-commerce customer newsletter.  Edited and published content to the live site.  Performed market research and competitive analysis for area development.  Worked with third parties partner companies on contract negotiations and relationship goals, website co-branding and partner integrations.

Honeywell DMC Energy Services – Oakland, CA

1996 – 1999

Residential Standard Performance Contract (SPC) Marketing Coordinator – Managed the SPC print, radio, mail, telemarketing and canvassing campaigns focused on installation of programmable thermostats.  Tracked campaign performance and managed the marketing budget.  Wrote and edited copy for direct mail pieces, radio spots, and point-of-purchase marketing collateral.  Managed customer service team and temporary employees.

Energy Efficiency Resource Center (EERC) Program Coordinator – Coordinated operations for an 8-person energy efficiency team responsible for managing PG&E’s Express Efficiency program and other energy efficiency programs, especially those serving small commercial, agricultural and chain account customers.  Coordinated site surveys, and conducted Business Energy Survey Tool (BEST) telephone surveys.  Developed content for the Trade Ally News, an energy efficiency vendor newsletter.

Managed PG&E client relationship, department policy and procedures, and overall quality of service.  Trained EERC team on Total Quality Management methods and skills.  Researched the California energy market and developed business proposals for energy management contracts.

Customer Marketing Representative – Consulted with PG&E’s small to medium-sized business customers on energy efficiency, equipment retrofitting technologies, and PG&E rebate programs.  Performed commercial energy surveys.  Acted as the point of contact for the commercial retrofit financing program.

EDUCATION

B.A., Connecticut College, New London, Connecticut – Anthropology / Environmental Studies – Graduated with Honors

Andrea Porter

CAREER SUMMARY

Over 12 years experience in managing energy efficiency programs, business and residential energy surveys, business customer account maintenance, and facility management for Pacific Gas and Electric Company.

EMPLOYMENT HISTORY

Pacific Gas and Electric Company – San Francisco, California

May 2003 – Current	Program Manager

2001 -April, 2003	Project Manager

1995 - 2001		Account Representative

1993 - 1995		Building Coordinator/Assistant Property Manager Trainee

1991 – 1993		Building Supervisor

Energy Efficiency Programs

Savings By Design Program Manager: Develop marketing materials and trainings that support delivery of PG&E's new construction energy efficiency programs to targeted market segments.  Deliver marketing materials and trainings to the field utilizing support of stakeholders and targeted market organizations.  Develop and manage contracts for external resources.  Assure project compliance with program and corporate goals, policies and procedures.  Develop supporting resource plans, budgets, and schedules.

School Resources Project Manager: Coordinated multiple efforts of consultants, business partners, and government agencies to provide K-12 school districts energy efficiency resources.  Resources provided were:  finance workshops, maintenance and operation workshops, custodial workshops, energy surveys, Energy Star Benchmarking, and educational materials for teachers and students.

Account Services:  Provided customer service and rates related functions to business and residential accounts, including providing energy surveys, qualifying customers for customer energy efficiency rebate programs, responding to billing inquiries, verifying application of appropriate rate schedules, coordinating service requests, drafting noncore gas contracts, drafting agreements and coordinating interconnection work for cogeneration and photovoltaic systems.  Acted as liaison for Berkeley’s Green Building Program and ReEnergize East Bay.

Corporate Building and Land Services Support

Provided tenant services work for all corporate employees, processed contract services invoices, and assisted in preparation of new contracts.  Approved and coordinated tenant facility work requests; directed contract employees, assisted in directing Building Mechanics and Engineers, coordinated lease facility functions, customized facility management computer program and acted as systems administrator; assisted in increasing client satisfaction by approximately five (5) percent.

EDUCATION

Cal Poly, San Luis Obispo - B.S.  Industrial Technology

John F.  Kennedy University, Orinda - M.A.  Consulting Psychology

Norman E.  Stone

CAREER SUMMARY

Expertise in alternative fuel vehicles, clean air programs, marketing energy efficiency programs and designing incentives for the complete spectrum of the company's customers (residential, industrial, commercial, and agricultural).  Over 20 years of experience in customer education, audits, and energy conservation programs.

EMPLOYMENT HISTORY

PG&E Company – San Francisco, California

2001 – Present		Manager, Business Energy and Clean Air Management

1993 – 2001		Manager, Low Emission Vehicle Programs

1993 – 1997	Manager, Commercial, Industrial and Agricultural Energy Efficiency Programs

1992 – 1993		Manager, Natural Gas Vehicle Market Development

1992 – 1993		Marketing Manager

1985 – 1989		Energy Management/Marketing Supervisor

1983 – 1984		Energy Management Engineer

1980 – 1982		Energy Management Representative

Manager, Business Energy and Clean Air Management

- Manage program design and delivery for all commercial, industrial, and agricultural energy efficiency programs, including information programs, energy management services, and incentive programs (retrofit and new construction)

- Concurrently manage PG&E's natural gas vehicle (NGV) and electric vehicle (EV) programs described below.

Manager, Low Emission Vehicle Programs

- Oversee the delivery of natural gas (NGV) and electric vehicle (EV) programs, including Epact compliance, infrastructure development to support PG&E fleet NGV and EV acquisitions, customer education, and research and development.

Manager, Commercial, Industrial and Agricultural Energy Efficiency Programs

- Managed the design and delivery of energy efficiency programs for all customer segments, including the development and promotion of incentive and informational programs.

Manager of Natural Gas Vehicle Market Development

- Executive-on-Loan to the American Gas Association (A.G.A.) in Arlington, Virginia.

- Provided direct marketing and sales support to A.G.A. member organizations.

- Project manager for the national Natural Gas Vehicle Conference in Orlando, Florida.

Marketing Manager

- Managed delivery of energy management surveys and incentive programs to Residential, Commercial, Industrial, and Agricultural customers for PG&E’s Vallejo-Napa Division.

- Supervised approximately 15 employees.

Energy Management/Marketing Supervisor

- Managed delivery of energy management surveys and incentive programs to all customer segments for PG&E’s Stanislaus Division.

Energy Management Engineer

- Performed energy surveys for commercial and industrial customers whose annual energy consumption exceeded 100,000 kWh a year.

- Supervised five energy management representatives, providing energy surveys to small commercial customers whose annual energy was less than 100,000 kWh a year.

Energy Management Representative

- Performed energy surveys for large commercial and industrial customers.

- Conducted follow-up visits of customers who had received energy audits to determine what recommendations had been implemented.  Documented any load changes at the customers’ facilities.

EDUCATION AND PROFESSIONAL REGISTRATIONS

United States Military Academy, West Point, New York

Registered Professional Engineer, Mechanical (California, #25631)

ASSOCIATIONS AND AFFILIATIONS

- Member, Board of Directors, California Natural Gas Vehicle Coalition, Sacramento, California (Past Chairman – 1999-2001)

- Member, California Electric Transportation Coalition, Sacramento, California

- Member, Executive Committee, Natural Gas Vehicle Coalition, Washington, D.C.

Section VIII.	Budget

# Footnotes

Estimates from internal PG&E analysis of participating industrial projects, performed in August 2003, indicates that SBD’s 2002 industrial incentives generally cover an average of only 8-12% of incremental measure cost

NRNC Market Characterization and Program Tracking (MCPAT) Report PY2002, Quantum Consulting, August 2003

# Text boxes

SoCal

Gas

###### SDG&E

###### SCE

###### PG&E