Redwood Coast Energy Authority

PY2004/PY2005 Energy Efficiency Program Proposal

CPUC Proceeding Number R.01-08-028

Submitted to the California Public Utilities Commission

September 23, 2003

Email Submission Confirmation Number:

[To be entered prior to printing and mailing original copies to CPUC]

Title of the Proposed Program:

REDWOOD COAST REGIONAL COMPREHENSIVE ENERGY INFORMATION AND EDUCATION PROGRAM

Contact Persons:

Kathy Jack

Executive Director

Redwood Coast Energy Authority

c/o Humboldt County Board of Supervisors

825 Fifth Street, Room 111, Eureka, CA 95501

(707) 825-2168

kjack@arcatacityhall.org

Other programs proposed:

Redwood Coast Regional Comprehensive Public Facilities, Business and Industry Program

Redwood Coast Regional Comprehensive Residential Program

[Printed copy of email confirmation to be interred following this page prior to printing and mailing original copies to CPUC]

Table of Contents

Section I.	Program Overview	3

A.	Program Concept	3

B.	Program Rational	3

C.	Program Objectives	10

Section II.	Program Process	11

A.	Program Implementation	11

B.	Marketing Plan	15

C.	Customer Enrollment	18

D.	Materials	18

E.	Payment of Incentives	18

F.	Staff and Subcontractor Responsibilities	19

G.	Work Plan and Timeline for Program Implementation	19

Section III.	Customer Description	21

A.	Customer Description	21

B.	Customer Eligibility	23

C.	Customer Complaint Resolution	23

D.	Geographic Area	23

Section IV.	Measure and Activity Descriptions	25

A.	Energy Savings Assumptions	25

B.	Deviations in Standard Cost-effectiveness Values	25

C.	Rebate Amounts	25

D.	Activities Description	25

Section V.	Goals	26

Section VI.	Evaluation, Measurement and Verification (EM&V)	27

Section VII.	Qualifications	29

A.	Primary Implementer	29

B.	Subcontractors.	31

C.	Resumes or Description of Experience	34

Section VIII.	Budget	35

# Section I.	Program Overview

## A.	Program Concept

The Redwood Coast Energy Authority (RCEA) is pleased to submit this proposal in response to the Californian Public Utilities Commission (CPUC) Decision 03-08-067.  The Redwood Coast Regional Comprehensive Energy Information Program (“Program”) proposes to build on the strengths of the RCEA to significantly increase the cost effectiveness of all energy efficiency information programs in this hard-to-reach market by overcoming identified participation barriers, tailoring the program offerings to unique local needs, and employing locally-based resources of the RCEA. The program concept is to provide a local resource that promotes and implements all energy efficiency information programs in the region to ensure that this important hard-to-reach market is served.  The Redwood Coast Energy Efficiency Program is comprehensive in that it serves all market segments.  The total 2004-2005 budget for this program is $953,746 to be funded by electric and gas public goods charges.  This does not include resources procurement funds identified by PG&E for energy efficiency.

## B.	Program Rational

This program addresses many of the policies, criteria and priorities as set forth in D.03-08-067 and Section 381.

The Program targets underserved or hard-to-reach customers

The RCEA region, by virtue of its remote rural geographic location, is considered a hard-to-each market.  This efficient and cost-effective program delivery strategy ensures that more customers, particularly the hard-to-reach customers of Humboldt County, will be aware of and create a demand for energy efficiency services and programs, whether provide by the RCEA, through PG&E’s statewide programs, or other program providers.

This Program Addresses Equity Issues

To date, there has been no accountability of PGC-EE funds collected by utilities compared to dollars that are spent in a given community or region.  Although we have no hard data to substantiate this, it is likely that a region like Humboldt County, due to its rural nature and distance from the primary resources of PG&E energy efficiency programs, has not received the full benefit of the PGC-EE dollars that it has paid into the programs in the last 20 years.  This Program is designed specifically to address that issue and to ensure the Humboldt County region has reasonable access to the estimated $2.7 million of the proportionate share of PGC-EE surcharge dollars that will be collected from ratepayers in the region during 2004-2005.

(?)

This Program is Innovative

This Program utilizes an innovative approach to aggregating energy efficiency programs and offering them through a local agency in order to increase local awareness and utilization of the programs as well as overall cost effectiveness.

This Program Has Been Designed To Best Suit the Regions Needs

In order to determine the current needs for energy efficiency programs in the region, the RCEA staff and consultants conducted numerous discussions and formal focus groups with representatives from the member agencies, the business community as well as energy efficiency providers.  The RCEA was specifically interested in a) the degree to which energy efficiency program information has reached Humboldt County constituents, and b) to identify specific barriers to energy projects and steps in the process that caused energy efficiency projects to either fail or not be considered.  One of the most cited barriers to energy efficiency was the lack of a local resource to assist entities with identifying and applying appropriate resources to their specific needs.  In addition, many cited the need for assistance in implementing follow-through on efforts that have identified opportunities in the past.  The last, and probably most significant challenge, was that rural customers tend to be most impacted by the current downturn in the economy, and the lack of availability of resources is more pronounced than in other region’s that may have a more robust economic foundation.  Other needs identified were assistance with gathering information at the front end of a project to determine options and scope, analyzing project feasibility, analyzing financing options, procuring funding once a project has been identified, processing energy program applications and identifying and selecting contractors to complete the project.

This Program is Closely Coordinated with other Program Implementers

Close coordination will be assured through a close working relationship between RCEA and PG&E and other program providers to ensure no overlap between this program and those of other providers.  The RCEA and PG&E both worked hard to make this a joint parties program, and were anxious to take advantage of the synergies that could have resulted in that arrangement.  This was not possible due to the inability of the parties to align their proposed program plans in the limited time between starting the partnership discussions and when the proposal were due to be submitted.  Despite the fact that this is an independent proposal, the management of PG&E has committed to seek partnering and collaboration opportunities with any RCEA programs ultimately approved by the Commission to the fullest extent possible.

In addition, the RCEA will go beyond this mandate to proactively look for opportunities to promote other CPUC-EE programs where these opportunities have yet to be identified to exist (e.g. new statewide or local programs that RCEA was not aware of at the time of writing its proposal).    Coordination with PG&E includes promotion of the following programs: SPC, Express Efficiency, Non-Residential Audits, Savings-by-Design Programs, Appliance Recycling, Single Family Rebates, Multifamily Rebates, Home Energy Efficiency Surveys and California Energy Star New Home Construction.   Coordination with other program providers will also be a priority, including programs such as the Ecology Actions Right Lights Program (if approved).  In addition, coordination with marketing and outreach activities will occur with the administrators of the statewide Flex Your Power campaign to ensure that the greatest leverage is obtained by consistent messaging and timing of promotional efforts, and that the RCEA does not duplicate creation of outreach and information resources that have already been funded.

This Program helps alleviates transmission constraints in an area identified by California Independent System Operator

The proposed program supports the overall California grid reliability in that Humboldt County has been identified by the California Independent System Operator (CA-ISO) as a region of concern due to congestion of the transmission system, as well as the potential for stability, voltage collapse, and thermal overload issues.  These problems are further compounded by the reduced level of availability of the area generation due to age, generator maintenance outages, and potential shortages or limitations of fuel (i.e. natural gas, oil, wood chip fuels).  In addition, there is some concern that the rebound in electricity consumption during 2003 from previous years has been significant, that despite the struggling economic conditions, (See Figure 1).

This Program is designed to achieve maximum cost effectiveness through the use of a combination of local resources and the inherent strengths of the local utility- PG&E.

Program Successes to Date

Since the RCEA is a new program, the program successes to date have been limited, but significant.  As a result of the successful organization of the RCEA and its outreach to communities, there has been growing focus on the specific needs of the region and a very positive response to the RCEA efforts.  In one recent focus group discussion, a participant pointed out that they were “particularly pleased that the RCEA was reaching out to the community to test our assumptions and to design the program to meet the needs of the community.”  In addition, to assure the best chance for success, the program will be modeled after (and build on the lessons learned from) similar successful programs in other jurisdictions throughout the State of California, including those of the San Diego Regional Energy Office (SDREO) and other emerging efforts in Ventura County, the Monterey Bay Area, and the South Bay Cities Council of Governments.  In addition, by design, the program will be highly leveraged with other successful programs, including not only that of PG&E, but also that of other non-utility local programs.  While this approach may seem challenging from the perspective of avoiding replication of efforts, good upfront and ongoing coordination and communications will ensure the strengths of each program are best utilized and the gaps in program coverage are filled.

This Program Will Overcome Significant Market Barriers

This Program is designed to address all of the market barriers identified in the Energy Efficiency Policy Manual (Version 2).  A summary of these barriers, as well as those identified locally, and how this program proposes to overcome those barriers, is found in Table 1 on the following pages.

| Table 1: Market Barriers/ Challenge and Corresponding Program Attributes Design to Address Them |
| --- |
| Market Barrier/ Challenge | Corresponding Program Attribute |
| Lack of Consumer Information /Availability of a local resource to assist entities with identifying and applying appropriate resources to their specific needs. RCEA efforts to date and subsequent focus groups have revealed that although energy information has reached Humboldt County, the lack of a centralized and local clearinghouse for information on energy programs is very noticeable. | Program will address the lack of availability of consumer information by providing local area customers with a local source of energy efficiency information and resources. This program will focus particularly on the information and resources that promote the statewide programs. In addition, the program will tailor information and resources that are not widely available to its specific market segments important to the region, such as the timber and dairy industry. This strategy will accomplish a more targeted and comprehensive penetration achievable using RCEA’s established and growing communication channels aligned with PG&E’s technical resources and rebate programs. The RCEA will also raise the visibility of the applications and benefits of energy efficiency products through several highly visible energy projects that highlight energy efficiency products and their benefits, such as those that are highlighted in the Energy Centers throughout the state and those that are recently proven in the statewide Emerging Technologies Program. |
| Need for assistance in implementing follow-through on opportunities that have been identified in the past. | Program will address this by having local resources dedicated to ensuring that the resources and technical assistance necessary to ensure implementation of projects occurs. This is particularly important in programs like Savings-by-Design, where there is a high degree of interaction between project implementers (i.e. architects, engineers) and the program administrators to ensure plans are checked and turned around expeditiously (this has been cited as a major barrier in customer participation in this specific program). |
| Lack of availability of resources due to impact of current economic conditions. | Program addresses this by providing targeted resources (technical and financial) at a specific locale that is significantly impacted by the current economic downturn. |
| Cost-effectiveness, particularly in light of the need for local personnel resources that could be redundant to IOU functions | The RCEA will work toward maximizing the inherent strengths of the combination of local resources and those of PG&E and other providers. While this close coordination may take a few months to fully optimize, the end result should be an overall higher cost effectiveness through the use of local resources where local resources are appropriate (e.g. day-to-day information and customer interaction), and PG&E resources where most appropriate (e.g. technical resources and rebate processing). |
| Higher start-up expense/ Lack of Financing for energy efficiency improvements, which is particularly acute for rural customers that are most impacted by the current downturn in the economy and its impact on the region’s economic foundation. Public agencies whose budgets have been significantly tightened due to local and statewide revenue shortfalls are particularly impacted. | Program seeks to “allocate” PGC-EE resources in an equitable manner to this region. Although no good statistics are available on how much of the PGC-EE dollars make it back to Humboldt County, we suspect it is much less than that to which is spent in more urban areas that have better access to resources and information to take advantage of the PGC-EE programs before incentive funds are fully subscribed. Program also seeks to overcome the financing barriers through the use of existing (e.g. California Energy Commission Low Interest Loans) and new financing programs. For example, the RCEA is in discussion with Headwaters Fund and local banks to assist with financing of projects once identified. Also, the RCEA will be investigating the formation of a project aggregation pool to achieve greater economies of scale and cost effectiveness and to potentially finance them through an RCEA-led ESCO type contractual arrangement. |
| Barriers to the entry of new energy efficiency service providers. | This program will assist local companies with training, gaining access to customers, and other resources that should enable them to grow their businesses and capabilities. In addition, the program will introduce resources (e.g. case studies, tools, and best practices) that are more widely available in larger urban areas. Lastly, the program will foster greater consumer demand for local energy efficiency service products and providers by providing marketing and outreach for the statewide energy efficiency programs. The resulting demand created may encourage new service providers to set up shop or expand their current businesses into the energy efficiency arena. |
| Lack of availability of high efficiency products. | The Program will build on the existing strong relationships between the RCEA and local energy services providers and retail outlets to encourage them to offer the type of energy efficient equipment that qualifies for rebates under the statewide programs. In addition, RCEA will further foster the availability of energy efficient products by using its local businesses networks to make them aware of programs that offer rebates for energy efficient products and expanding the local demand for energy efficient equipment, thus encouraging local businesses to provide greater “shelf space” for these products. |
| Lack of a viable and competitive set of providers of energy efficiency services in the market. Due its remote location and struggling economy, this challenge is particularly acute in Humboldt County. The RCEA conducted a survey of local business that offer energy efficiency services. There are only three consultants that offer various Title 24 consulting services, and other than retail outlets, only one firm that specializes in efficiency products. (The closest Home Depot is in Redding, CA, nearly 2 hours driving distance). | This program will support local contractors, suppliers and retail stores that can offer energy efficiency services by providing them with advertising and promotion support and creating a ready market in which to offer their services, along with a rebate and information infrastructure that fosters customer interest in energy efficiency services. |

### Basis for Evaluation of this Program

This program is an information program, therefore the proposal should be evaluated as an information program per the criteria description in D.03-08-067, p. 27.

## C.	Program Objectives

The Redwood Coast Regional Comprehensive Energy Information Program is designed to provide a comprehensive portfolio of energy efficiency information and education for Humboldt County, including:

(  Redwood Coast Regional Energy Center, which will incorporate components and program offerings normally provided for in various education and training programs, Building Operators Certification Training and local focus and access to statewide Emerging Technologies efforts.

- Public Sector Codes and Standards, and Emerging Technologies which will leverage other information programs to the benefit of this hard-to-reach market.

The objectives, primary tasks, milestones, marketing, coordination and other specifics of each of these two program components is described in the following sections.

The objectives of the Redwood Coast Regional Comprehensive Energy Information Program are to:

- Significantly increase the availability of information and education programs to all market segments in Humboldt County to produce a marked increased participation in the installation of energy efficient equipment through various statewide programs that will deliver long term savings and peak demand reduction.

- Provide Humboldt County’s hard-to-reach customers with quality information about energy use in their homes and facilities.

- Overcome the identified market barriers that are information-related and are described in Section C.

- Enable and encourage customers to make informed decisions to change energy use and practices.

- Significantly leveraging the RCEA institutional strengths in gaining access to local resources and serving specific local needs to increase the overall cost-effectiveness of resources PGC-EE resources spent in Humboldt County.

- Leverage the RCEA institutional strengths and commitment to energy efficiency to develop local policies, ordinances and incentives that maximize the potential for local governments to enable energy efficiency market transformation

# Section II.	Program Process

## A.	Program Implementation

Redwood Coast Regional Comprehensive Energy Information Program- Program Implementation

This primary component of the Redwood Coast Comprehensive Energy Information Program is the Redwood Coast Energy Resource Center (RCERC), which is composed of a centrally-located facility and professional staff that will provide a central clearinghouse for energy efficiency information and resources for residents, businesses.  The costs for this resource will be kept very low by using either the facilities of a RCEA member agency (e.g. the County of Humboldt), sharing space with a local strategic partner (e.g. the Regional Economic Development Agency), or the least preferred option of subleasing space in a suitable facility.   The RCERC will include a workstation available for its consultants and more importantly, for other program providers that are working in the region on a short-term basis.  The RCERC will also make its conferencing and training room facilities available to other program providers on available basis.

How This Program Improves on the Existing Approach

The RCERC is innovative in that it provides a very low cost means to deliver a wide range of information directly to the heart of a hard-to-reach market.  It takes the message of energy efficiency directly to the people and the businesses of Humboldt County.  Additionally, the approach has the following advantages over existing approaches to information programs:

- The Pacific Energy Center and other information sources are located in the San Francisco Bay area and it is not likely that consumers from remote Humboldt County would have the opportunity to drive 5 ½ hours to visit the facility.

- Offers the customer expanded assistance, including:

  - Directly tying the information resource to implementation programs  (either PG&E’s, other providers or the companion Redwood Coast Non-Residential or Residential Programs)

  - Providing assistance with identifying an approved contractor or vendor to accomplish any required work

  - Providing assistance to identifying financing for the project (e.g. banks that offer energy efficiency loans, SBA loans for businesses, etc.)

Training classes and seminars will be offered based on the specific needs of the customers in the Humboldt County area, including design/build firms, engineers and architects working on commercial properties.  The RCEA will partner with PG&E to provide technical and training resources the greatest extent possible in order to not duplicate successful programs that are already available.  Topics of seminars and workshops will include Commercial and Industrial Lighting, HVAC for Commercial Facilities, building envelope designs, day lighting, Motors/Adjustable Speed Drives, Energy Efficient Refrigeration, Motors (Water Pumping Applications), Lighting Fundamentals,  Groundwater Wells & Pumps, Residential and Non-residential Title 24 Compliance, Residential HVAC Quality Installation, Compressors/Air Leak Certification, HVAC Sizing and Duct Design, and Energy Efficiency Strategies for Schools.

Primary Task and Milestones

The following will be accomplished as part of this program element:

- Completion of the formation of the Energy Resource Center.

- Establish an RCERC “customer hotline” and customer resolution tracking system.

- Develop a comprehensive training and seminar plan based on the specific needs of the region.

- Meet with PG&E and other program implementer representatives (including the CEC, DOE) to assess available information and training materials that can be imported into the RCERC.

- Identify those specific resources that would be needed to be developed to support the RCERC events (e.g. collaterals, training courses, etc.).

- Launch the RCERA with an opening event.

- Commence training schedule and conduct training and information sessions on a regular basis.

Goals

- Conduct at least 4 training sessions for the public sector, 6 sessions for businesses, and at least 4 events for residential customers.

- Promote RCERC resources and energy efficiency information at 12 community events or more.

- Provide and initial response to every customer inquiry within 48 hours.

- Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent).

Customer Description and Enrollment

The program targets all PG&E electric or natural gas customers, with an emphasis on hard-to-reach audiences of low-income, seniors, renters and non-English speaking audiences of diverse ethnic backgrounds.

Enrollment for programs will be accomplished through various means, including email, phone and fax to the RCEA offices.

Building Operator Certification and Training

Although the Building Operator Certification (BOC) and Training program is a uniform statewide program administered by the IOUs, this program seeks to incorporate one certification class to be hosted at one of the local colleges (College of the Redwoods, or Humboldt State University).

Emerging Technologies

- The Emerging Technologies (ET) program is incorporated in this program because existing Emerging Technologies efforts to date have struggled to have strong connection and relevance for the hard-to-reach markets.  This direct link of the ET efforts to a hard-to-reach rural market will serve to improve the overall ET efforts to ensure they are not serving just the needs of the urban core customers, but the broader customer spectrum.

As part of this limited effort, the RCEA proposes the following:

- An RCEA staff (or RCEA consultant) is given a seat on the Emerging Technologies Coordinating Council (ETCC).  The purpose of this position would to:

  - Explore the viability of a future demonstration of one or more technologies that specifically deliver value to the rural, hard-to-reach customer.

  - Help provide a needed non-utility perspective to the ETCC activities.

  - Help the ETCC design information delivery mechanisms for the results that emerge from the technology demonstrations that penetrate the hard-to-reach market segments. Facilities managers in Humboldt County are as interested in new technologies as those in the core of the City of San Francisco.

How This Program Improves on the Existing Approach

To date, most of the information and results of the Emerging Technology efforts have been retained within the utility working group and staff.  This program will specifically work with the ETCC, the CEC PIER Program, DOE and other resources to assist in identifying emerging technologies that would be most beneficial to various hard-to-reach market actors (e.g. for Humboldt County timber and dairy).

Energy Policies, Codes & Standards Program Element

Objectives

This objective of this program element will be a targeted information program element to assist all RCEA member agencies to develop energy-efficient policies, practices and procedures that support the use of energy efficient building practices in its own buildings as well as those built within their respective communities.  Policies may include any or all of the following:

- All public agency buildings that are built new or undergo retrofit will be designed such that they qualify for Energy Star Building certification and qualify for utility and other program criteria (e.g. Savings by Design), and incorporate high-performance technologies that have a payback of 5 years or less.

- All commercial and residential new construction of retrofits will be strongly encouraged to qualify for Energy Star building certification and qualify for utility and other program criteria (e.g. Savings by Design).

- All RCEA member agencies will purchase Energy Star appliance when available and when they are shown to have an incremental cost payback period of 3 years or less.

In addition, this task will target the appropriate market actors by working with local permitting officials, designers, builders, and energy consultants to provide training on how to best meet the expanded criteria of the 2005 Title 24 Standards.  Close coordination will occur with industry participants that are involved in Title 24 compliance, including Title 24 consultants, engineers and architects.  In addition, RCEA will work with PG&E to identify specific codes and standards enhancement work of interest to Humboldt County, including special training seminars on application of the new 2005 Title 24 guidelines.

Primary Task and Milestones

- Develop draft policies for local government adoption

- Local governments adopt policies

- Develop and conduct Title 24 training for local permitting officials, designers, builders, energy consultants

Goals

- Have at least 75 percent of the RCEA member agencies adopt the policies as described above.  Additionally, reach out to other agencies that are not members (e.g. schools, special districts), to have them adopt the same policies.

- Conduct at least one Title 24 training session for permitting officials and one session for local industry stakeholders (e.g. Title 24 consultants, engineers and architects).

Customer Description and Enrollment

The participants in this program element will be the RCEA member agencies, as well as other public agencies on a voluntary basis.

Contractor Support

The RCEA will use either PG&E technical staff for Title 24 training, or retain a qualified expert from the California Association of Building Energy Consultants (CABEC).

Public Housing Program Element

Objectives

The RCEA will work with Heschong Mahone Group (if the program funded) to work with local Housing Authorities to develop and evaluate a two-tiered utility allowance schedule that reflects the lower costs of operating energy efficient homes.  The goal is to overcome the significant barriers that low-Income developers and owners face during the rehabilitation of low-income housing.  The program provides the means for developers to design and build more efficient homes by enabling the developer's to recover their investment more quickly, lower the monthly expense burden to the tenants, and pay off the housing authority's loans more quickly.

The program also bridges the split-incentive gap between owners and tenants.  The utility expenses for the tenants decrease slightly more than the utility allowance thereby enhancing tenants' ability to cover their monthly expenses.

Goals

Develop a two-tiered utility allowance in as many local housing authorities as possible (as least one).

## B.	Marketing Plan

Marketing and Outreach

Marketing and outreach for the education and information programs will be accomplished by the RCEA through newspaper articles, ads, mail inserts, newsletter articles with industry partners (e.g. Chambers of Commerce), an RCEA newsletter delivered via direct email and through local jurisdiction bill inserts (e.g. water bills).  Events will be listed on all local events calendars, including that of the local RCEA cities, libraries, and various electronic media like the HumGuide (http://www.humguide.com/), and the Humboldt County Economic Development Division Events & Notices page on their web site.  The RCERC will also take a travel display of information on the road to community events, including:

- Humboldt County Fair (over 70,000 attended in 2002)

- City of Arcata Taste of the Holidays event

- Arcata Bay Oyster Festival

- Arcata Folk Dance Festival

- Autumn Vintage (Annual wine auction fundraiser for College of the Redwoods).

- Avenue of the Giants Marathon & 10k Run (Annual marathon through Humboldt Redwoods State Park).

- Bebop and Brew (Annual Jazz and Micro Brew tasting event to benefit the Arcata Foundation)

- Bikes By The Bay event

- Blues by the Bay (Annual blues festival on the Eureka waterfront, held by Redwood Coast Music Festivals).

- Buddy Brown Blues Festival (Benefit concert for the Blue Lake Volunteer Fire Department).

- Fortuna Redwood Autorama

- Fortuna Rodeo

- Humboldt International Film Festival

- Humboldt Tri-Kids Triathalon

- Kinetic Sculpture Race

- Mountain Music Festival

- North Country Fair

- Paddle to the Headwaters Canoe Marathon

- Redwood Coast Dixieland Jazz Festival

- Redwood Run

- Reggae on the River

- Tech Expo 2001

- Tour of the Unknown Coast

The newspapers to be targeted for articles and some advertising will include:

- Arcata Eye.  A weekly newspaper covering the cities of Arcata and Blue Lake.

- Eureka Reporter.  An online newspaper for Eureka and environs.

- Eureka Times-Standard: Daily newspaper covering Humboldt County, based in Eureka.

- McKinleyville Press: A weekly community newspaper serving the communities of McKinleyville, Fieldbrook, Westhaven, Trinidad, Big Lagoon and Orick.

- Merge Media. HSU's mass media department merging the Lumberjack with other projects.

- Myers Flat News. Semi-monthly news from Myers Flat.

- North Coast Journal. Weekly magazine of north coast politics, people, and art. Based in Arcata.

- Rio Dell-Scotia News. A monthly Chamber of Commerce newsletter that supports local business and community enterprise.

- Senior News. Monthly news and features of concern to the senior community in Humboldt and Del Norte County. Based in Eureka.

Coordination with Other Entities

In order to minimize overlapping messages and to minimize costs, close coordination will be accomplished with all parties offering information and education components, including PG&E, other non-IOU providers of education and information services, as well as the significant amount of resources available through the California Energy Commission and the Department of Energy.  To the extent that the RCERC can import training and seminars from PG&E, it will.  If PG&E does not offer a particular topic or their resources are not available, the RCREA will make arrangements to develop and conduct the training with a local resource or another qualified instructor, including DOE resources that are available through the RCEA’s recent partnership through the Rebuild America Program.  The RCERC will also seek to collaborate with local colleges and universities, and manufacturers and vendors of energy efficient equipment and services.

Contractor Support

Contractor support will be provided for development of the RCERC, development of the customer feedback system, RCERC employee training, and development of a customer inquiry referral database, development of information and training programs, as well as materials design and printing.  The RCERC will also call on various subject matter experts from utility and non-utility entities to provide instruction and/or consultation for seminars, displays, demonstrations, and printed information provided to customers.

Exhibits and Displays

The RCERC will not commit a large amount of resources on “bricks and mortar” and sophisticated exhibits and displays, but will focus its resources on deploying relatively low cost, yet highly professional quality static information displays that “take the message to the people.”  For example, the opportunities for retrofitting older homes will be highlighted in an eye-catching poster-sized display that will promote a respective program or upcoming seminars.  These displays will be constantly be prominently displayed throughout the region at places where people frequent, like food stores, malls, hardware stores and retail outlets.  In some cases, the RCERC may work with a vendor to showcase equipment and demonstrating technologies for specific applications that consumers can go see during normal working hours (e.g. high-efficiency lighting retrofit at a Kinko’s location, or seasonal displays of energy efficient equipment at hardware stores).  Although the RCERC will be lightly staffed with personnel working other programs, they will have a comprehensive knowledge of where to go for any particular issue or question.  If an answer cannot be found in-house, the RCERC will have a comprehensive database of contacts and resources to refer customers to.  Each customer that contacts the RCERC will be given or mailed a feedback card in 2 weeks to ensure that their needs were met and to request if they need additional assistance taking the “next step.”  The primary means of customer contact will be in person, by phone, and by e-mail.

The RCERC will also be an excellent platform for local promotion of other public-good energy programs, such as the Self-Generation Program.

###### Marketing and Outreach

The RCERC will use a wide range of methods to market its service, including:

- Flyers used to market specific seminars to targeted markets;

- Inserts in member agency water bills;

- Descriptions of the technical centers, exhibits and demonstration capabilities are detailed on the Web site.

- A general information brochure that briefly describes all the services available at the RCERC.

- The RCERC facilities will be made available to customers as a venue for their own meetings in order to provide exposure to the information in the centers.

- A local marketing specialist will be retained to assist in the development and execution of the final marketing plan, but activities to be considered include:

- Program promotion through mailing to all businesses and residents in collaboration with distributing water bill sand other mass mailings.

- Local runs of Flex Your Power public service announcements and radio with references to RCEA promotional campaigns and information programs.

## C.	Customer Enrollment

Customers will be enrolled by a variety of methods.  In order to best utilize the existing resources of PG&E, customers will be given the option to call a toll-free phone number or access the PG&E’s web site to participate in the statewide programs (Express Efficiency, SPC, single family and multi-family rebates and audits, etc.).  In addition, a local phone number will be provided for customers that prefer a local contact.  Inquiries received by either PG&E or the RCEA will be received, then appropriate action taken, including:

- Pre-qualifying customer to ensure the customer’s needs are aligned with the most appropriate program.

- Mailing program information.

Both PG&E and the RCEA will share all inquiry information that comes from customers in Humboldt County to best coordinate the required follow-up actions to be taken, recognizing in some cases, interaction directly with PG&E would be most efficient and appropriate (e.g. in the case where the decision to proceed has been made and the project is moving into the rebate stage), whereas some customers may need extra attention that can be best provided by the local RCEA staff resources to ensure that the project does not become a lost opportunity.

## D.	Materials

This program will produce high quality information materials.  If there is an opportunity to co-brand existing PG&E information to reduce costs, then this approach will be pursued to further reduce costs.

## E.	Payment of Incentives

As an information only program, there will be no incentives paid to customers.

## F.	Staff and Subcontractor Responsibilities

RCEA staff will have primary responsibility for implementation of program to include marketing and outreach, promotion, collateral material.

Table 2 describes the relative roles and responsibilities of RCEA and PG&E staff and subcontractors.

Table 2: Staff and Contractor Responsibilities

| Staff or Consultant | Role/Responsibility | Level of Effort |
| --- | --- | --- |
| RCEA Program Director | Overall coordination of RCEA-PG&E partnership | 1.0 FTE |
| RCEA Project Manager | Day-to-day operations and project management activities | 0.5 FTE |
| RCEA Administrative Assistant | Day-to-day administrative issues | 0.5 FTE |
| Local Government Commission | Assistance with working with public agencies to incorporate energy policies, outreach and | As needed to augment RCEA capabilities |
| Consultants |  | As needed to augment RCEA capabilities |

## G.	Work Plan and Timeline for Program Implementation

Table 3 outlines the work plan and timeline for accomplishment of major program objectives.

# Section III.	Customer Description

## A.	Customer Description

All residential and non residential customers in Humboldt County who pay the PGC for energy efficiency qualify for this program.

This program seeks to serve all energy consumers in Humboldt County.  By virtue of the remote rural geography, all customers are defined as hard-to-reach (HTR).  This program addresses all market segments including Agricultural, Commercial, Industrial, Government, Residential – multi-family, Residential – single-family, Institutional, Schools and New Construction.

The proposed program, in its entirety, addresses a significant hard-to-reach market, as follows:

### Geographic Barrier

By virtue of its remote, rural geographic location, the entire area served by RCEA (Humboldt County) is defined as hard-to-reach.  Humboldt County is at the northern most tip of PG&E’s service territory.  The distance from PG&E’s Pacific Energy Center to City of Eureka is approximately 270 miles- over 5 ½ hours driving time (Source: Mapquest.com).

### Business Size Barrier

The program is designed to address a very high number of hard-to-reach very small public sector customers and businesses.  As can be seen in Table 4, a very high percentage of businesses in Humboldt County are defined as hard-to-reach from the business size criteria.

Table 4

This program seeks to serve all energy consumers in Humboldt County.  By virtue of the remote rural geography, all customers are defined as hard-to-reach (HTR).  This program addresses all market segments including Agricultural, Commercial, Industrial, Government, Residential – multi-family, Residential – single-family, Institutional, Schools and New Construction.

## B.	Customer Eligibility

To be eligible, participants must be a PG&E customers.

## C.	Customer Complaint Resolution

The RCEA will respond to all questions and/or complaints within three working days. Complaints will be recorded in writing and handled by the RCEA Program Director.

If a customer has a question, concern or dispute that relates to statewide program policies, rules or procedures, a program representative will evaluate the issue and seek to resolve the dispute consistent with program rules, policies and procedures.

Complaints that involve another energy efficiency provider (e.g. a complaint related to a statewide programs will be handled by PG&E.  PG&E will inform RCEA as to the final resolution of all complaints.)

Complaints that involve RCEA activities that require resolution will be discussed by all involved parties in order to identify a mutually agreeable solution and an acceptable timeframe for resolution.  If parties cannot agree on a solution and/or an acceptable timeframe, the dispute will be handled by an independent dispute mediation firm within 30 days of the failure to agree.

If a customer has a dispute relating to work performed by a licensed contractor, the program will refer the customer to the Contractor State Licensing Board.  If a customer has a dispute relating to work performed by a non-licensed contractor, the program will recommend that the customer work directly with the contractor to resolve the dispute.

## D.	Geographic Area

This program targets Humboldt County and the Cities of Arcata, Blue Lake, Eureka, Fortuna, and Rio Dell as shown in Figure 1.   Humboldt County is bound on the north by Del Norte County; on the east by Siskiyou and Trinity counties; on the south by Mendocino County and on the west by the Pacific Ocean. The County encompasses 2.3 million acres, 80 percent of which is forestlands, protected redwoods and recreation areas.  The January 1999 population of Humboldt County was 128,100, according to the State Department of Finance. The County has seven incorporated cities ranging in size from approximately 400 to 35,000 persons. Approximately half of the County’s residents live in incorporated communities, while 59 percent of the County lives in the area surrounding Humboldt Bay. According to the State Department of Finance, the cities of Eureka and Arcata together contain about 35 percent of the County’s population, while 13 percent of the population is scattered among five other incorporated cities (Blue Lake, 1,250; Ferndale, 1,300; Fortuna, 10,250; Rio Dell 2,960; and Trinidad, 360). Approximately 67,700 of County residents reside in unincorporated communities.

In terms of regional population trends, the chief growth areas of the County are around the unincorporated communities of McKinleyville and Garberville, and the cities of Arcata and Fortuna. Most of these regions have an adequate supply of land and necessary public facilities for urban use and can, therefore, be expected to remain as principal growth areas, respectively. Table 5 details County population projections over the next two decades, including estimates for several of the incorporated areas.

| Table 5: County Population Forecasted Changes |
| --- |
| Location | 1998 Population | 2010 Population | 2020 Population |
| Eureka | 27,750 | 28,870 | 29,830 |
| Arcata | 16,330 | 18,180 | 20,000 |
| Fortuna | 10,140 | 12,560 | 15,000 |
| Humboldt County | 124,000 | 131,600 | 140,000 |
| Unincorporated | 67,400 | 67,800 | 68,140 |

The proposed program supports the overall California grid reliability in that Humboldt County has been identified by the California Independent System Operator (CA-ISO) as a region of concern due to congestion of the transmission system, as well as the potential for stability, voltage collapse, and thermal overload issues.  These problems are further compounded by the reduced level of availability of the area generation due to age, generator maintenance outages, and potential shortages or limitations of fuel (i.e. natural gas, oil, wood chip fuels).

# Section IV.	Measure and Activity Descriptions

## A.	Energy Savings Assumptions

Pursuant to the Commission’s approved Energy Efficiency Policy Manual, this proposal is for an information-only program is not expected to provide an estimate of energy savings.  The program is anticipated, however, to deliver energy savings as a result of the increased access to information and resources in this traditional hard-to-reach market.  To the extent that it is possible through customer feedback mechanism, the RCERC will track the subsequent activities of customers that attend seminars, events and call-in to ascertain a) if the took and actions as a result of information provided by the RCERC, b) if not, why not (for feedback to future programs), and c) if they did, estimate of energy savings and would they believe they would have taken this action without the information and intervention of the RCERC.  This information may provide the ability to estimate resulting savings as a result of information and education campaigns as part of future energy efficiency information programs.

## B.	Deviations in Standard Cost-effectiveness Values

Based upon the Commission’s approved Energy Efficiency Policy Manual, this information program implementation plan is not expected to provide energy savings targets.

## C.	Rebate Amounts

There are not rebates associated with this program.

.

## D.	Activities Description

Not applicable.

# Section V.	Goals

A summary of this programs goals include the following:

- Conduct at least 4 training sessions for the public sector, 6 sessions for businesses, and at least 4 events for residential customers.

- Promote RCERC resources and energy efficiency information at 12 community events or more.

- Provide and initial response to every customer inquiry within 48 hours.

- Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent).

- Have at least 75 percent of the RCEA member agencies adopt the policies as described above.  Additionally, reach out to other agencies that are not members (e.g. schools, special districts), to have them adopt the same policies.

- Conduct at least one Title 24 training session for permitting officials and one session for local industry stakeholders (e.g. Title 24 consultants, engineers and architects).

- Develop a two-tiered utility allowance in as many local housing authorities as possible (as least one).

# Section VI.	Evaluation, Measurement and Verification (EM&V)

This EM&V plan is based on the Commission’s objectives as outlined in the Energy Efficiency Policy Manual (EE Policy Manual) and adheres to the guidelines in the International Performance Measurement and Verification Protocol (IPMVP).

The proposed evaluation of the program’s success will primarily be to provide measurable and quantifiable results in the form of achieved levels of energy and peak demand savings by the program.  The success of the program is also gauged by other program evaluation studies, such as process evaluation and market assessment and customer behavior analysis studies. Such studies provide (a) ongoing feedback and corrective guidance regarding program implementation and delivery to customers through program process evaluation, and (b) measured indicators of the program effectiveness through analysis of baseline conditions and customer’s satisfaction.

To comply with the objectives of the Commission for ongoing assessment and improvement of programs, the EM&V plan will also focus on process issues. The plan may also include 1) analysis of program accomplishments: 2) analysis of program design, delivery and implementation with recommendations for program enhancements; 3) an assessment of program targeting and customer satisfaction; 4) an analysis of incentive levels and options, if any, and 5) additional market assessment and evaluation as needed. More specifically, these activities may be done as follows:

Market Assessment and Customer Behavior Analyses:  Market saturation/potential studies from statewide studies currently underway will inform the market assessment and baseline analysis to assist with future program activities.  These activities assist with assessing customer awareness, behaviors and practices given their participation in the program.

Process Evaluations: These activities may include evaluations of program delivery in terms of timeliness and customer satisfaction.  The objectives of these activities will be to provide feedback to the program implementers on elements of the program that can be improved to enhance the program’s performance. Assessing performance of various delivery aspects of the program will help to identify specific, actionable servicing actions to make the program more effective, including statewide integration between the investor-owned utilities, and with other implementers of California programs, as appropriate to improve program delivery.

### Budget and Potential EM&V Contractors:

### The program will allocate approximated 5 percent of the contract amount to EM&V activities.

Potential EM&V Contractors

The abbreviated list of contractors proposed below can objectively evaluate program success and have performed work that includes impact evaluation, measurement and evaluation, measurement and verification, process evaluation, market assessment and verification of program accomplishments.  These are firms that have a proven track record of completing high quality, objective evaluations of energy efficiency programs either for the California investor-owned utilities or for other entities.  As stated earlier, this list is not inclusive of all the qualified evaluators who could objectively evaluate programs. The final list of evaluation consultants will be based on several factors including: future Commission decisions, the mix of approved programs and the experience of the evaluation consultants.

ADM Associates, Inc

Aloha Systems

Alternative Energy Systems Consulting (AESC)

Applied Management Sciences Group

Architectural Energy Corporation

ASW Engineering Management

Aspen Systems Corporation

EcoNorthwest

Energy & Environmental Economics

Energy Market Innovations

Equipoise Consulting

Freeman Sullivan

Frontier Associates

GDS Associates

Global Energy Partners

Heschong Mahone Group

ICF Consulting

Itron (RER)

KEMA-Xenergy, Inc.

KVDR Consulting

Megdal & Associates

Nextant

Opinion Dynamics

P.A. Consulting, Inc.

Quantec LLC

Quantum Consulting, Inc

Research into Action, Inc.

Ridge & Associates

RLW Analytics, Inc.

Robert Mowris & Associates

SBW Engineering

Science Applications International, Corp (SAIC)

Skumatz Economic Research Associates (SERA)

Summit Blue Consulting

TechMRKT Works

Vanward Consulting

Wirtshafter Associates

Sisson and Associates

# Section VII.	Qualifications

## A.	Primary Implementer

The RCEA Board, staff and consultants are well qualified to carry out this program in a timely and cost-effective manner.  Details of the program team member’s qualifications and experience are found in the following Sections, however, a summary of the respective strengths and key program contribution of the primary partners are found in Table 6.

| Table 6: Strengths of the Program Implementer and Identified Areas for Augmenting the RCEA’s Capabilities |
| --- |
| Quality or Strength |  |
|  | RCEA Staff and Resources Capabilities | Need for Augmenting RCEA Capability with Other Resources (contractors or PG&E (Note 1)) |
| Strong commitment of community leaders and local government institutions to energy efficiency through the charter of the RCEA | ((((( | No |
| Close knowledge of customer data, including local demographics, building size, age, type, ownership, energy consumption, etc. | ((((( | Yes (Note 2) |
| Talented and committed staff | ((((( | No |
| Experience in program design, operations, delivery and best practices | (( (Note 3) | Yes (Note 3) |
| Close relationship and communication channels with an extensive community-based network of resources and stakeholders | (((( | No |
| Deep understanding of the unique local needs and challenges of customers in the RCEA territory, including program and policy objectives and preferred implementation strategies. | ((( | Yes (Note 3) |
| Knowledge of the Humboldt County’s unique needs and challenges. | ((((( | No |
| Comprehensive portfolio of energy programs targeting residential and business sectors. | This program proposes to fill this need | No |
| Ability to align end-use customer with project financing. | ((( | No |
| Ability to assist in identifying and selecting contractors to complete projects. | ((( | No |
| Existing program infrastructure for inspections, rebate processing, tracking and reporting. | ( | Yes (Note 1) |
| Technical analysis capabilities including cost-effectiveness calculations, saturation and market potential studies and analysis of savings from various measures in different operating environments. | ( (Note 3) | Yes (Note 1) |
| Expertise in appropriate technology application and deployment. | ((( (Note 3) | No |
| Training courses for city staff such as designers, plan reviewers and building inspectors as well as for contractors, building owners and operators and large customers, including hands-on training | ( | Yes (Note 1) |
| Notes PG&E management has committed to seek partnering and collaboration opportunities with any RCEA programs ultimately approved by the Commission to the fullest extent possible. Examples of this collaboration include sharing training and information resources. If PG&E did not provide this information, additional costs will be required. Particularly important will be data on electricity and gas consumption by customer SIC code; transmission and distribution pinch points, ability to identify customers with high electricity use and records of past program participation. The RCEA will consult recent statewide penetration studies and would require access to any local data that was collected. Primarily through its retained expert consultants. |

Roles and Responsibilities of Each Team Member

The RCEA will administer all aspects of the program including management and coordination of subcontractors.  Detailed roles and responsibilities of RCEA staff, contractors and what would be anticipated to be handled by PG&E are outlined in Table 7.

Table 7: Key Personnel Roles and Responsibilities

| Team Member | Roles and Responsibilities |
| --- | --- |
| RCEA Board of Directors | Overall responsibility for the hiring and performance of the RCEA staff and operations. |
| RCEA Staff | Program management and day-to-day implementation |
| Consultants | Assistance to RCEA staff to augment capabilities where necessary. |
| PG&E | Collaborating with training and seminar resources from the Pacific Energy Center. |

## B.	Subcontractors.

Local Government Commission

The Local Government Commission (LGC) is a nonprofit, nonpartisan, membership organization that provides inspiration, technical assistance, and networking to local elected officials and other dedicated community leaders who are working to create healthy, walk able, and resource-efficient communities.  The LGC's membership is composed of local elected officials, city and county staff, planners, architects, and community leaders who are committed to making their communities more livable, prosperous, and resource-efficient.

Formed in 1979, the Local Government Commission's (LGC) original mission was to identify and implement local solutions to the energy crisis, based on conservation and the use of renewable resources. Accordingly, the LGC produced numerous energy policy documents, followed by conferences for elected officials and workshops for government staff and citizens.

More recently, the LGC worked under contract with the CEC to develop energy efficiency guidelines for local governments to incorporate within their general plans and, in partnership with CEC, sponsored a series of workshops for local elected officials. Out of these efforts emerged the Energy Aware Planning Guide, a comprehensive policy handbook for local governments that outlines opportunities for energy conservation and addresses economic and environmental concerns for each. The LGC helped the CEC produce a second, follow up guidebook, Energy Aware Planning Guide: Energy Facilities.

The LGC was the lead on the effort to assist Humboldt and Ventura Counties establish Regional Energy Authority (REA) pilot projects. REAs are joint undertakings by California local governments to develop and implement comprehensive energy strategies and encourage conservation and energy efficiency. This program provides technical assistance to the communities in the counties to plan and establish an REA, and to build sustainable local infrastructure for delivering energy efficiency services.

K. J. Kammerer & Associates

Mr. Kammerer led the development of the San Diego Regional Energy Office (SDREO).  Responsible for all aspects of energy policy, planning, development, startup, fundraising and administration of over $75M of public-good energy programs for the San Diego region- the third largest county in California and the sixth largest metropolitan area in the U.S. (1998 to 2003).

Mr. Kammerer was the primary motivator and developer of the majority of programs now offered by the SDREO from 1998 through 2003.  These programs included the start-up of a highly successful San Diego Energy Technology and Training Center, a highly successful Cool Roofs Program that installed over 27 million square-feet of energy efficient roofs to customers throughout all of Southern California, and the highly successful San Diego Self Generation Program, which was designed to install over 8 MW of clean distributed generation per year.

Mr. Kammerer led the reorganization of SDREO in 2001 after completing a comprehensive evaluation of various structures, including Joint Powers Authority and an independent public benefit, not-for-profit Corporation.  Led the transition from the San Diego State University Foundation to establish an independent public benefit, non-profit corporation, including application with the Secretary of the State, By-Laws, instituting financial controls and reporting, human resources, etc.  Most recently led the San Diego Regional Policy Advisory Council (REPAC) in the analysis of more formal options, strategic planning and the development of operational plans for the proposed government-led San Diego Regional Energy Authority (currently under consideration by the San Diego Association of Governments).  This effort included initiatives including, among other initiatives, more comprehensive administration of public-good funds, Community Choice Aggregation under AB 117, and development of renewable and other energy projects financed by the REA.

Mr. Kammerer has a close working knowledge of the provisions of relevant legislation and regulatory proceedings including State of California Public Utilities Codes (Sections 381-384).  A party of record to all regulatory processes that are of interest to local governments and public agencies, particularly those that are related to the availability of public good energy funding (in particular, CPUC Rulemaking 01-08-028 and the recently proposed Order Instituting Rulemaking Regarding Implementation of Community Choice Aggregation under Assembly Bill (AB) 117 (Chapter 838, September 24, 2002).

Mr. Kammerer was a key author, and led the completion of the San Diego Regional Energy Infrastructure Study, a comprehensive supply and demand analysis for the San Diego region during the 2000-2001 energy crises.  In addition, was the primary author of the 2030 San Diego Regional Energy Strategy, adopted by SANDAG in June 2003.

Mr. Kammerer has an excellent working knowledge of local government and Council of Governments processes through my experience with the close SDREO-SANDAG relationship from 1998 through 2003.  This effort included frequent direct interaction and communications with all levels including Supervisors, City Council members, Directors, and staff, to incorporate the needs of SANDAG and its member agencies into SDREO plans.

Mr. Kammerer has active, close relationships with senior staff (and some Commissioners) of the California Energy Commission (CEC), the California Public Utilities Commission (CPUC), the California Power Authority (CPA), and the Department of Energy (DOE).

## C.	Resumes or Description of Experience

Kathy Jack

Interim Executive Director of the Redwood Coast Energy Authority

Kathy Jack received a Bachelor of Arts degree in Environmental Systems and Society, form Cornell University in 1993, and a Masters of Science degree from Humboldt State University (HSU), in Environmental Resources Engineering in 2003. At HSU, Ms. Jack researched “The Potential Carbon Dioxide Emissions Avoided by Grid-Connected Photovoltaic Systems in Arcata, California,” and instructed Appropriate Technology classes in the Engineering Department.

Ms. Jack has worked in Ecological Planning, and Building and Systems Design for over 10 years. She has studied and worked with leaders in the field of Green Building and Architecture, Solar Electric Systems Design, and Permaculture, in the United States, Australia, New Zealand, and Senegal.

Since November 2001, Jack has worked as the City of Arcata’s Energy Program Specialist, where she has worked to develop the City’s Energy Program, including community outreach, facilities management, and completion of the Community Greenhouse Gas Inventory.

Kathy Jack has served as the Interim Executive Director of the newly formed Redwood Coast Energy Authority (RCEA), since August of 2003.  In this capacity, she has worked with staff of the Local Government Commission and the RCEA Board of Directors to establish the RCEA as an official entity, including creating a budget, hiring staff and consultants, and launching strategic planning for program development. Projects initiated include a regional water and wastewater energy cost savings analysis, coordination of member agency facilities data, creation of cohesive regional resource centers for energy information, and establishing and obtaining funding for the RCEA Million Solar Roofs Partnership.

# Section VIII.	Budget

Below is a summary budget for the Program.

| Budget Item | Budget |
| --- | --- |
| Administrative Costs | $115,181 |
| Marketing/Advertising/Outreach | $206,240 |
| Direct Implementation | $592,248 |
| EM&V | $40.077 |
| Potential Performance Award | $66,762 |
| Total Budget | $953,746 |

# Footnotes

The Redwood Coast Energy Authority (RCEA) was formed in 2003 as a Joint Powers Association, representing seven municipalities (the Cities of Arcata, Blue Lake, Eureka, Ferndale, Fortuna, Trinidad and Rio Dell) and Humboldt County.  RCEA’s purpose is to develop and implement sustainable energy initiatives that reduce energy demand, increase energy efficiency, and advance the use of clean, efficient and renewable resources available in the region.

INTERIM OPINION SOLICITING 2004-2005 ENERGY EFFICIENCY PROGRAM PROPOSALS AND ADDRESSING SCOPE OF PROCEEDING dated August 21, 2003.

By virtue of its remote, rural geographic location, the entire area served by RCEA (Humboldt County) is defined as hard-to-reach.  Humboldt County is at the northern most tip of PG&E’s service territory, that covers over 70,000 square miles and extends from Eureka in the north, to Bakersfield in the south.  The distance from PG&E’s Pacific Energy Center to City of Eureka is approximately 270 miles, and over 5 ½ hours driving time (Source: Mapquest.com).

Energy Efficiency Policy Manual, Appendix C, page 41.

Estimated using the average per kilowatt-hour share of the utility’s Public Goods Charge energy efficiency program for PY004/PY2005.

Estimate based on total electricity consumption of Humboldt County as a proportion of the overall consumption of PG&E customers.

Humboldt County has eight power plants with the combined output capacity of 188 MW.  The largest plant is the 32 year old Humboldt Bay Power Plant owned and operated by PG&E.  46 percent of Humboldt Counties generation is renewable, with 4 biomass plants (83 MW), and two hydro plants (2.5 MW).  Humboldt Bay Nuclear Power Plant (Unit 3) was shut down in July 1976. (font)

California ISO 2003 Summer Assessment April 11, 2003.

Paraphrased comments of a member of the Humboldt County Economic Development Agency during a meeting of the Humboldt County Prosperity Network on September 5, 2003.

The modeling of the SDREO efforts has been accomplished through RCEA staff and consultant conversations with SDREO staff and retaining Kurt Kammerer, the former Executive Director of SDREO to assist the RCEA with program design, strategy and startup of operations.

There is a high degree of communication between local government program implementers.  Regular meeting are organized by the Local Government Commission where program implementers share lessons learned and best practices.  In addition, the RCEA has specifically retained consultants that have a background and expertise in local government energy efficiency programs.

Established in July of 2003, the Headwaters Fund Revolving Loan Fund provides loans to small businesses in Humboldt County through the Redwood Region Economic Development Commission (RREDC) and the Arcata Economic Development Corporation (AEDC). The purpose of these loans is to spur local business expansion to support job creation, retention and general economic development in Humboldt County.

The RCEA customer resolution tracking system will be established using a low-cost customer relationship management software system, pre-populated with public information from the County tax assessors office (e.g. on building location, owner, square footage, etc.) font

Humboldt County has eight power plants with the combined output capacity of 188 MW.  The largest plant is the 32 year old Humboldt Bay Power Plant owned and operated by PG&E.  46 percent of Humboldt Counties generation is renewable, with 4 biomass plants (83 MW), and two hydro plants (2.5 MW).  Humboldt Bay Nuclear Power Plant (Unit 3) was shut down in July 1976.

California ISO 2003 Summer Assessment April 11, 2003.

The RCEA Board of Directors consists of City of Arcata, Vice Mayor Constance E. Stewart, RCEA Chair; City of Blue Lake, Wiley Buck; City of Eureka, City Council Member Jeff Leonard; City of Ferndale, Mayor Larry Taubitz; City of Fortuna, City Council Member Dean Glaser  ; City of Rio Dell, City Manager Eli Naffah, City of Trinidad, Mayor Dean Heyenga; and Humboldt County, Supervisor John Woolley.

# Text boxes

Figure 1: Map of Geographic Area

Source: Humboldt State University INDEX OF ECONOMIC ACTIVITY FOR HUMBOLDT COUNTY August 2003 (http://www.humboldt.edu/~indexhum/current.htm)

Figure 1: Example of an RCERC Poster Displays