Supermarket Lighting Maintenance Program (SLiM)

##### PG&E Service Territory

Table of Contents

I.	Program Overview 	  1

A.	Program Concept 	  1

B.	Program Rationale 	  1

C.	Program Objectives 	  3

II.	Program Process 	  5

A.	Program Implementation 	  5

B.	Marketing Plan 	  5

C.	Customer Enrollment 	  5

D.	Materials 	  6

E.	Payment of Incentives 	  6

F.	Staff and Subcontractor Responsibilities 	  6

G.	Work Plan and Timeline for Program Implementation 	  7

#### III.	Customer Description 	  8

- Customer Description 	  8

- Customer Eligibility 	  8

- Customer Complaint Resolution 	 8

- Geographic Area 	 8

IV.	Measure and Activity Description 	 9

- Energy Savings Assumptions 	 9

- Deviations in Standard Cost-Effectiveness Values 	 10

- Rebate Amounts 	 11

- Activities Descriptions 	 11

### V.	Goals 	 12

VI.	Program Evaluation, Measurement, and Verification (EM&V) 	 13

A.	Proposed Evaluation Approach 	 13

B.	Potential EM&V Contractors 	 14

VII.	Qualifications 	 15

- Primary Implementer 	 15

- Subcontractors 	 15

- Resumes or Description of Experience 	 15

VIII.	Budget 	 16

Supermarket Lighting Maintenance Program (SLiM)

##### PG&E Service Territory

Section I.  Program Overview

A.  Program Concept

Lighting constitutes approximately one-third of the energy consumption of supermarkets and up to one-half of the consumption of retail stores without large food refrigeration loads.  The Supermarket Lighting Maintenance Program (SLiM) will provide professional assistance to supermarkets and other similar retail outlets to enable them to reduce lighting energy consumption by means of existing systems without capital expenditures.  For a variety of reasons, large retail stores waste huge amounts of energy either through over-lighting or by not properly controlling their lights.  This is true even in stores that have undergone efficiency retrofits such as installing electronic ballasts.  Through the SLiM Program, technicians will work closely with local, district, and corporate management to ascertain the way to operate the existing lighting system in order to maximize energy conservation without being obtrusive to customers.  The SLiM technicians will then implement that strategy through instruction of personnel, reprogramming of energy management systems, and minor electrical repairs as necessary.

B.  Program Rationale

Aloha Systems has conducted audits in a number of supermarkets and drug stores through the energy efficiency programs of municipal utilities.  In this process we found the opportunity for very significant energy conservation merely by fine-tuning existing lighting systems and their controls.  The supermarkets we audited had an average annual consumption of about 1,600,000 kWh, of which 500,000 kWh were used by the lighting system.  Drug stores and other stores without large refrigeration systems use less energy – approximately 700,000 kWh per year on average – but their lighting consumption is proportionately larger, averaging 360,000 kWh.  The savings potential we discovered, not including the savings that could be achieved through physical retrofits in those stores with old T12 lighting, averaged 78,000 kWh per year per store.  Less than 10% of the stores audited had no opportunity for energy savings through relatively minor “tune-up” work.

In general, the savings that can be achieved are accomplished through reduced lighting.  In some cases this is practical throughout the day and night.  In other cases it is practical during the late night hours.  Another means of achieving savings is by turning most of the lights off when the store is closed and no employees are present.

There is an entire array of problems that result in the lighting energy waste in stores.  In some cases we found an energy management system that was programmed to turn the lights off, but our interval metering demonstrated that the lights operated all night long.  In another case we found a store manager who thought the EMS shut the lights off around midnight after the store closed but the EMS was in fact programmed for continuous operation since the store had at one time operated on a 24 hour/day basis.  In one particularly interesting example, we found that a relay in a control panel had broken and an electrician had simply bypassed the relay, leaving that specific circuit of lights running in three-lamp mode when all the others operated in two-lamp mode.  Our measurements indicated that the failure to replace this $50 relay caused the store to waste 11,872 kWh per year by operating extra lights that were virtually indistinguishable from the sales floor when turned off.

We also discovered many situations where lighting control systems were hastily wired in a manner that inhibited their ability to provide reduced lighting while maintaining even and pleasing levels of sales floor illumination.  Many if not most store fixtures are wired in a three-phase pattern that theoretically enables 1/3 or 2/3 reduction in lighting in a very even pattern across the ceiling.  When done properly, this reduction can be implemented in a way that is virtually unnoticeable to shoppers in the store.  We discovered many situations where diligent control of the lighting system at the circuit breaker panel could implement such unobtrusive patterns, but operation of the automatic lighting system by using the “1/3” or “2/3” control buttons produced splotchy lighting levels throughout the store.  Many store managers used the reduction modes during the “energy crisis” but have since returned to 100% operation because of the system’s inability to easily achieve aesthetically pleasing light level reductions.  A few hours of careful rewiring in circuit breaker panels or control systems would eliminate this problem without requiring any new equipment.

Finally, we found that there is a general lack of awareness among local store management and employees regarding the costs of electricity and the dollar value of taking relatively easy steps such as turning off lights.  This causes a lack of appreciation for the benefits, which ultimately results in abandonment of conservation practices over the course of time.

The SLiM Program will address all of these issues and correct the problems.  The SLiM technicians will visit a store, determine the capabilities of its present lighting system, determine what it is now doing, and assess what more can be done to achieve greater energy savings.  They will make minor physical repairs or adjustments to facilitate reduction, such as rewiring the relays of a control system so the system’s 1/3-shutdown pattern is even and unobtrusive.  If manual controls are needed, the technicians will develop a lighting reduction strategy, clearly mark switches, and instruct employees on how and when to turn lights on and off.  At the same time, the technicians will tell the store employees how much money they will save by doing their conservation activities.

Likewise, the technicians will work closely with the local store management.  This way the managers can provide input regarding the lighting reduction plans and patterns that ultimately will be implemented.  Local management input is important because it will decrease the chance that overly aggressive lighting conservation would interfere with local managers’ perceived customer satisfaction.  It will also increase the persistence of the program because the managers and local staff will feel a sense of “ownership” with it.  One of the intrinsic problems with the centrally controlled energy management systems in chain stores is that local managers neither understand nor support them.  Since they don’t understand how the system is supposed to work, they don’t know when it malfunctions.  When they have no control over how the EMS is set up, they do not develop a positive sense of concern about it and are more likely to view it as a burden.

A final part of the SLiM Program will be regular follow-up.  In stores where automatic controls dominate the energy savings, we will follow up on an annual basis.  In stores where the energy savings are achieved mostly through manual action, we will follow up quarterly.  During the follow-up visits, the SLiM technicians will meet with store personnel to determine how the system is working, making changes if necessary, and provide a general reminder of the importance of energy conservation.  SLiM technicians as well as Aloha Systems senior staff will also occasionally attend the district managerial staff meetings in participating chain stores to make sure the regional management is also aware of the importance of energy conservation and the benefits that it achieves.

Hard-to-Reach.  The SLiM Program in the PG&E service territory will focus on stores located outside of the Metropolitan Bay Area.  Because some of these stores are geographically quite remote, they do not always receive much attention from corporate staffs.

C.  Program Objectives

The Supermarket Lighting Management Program will achieve energy savings and peak load reduction through optimized and effective control of lighting in supermarkets, drug stores, and similar large retail facilities.  Expert technicians will work closely with corporate and local store personnel to produce these savings through proper use of existing equipment, along with minor repairs when necessary.

At any individual store we will begin by assessing the store’s existing system and how it operates.  We will determine what the EMS says it does, what the local personnel think it does, what they want it to do, and what it really does (all of which may be different).  We will also assess its potential and what needs to be done to make it better.  This might involve minor rewiring, reprogramming, shutting off circuit breakers, and/or developing a written lighting turn-on/turn-off plan.

We will assess the energy savings potential of what we consider the optimal energy efficiency plan.  This assessment will be vital not only for the reporting and EM&V of the SLiM Program, but also for the store’s personnel to understand the value they receive from conservation and the benefits of the specific plans we have derived.  This information will be provided to the local staff as well as regional and corporate staff in a clearly understandable manner as an educational tool.

After a store has had its system optimized, we will return in one month to discuss it with the local personnel.  We will work with local managers to see if there are any difficulties or any changes that would be helpful.  We will make sure that automatic controls are still operating as set and that behavior-based plans such as night shut-down continue to be implemented.  Each store will also have an annual follow-up, and those stores that rely on people to effectively implement their conservation plans (such as turning off coded circuits each evening) will be checked on a quarterly basis, typically without announcement and perhaps without local staff even knowing they are being observed (since lighting patterns can be casually observed, many times even from the outside of the store.)  These visits would target the specific details of a particular store.  For example, if a store is closed and unoccupied in the early morning hours and its lights are supposed to be off, we could drive by during that time and observe through the windows that they are indeed off.  Problems could then be addressed, regardless of whether these problems were caused by staff’s lack of diligence or by equipment malfunction.

Education and conservation awareness will be an additional component of the SLiM Program.  During the course of the tune-up visits, the very nature of working closely with local management to implement a desirable strategy will impart a certain amount of valuable information regarding conservation.  For example, a discussion may take place regarding the actual dollars to be saved by turning off refrigerator case lights during night stocking hours.  Managers will then be able to see that this is not just a nuisance, but a valuable cost-saving activity.  Local stores will also be encouraged to have SLiM staff visit during one of their staff meetings to make brief presentations about energy conservation as well as answer any questions.  These discussions regarding energy use and conservation would not be limited strictly to lighting.  Many stores make simple food placement errors that can decrease the efficiency (and effectiveness) of the refrigeration systems, so a tangential amount of refrigeration conservation would be achieved through this informational presentation.

Additionally, information will be gathered in an informal manner regarding equipment and other improvements that would be beneficial to the store.  This would certainly be true of lighting.  (It is interesting to note that the major chains generally have a mix of stores with efficient and inefficient lighting systems, even in the same general location.)  Although a formal audit of the refrigeration and HVAC systems is not a component of the SLiM Program per se, the technicians will be working around and near these systems and will note any major situations in which conservation could be achieved.  This information would then be passed on to the corporate energy management personnel as part of our routine reporting.

Finally, for chain store participants there will be an educational component at the regional level and an informational component at the corporate level.  On a regular basis, senior Aloha staff will offer to meet with divisional managers and discuss the program’s progress.  Simply making presentations of the energy savings achieved in the participating store facilities will help them value conservation.  As with the staff interactions at the local store level, these regional meetings would also provide opportunities for interested general managers and district directors to learn more about saving energy.

Our objective is to provide SLiM services to 250 stores in the PG&E service territory.  This is a conservative estimate, and we believe that 300 store tune-ups may actually be achievable.  Obviously doing additional stores with the same budget would make the highly cost-effective program even more cost-effective.  If 300 stores are incorporated into the program, the TRC ratio raises to 4.6 from the 3.9 TRC of the present proposal.

A duplicate program is proposed for the SCE service territory.

Section II.  Program Process

A.  Program Implementation

The Supermarket Lighting Maintenance Program in the PG&E service territory will be implemented through Aloha Systems’ northern California office.  The program managers, technicians, and engineers will be Aloha Systems employees.  The SLiM Program will operate independently of any PG&E or other non-utility energy efficiency program.

The SLiM Program does not directly overlap with other energy efficiency programs because it essentially provides staffing support for commissioning and recommissioning of existing equipment.  However, the SLiM staff will be working very closely with the store personnel, including corporate energy managers. They will develop detailed knowledge of the lighting infrastructure of the stores, and to a lesser extent the HVAC and refrigeration equipment.  We know that some stores do not have energy-efficient lighting technologies, and the technicians will specifically inform corporate management of recommendations for lighting fixture retrofits.  As part of those recommendations, the report would include discussion of the applicability of other efficiency programs such as the statewide SPC and Express Efficiency programs.  SLiM participants, therefore, may be somewhat more likely to participate in such programs, although such participation would be for the installation of equipment, which is not covered under SLiM.  There could not be a “double-dipping” situation because SLiM does not cover new equipment and SPC and Express Efficiency do not cover the services offered through SLiM.

B.  Marketing Plan

Aloha Systems has or had working relationships with the corporate energy managers of some of the major chain stores.  We will market SLiM directly to the corporate managers responsible for energy management.  We believe that working with two or three major chain stores would enable us to have more than sufficient local stores to implement the program.  From our observations, all of the chain stores have individual facilities that could greatly benefit from SLiM participation.  We will attempt to include some smaller chains, as well as all of the major chains, in the program.

C.  Customer Enrollment

Customers will enroll by agreeing to participate after discussions with Aloha Systems regarding the program.  Most of the participating stores will probably be part of large corporations with many local facilities.  We anticipate significant interest from these chains, and we will sign up participating stores with a maximum of 50 stores per chain at any given time.  This will eliminate the chance for any one chain to gather all of the benefits.  After those 50 stores have been tuned up, we may add more stores from that chain if deemed appropriate.

The program is not technically limited to chain accounts.  Individual or small chain stores will certainly be welcomed and encouraged to participate.  We will attempt to reach some of the smaller store chains, although we do not plan concentrated direct marketing toward individual stores.  Although we hope for a diversity of customer participation, the single true goal of the program is saving energy through direct action, and our staffing efforts will be primarily expended toward that goal rather than extensive and difficult sales and marketing to individual accounts.  Any store that wishes to participate that has not been contacted may enroll by contacting us and signing up for participation.  The Aloha Systems website will also clearly describe the program and encourage individual store participation.  Because the number of participants is not rigidly fixed, we do not foresee the need to turn away a few individual non-chain stores even if they apply relatively late in the program and we are already committed to large chains provide SLiM to 250 sites.  These single-account customers will be welcomed to enroll.

D.  Materials

Only minor amounts of materials will be used in the project, as it relies on the recommissioning of existing equipment.

E.  Payment of Incentives

The SLiM Program will not use cash incentives paid directly to participants.  Rather, it will provide direct implementation of energy efficiency at no cost to the participants.

F.  Staff and Subcontractor Responsibilities

Aloha Systems is a licensed general and electrical contractor and will use its own full- and part-time employees to the extent possible.  We do not anticipate any need for subcontractors in this project.  Aloha staff will make minor repairs to electrical systems if needed.

Program Manager.  The SLiM program manager will be a full-time employee dedicated to the overall management of the program in the PG&E territory.  The program manager will be responsible for marketing, meeting with store management, master-scheduling of tune ups, answering questions from store personnel, developing educational materials, quality assurance, project follow-up, preparing reports, and all other routine managerial aspects of the program.

SLiM Technicians.  The primary work of the SLiM Program will be carried out by the electricians working in the store.  The two technicians will be dedicated full-time to the SLiM/PG&E program and will typically work together on a tune-up.  The work will include understanding lighting systems, their energy use, and conservation.  At some sites there may be work with the energy management system.  At some sites there may be minor electrical wiring work.  The SLiM technicians most likely will be hired specifically for this program, and we plan to build a team pair where one has primary experience as an electrician or in building trades and one has experience with computer or EMS systems.

Senior Technician.  One of Aloha’s senior technicians will be dedicated to the SLiM Program on a 50% basis.  He will be available to assist the SLiM project technicians on an as-needed basis and to assist with more complicated site projects.

Program Administration.  Administrative and clerical support will be required for program accounting and other central administrative functions.  We anticipate a 50% FTE clerical load.

Senior Engineering and Management.  Aloha’s senior engineering and management staff will be required to provide overall project coordination, quality assurance, technical training, and strategic design and review of project goals and objectives on both program-wide and district-level implementation.  Consistent with Aloha’s history, commitment to, and reputation of top-notch technical quality at all levels, senior management will be involved in the project on a routine basis, including project-wide meetings with the full SLiM staffs of both the SCE and PG&E programs and routine meetings with key personnel of major chain store participants.  Senior managers will also provide coordination with other programs, coordination with IOU and CPUC staff, and other functions as needed.  We anticipate a 50% FTE requirement for these functions from a combination of top Aloha personnel, including the regulatory reporting manager, senior executives, and senior engineers.

G.  Work Plan and Timeline for Program Implementation

| Activity | Quarters of 2004 | Quarters of 2005 |
| --- | --- | --- |
| Begin Project | x |  |  |  |  |  |  |  |
| Meeting Corporate Energy Mgrs | xxx |  |  |  |  |  |  |  |
| Specific training of engineer | xxxxx | xxx |  |  |  |  |  |  |
| On-Site work at Stores | xxx | xxxxxx | xxxxxx | xxxxxx | Xxxxxx | xxxxxx | xxxxxx |  |
| Follow-Up at Stores |  | xxxxxx | xxxxxx | xxxxxx | Xxxxxx | xxxxxx | xxxxxx | xxxxxx |
| Meet with Additional Managers |  | xxxxx |  |  | Xxxxx |  |  |  |
| Prepare First Year Assessment |  |  |  | xx | Xx |  |  |  |
| Assess Full Program Success |  |  |  |  |  |  | xxxxxx | xxxx |
| Assess 2006-07 Cont/Expansion |  |  |  |  |  |  | xxxxx | x |
| Prepare Final Report |  |  |  |  |  |  |  | xxxxxx |
| Publicize Results |  |  |  |  |  |  |  | xxx |

Section III.  Customer Description

A.  Customer Description

Medium and Large Commercial.  The customers are grocery stores, drug stores, and other similar retail outlets within the PG&E service territory.  They typically will range in size from 100 to 500 kW.  A smaller non-grocery store could have a demand slightly below 100 kW and a very large supermarket could have a demand in the 500-750 kW range.

Hard to Reach.  The primary focus will be on stores located in PG&E territory but outside of the Metropolitan Bay Area.  Some of these stores are quite geographically remote and have not had the level of attention from corporate management that urban stores receive.

B.  Customer Eligibility

The following eligibility criteria apply to the SLiM Program:

- All participants must be customers of Pacific Gas and Electric.

- Participants must have stores that have at least 20 kW of lighting load.

C.  Customer Complaint Resolution

Local store managers will be given the business cards and contact information of the technicians who work at their stores.  They will also be given an information sheet that describes the program and contains the names and contact information for senior Aloha Systems management.  The corporate energy managers of participating chain stores will also have this contact information.  If we receive a complaint, we will promptly contact and/or visit the complaining party to resolve the issue.

D.  Geographic Area

Participating stores will be located in the PG&E service territory and have sufficient lighting load to justify the work.  We will focus the project in Mendocino, Sonoma, Lake, Napa, Solano, and Yolo Counties.  As the project advances, participant stores in other counties may be included if necessary.

Section IV.  Measure and Activity Descriptions

A.  Energy Savings Assumptions

In order to estimate energy savings, we assessed the specific recommendations we made during recent energy audits of six grocery stores and six drug stores owned by two major chain store corporations and located in Burbank and Glendale, California.  These audits evaluated the energy use of the refrigeration, HVAC, and lighting systems in the stores.  Even though most (but not all) of the stores had already undergone lighting retrofits to install electronic-ballasted T8 lamps, all of them had significant opportunity to save more energy through lighting conservation.  In all but one store (which had inefficient HID lighting that could not easily be controlled), there were recommendations to better control the existing systems.

Based on the specific information for these stores, we developed general expectations for energy savings at other stores.  We started by averaging the savings of the eleven stores where recommendations for better lighting control were made.  (The store where no recommendations for control improvements were made was excluded from the average because stores that do not have opportunity for lighting control-based savings will not be included as SLiM participating sites.)  The details and specific values for the stores are included in the supplemental Excel spreadsheet.

A review of the spreadsheet details will show that there is a considerable difference in energy use of a supermarket and another type of retail outlet such as a drug store.  This is primarily a function of refrigeration systems, and secondarily a function of the slightly larger building size of a supermarket.  However, the lighting component of the consumption does not differ that much.  Interestingly, we often found greater savings opportunity in the smaller drug stores than the larger supermarkets.  There were a variety of reasons for this.  One major reason is that the large supermarkets appear to have received more attention from corporate staff than the smaller drug stores, which therefore had a higher percentage of inefficient lighting technologies remaining (and hence more opportunity to save by shutting off inefficient lights).  Another major reason is that drug stores are more likely to totally shut down during a portion of the night, yet lighting systems did not always turn off the lights (even in some cases where everyone thought they did).

The per-store energy values below represent the average of the eleven stores in this 2003 audit work:

Annual Energy Consumption	1,200,167 kWh

Annual Lighting Consumption	438,996 kWh

Energy Savings by Improved Lighting Control	78,259 kWh

Total Coincident Demand Reduction by Lighting Control	7.0 kW

The anticipated savings by using improved lighting control refers to the amount of savings we would anticipate making by actually implementing the type of strategies specifically planned for the SLiM Program – namely those measures that do not require fixture retrofits or installation of control equipment, but rather rely on minor repairs, reprogramming, and/or manual operations.  The maximum anticipated reduction in one store was 213,943 kWh/year in a drug store that was significantly over-lit.  The minimum anticipated reduction was 11,872 kWh/year in the otherwise well-controlled grocery store that had the relay bypass discussed previously in this proposal.

We have no reason to believe these stores are not typical of what will be encountered in the SLiM Program.  Furthermore, we will specifically target stores that are likely to achieve benefits.  Nonetheless, in order to be conservative in our preliminary evaluation of the program’s potential, we have reduced the average annual savings estimate per store by 20%.  This reduction will also account for some changes that may be energy-efficient and technically possible but undesirable by local managers for sales-based or other non-technical reasons.  Based upon this reduction, the savings values per store that we used in the evaluation spreadsheet are as follows:

Energy Savings per SLiM Participant	62,400 kWh

Coincident Peak Demand Reduction per Participant	5.6 kW

It is within reason to believe that overall program energy savings may be double the estimates contained in this proposal, particularly since we will be able to select stores from a large base of potential participants, whereas the twelve stores in the audit program represented 100% of the stores available for audits.

Of course, at each store visit the technicians will diligently document exactly what was found and what changes were made.  As any given store has its tune-up completed, we will have a very accurate estimate of the energy savings and demand reduction achieved at that store.  These values will then be able to be added to obtain the overall program energy savings and demand reduction.

B.  Deviations in Standard Cost-effectiveness Values

We have used the default net-to-gross ratio of 0.8 from the Energy Efficiency Policy Manual.  There is some validity to the argument that a net-to-gross ratio very close to 1.0 is appropriate because of our ability to select actual stores for participation.  It is true that some (though unfortunately very few) local store managers do take it upon themselves to implement plans similar to what we are doing in the SLiM Program.  However, these stores would be screened out early in the process and would not be counted toward the program’s participation goals.  The goal is 250 stores in which we do some sort of work.  This would not include stores where we walked in, talked to the store manager, saw the wonderful program he had done, and said “Congratulations, you did it all yourself.”

Incremental measure costs are zero because the service is provided free of charge to the participant.

We used a useful life of four years in order, once again, to be conservative.  The changes that comprise the tune-up at any given store may include a mix of measures with widely divergent useful lives.  Fixing a broken part could have a life of 20 years.  Telling employees to turn off the red dot circuit breakers every night at midnight might have a useful life of four months, and the dots themselves might stay on the panel for 5 to 10 years.  Reprogramming an automatic control system might last 20 years, but might only be relevant for five.  We are well aware of the potential for some very-short useful life measures, such as behaviors of store clerks turning off lights.  However, we specifically address this issue by including quarterly revisits for those sites.  The quarterly visits will place persistence clearly at two years, but we also believe that this repetitive focus on the issue will more greatly instill the behavior into the workforce at the store on a more permanent basis.  By the end of the two years, it will probably be routine enough to last another few years.

C.  Rebate Amounts

There are no rebates provided in this program.

D.  Activities Descriptions

Most of the activities of the SLiM Program will result in direct measurable savings through automatic or manual control of energy-using equipment.

There is a tangential educational result of the direct interaction between SLiM staff and local, regional, and corporate store personnel.

Section V.  Goals

The main project goal is to reduce the energy consumption of lights at large retail stores through manual and/or automatic reduction in lighting operation.  In some instances (those where lighting reduction during afternoon hours is implemented) there will also be a coincident peak demand savings achieved.

The following table provides the estimates of the overall energy-saving and demand reduction of the program along with its societal benefits:

Net Annual Energy Savings	12,480,000 kWh

Net Lifecycle Energy Savings	49,920,000 kWh

Net Coincident Peak Demand Reduction	1,120 kW

TRC Net Benefits	$2,170,912

TRC Ratio	3.8617

Section VI.  Program Evaluation, Measurement, and Verification (EM&V)

A.  Proposed Evaluation Approach

The energy savings estimates were based upon anticipated savings that could be achieved by implementing the SLiM Program at eleven specific stores for which we conducted energy audits.  We are very confident of the accuracy of these estimates for these particular stores.  We also consider these stores to be typical of the mix within the general California population.  However, we do not know this with certainty.  It is likely that much greater savings will be achieved at some stores while others will have lower savings numbers.

Once the SLiM Program is implemented in a given store, we will have the exact details of what we did and how much energy those actions will save.  This will be carefully documented and provided to the EM&V contractor in detail on a timely basis.  Our program tracking of the program’s energy savings accomplishments will be much more specific than simply multiplying stores by the assumed average per-store savings estimate.

The EM&V contractor will be able to verify most of these actions and savings estimates by relatively straightforward and simple inspections.  For example, if we report shutting off one-third of the lights in an organized pattern, the EM&V contractor will be able to observe this simply by walking into the store.  We anticipate that the EM&V contractor may also wish to collect a small sample of interval data with dataloggers.  We will be able to assist in any way desired, including identifying specific panels and locations where such data collection would best be achieved.

This project has the potential to benefit from iterative EM&V/implementation work.  If, for example, the EM&V contractor finds that something is not working as described, we will be able to take that information and fix the problem.  Thus the EM&V contractor not just describes, but also enhances, the success of the program.

The participating customers will be informed of the EM&V component of the program.  Store managers will be given the name of the EM&V contractor, and the EM&C contractor will be given the names and contacts of the store managers.  The contract between Aloha and the participating customers will require their cooperation with the EM&V process as part of their participation.

B.  Potential EM&V Contractors

The following four companies are capable of performing the EM&V work necessary for evaluation of this program.  Since Aloha Systems has many years experience of its own in program EM&V, these companies, their principals, and their technical qualifications are well known to Aloha management.  Furthermore, there are no contractual arrangements or conflicts of interest between Aloha Systems and any of these companies that would prevent their evaluation of the program from being objective.  They are listed in alphabetical order and not in any order of qualification or recommendation.

Alternative Energy Systems Consulting (AESC)

1945 Camino Vida Roble, Suite A

Carlsbad, CA  92008-6529

ASW Engineering

2512 Chambers Road, Suite 103

Tustin, CA  92780-6950

Quantum Consulting, Inc.

2030 Addison Street, Suite 410

Berkeley, CA  94704-1144

RLW Analytics

1055 Broadway, Suite G

Sonoma, CA  95476-7467

Section VII.  Qualifications

A.  Primary Implementer

Aloha Systems is an engineering, contracting, and consulting firm specializing in energy efficiency.  It has been providing these services in California for 16 years.  The company is a licensed general and electrical contractor (#541443) and has registered professional engineers on staff.  Many of the company’s full- and part-time personnel have prior utility employment experience.

Aloha Systems and its staff have significant experience with lighting in general and grocery stores in particular.  We have worked closely with the corporate energy managers of retail stores and conducted comprehensive energy audits in a number of stores.  We have worked with many energy users in lighting efficiency improvements, including public schools, small and large commercial enterprises, and manufacturing and industrial facilities on projects such as SPC, Express Efficiency, and the Self-Generation Incentive Program.  We have also provided project assessment, evaluation, and measurement and verification for a number of end-users, utility programs and non-utility programs.

B.  Subcontractors

The SLiM Program does not plan to use subcontractors.

C.  Resumes or Descriptions of Experience

Dr. Mark S. Shirilau, president and CEO, has twenty years experience in the utility energy efficiency arena.  Prior to joining Aloha Systems as its executive vice president in 1989, Mark worked at Southern California Edison.  Among the positions he held at Edison was engineering supervisor of the Residential Conservation Program corporate staff.  Mark received his Ph.D. in electrical engineering from the University of California at Irvine, and his doctoral dissertation addressed the ability of utility rates and conservation programs to affect residential energy use for the benefit of the customer, the utility, and the power grid.  Mark is a former student in both the UC and CSU systems and has also served as a part-time professor of engineering.

Robert A. Prodonovich, vice president, has served three years as division manager responsible for Aloha’s various energy auditing and evaluation programs.  Prior to joining Aloha Systems, Rob served as vice president of Reliable Energy Concepts, a lighting contractor specializing in major energy efficiency projects.  He also has an extensive background in industrial facilities management and is a licensed contractor.  Rob will provide administrative and technical expertise, together with other members of his staff, on an as-needed basis.

Jonathan C. McClure and/or TBD, senior technician, has served part-time in New York as manager responsible for Aloha’s operations in the northeast and part time in California.  Jon has an extensive background in a variety of industrial processes and manufacturing, including quality control in railroad car assembly and bottling operations.  He has also owned and operated a small business specializing in computer repair.  In conjunction with the various PGC local programs that Aloha is offering, Jon may be relocating full-time to California to provide additional technical, quality, and project management assistance.

Timothy Thorvick, Sean Raab, Ami Kotev, and/or TBD. Two electrician/technicians will be dedicated full time to the program.  We will balance the two-person teams with one person whose primary strength is in building construction trades and another whose primary strength is in computer or control technology.  Tim and Sean both have over twenty years experience in construction, including work in various building trades and formerly owning their own contracting firms.  Ami has his degree in electrical engineering with an emphasis in power systems and computer technology.

Gina Jojola, Luis Sanchez, Paul Weidenzahn, and/or TBD, program manager.  The program manager will be responsible for the overall implementation of the program in the PG&E territory and will be dedicated to the project on a full-time basis.   Gina has worked at Aloha Systems for two years coordinating a variety of energy efficiency projects.  She received her BA in 1998 from Vanguard University.  Prior to joining Aloha, Gina worked as a production coordinator, project scheduler, and quality control analyst in a manufacturing facility.  Luis has worked as an electrical engineer at Aloha Systems on a variety of energy efficiency projects.  Luis received his BS in electrical engineering from U.C. Irvine in 2002 and is a registered engineer-in-training.  Paul is not presently working for Aloha but has indicated a possible interest.  Assignment of the program manager position will depend upon which of Aloha’s proposed programs are funded and which of the selected programs are best matched with available personnel.

Robert D. Hall, vice president, has served as division manager responsible for Aloha’s Texas operations and its security consulting in both Texas and California.  Prior to joining Aloha, Rob served as chief of police of Nolanville, Texas, and brings an extensive background in management and team leadership.  In conjunction with the various PGC local programs that Aloha is offering, Rob Hall may be relocating full-time to California to provide additional managerial assistance.

Dr. Brian C. Stevens, senior consulting engineer, will provide engineering expertise as needed.  Brian received his Ph.D. in electric power systems engineering and has expertise in metering and power systems analysis.  Brian is a former employee of Public Service of New Hampshire and later worked for Dr. Shirilau as a consultant for his major research projects at Southern California Edison.  Brian also has served as electrical engineering director for a mining facility that is the largest single user of electricity in Arizona.

Michele L. Farrell, regulatory affairs manager, will provide administrative and regulatory reporting work for the local energy efficiency projects sponsored by Aloha.  Michele received her B.A. in accounting and business administration from Portland State University in 1976.  She worked at Southern California Edison where she was responsible for program design and management of the residential conservation programs, and later served in the Revenue Requirements departments of Edison and Portland General Electric.

Section VIII.  Budget

Managerial and Clerical Labor	$ 196,440

Benefits and Payroll Tax	242,348

Travel and Conferences	38,000

Equipment	94,000

Facilities, Utilities, etc.	80,000

Regulatory Labor	25,500

Office Supplies and Postage	   11,000

Total Administrative Costs		$  687,288

Marketing Labor	  10,000

Total Marketing Costs		10,000

Activity Labor	361,000

Hardware, Tools, and Education Materials	  25,000

Total Direct Implementation		386,000

EM&V		50,000

Financing and Profit		      11,333

Total Budget		$ 1,144,621

Potential Performance Award		79,330