BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF CALIFORNIA

2004-2005 Energy Efficiency Program Selection

Energy Efficiency Proposal

Comprehensive Hard-to-Reach Mobile Home Program

Proposal No:

Electric Workbook and Gas Workbooks Submitted Separately with the Same Joint Narrative

Designed to Complement Utility Filed HTR Programs

in Targeted Local Communities

in

Southern California Edison and Southern California Gas Company

Service Areas

Steven R. Shallenberger, President

American Synergy Corporation

28436 Satellite St.

Hayward, CA 94545

1-909-288-4651

Email:  Shallenbgr@aol.com

September 23, 2003

Other Proposals Submitted:

- SDGE mobile home

- PG&E multi family

# Table of Contents

Table of Contents	2

SECTION I  Program Overview	3

A.  Program Concept	3

B.  Program Rationale	4

C.  Program Objectives	5

SECTION II.  Program Process	10

A.  Program Implementation	10

B.  Marketing Plan	10

C.  Customer Enrollment	11

D.  Materials	11

E. Payment of Incentives (not applicable)	12

F. Staff and Subcontractor Responsibilities	12

G.  Work Plan and Timeline for Program Implementation	13

SECTION III  Customer Description	15

A.  Customer Description	15

B.  Customer Eligibility	15

D. Geographic Area	16

Section IV  Measure and Activity Description	17

A.  Energy Savings Assumptions	17

B. Deviations in Standard Cost-Effectiveness Values	24

C. Rebate amounts (not applicable)	24

D. Activities Description	25

Section V  Goals	26

SECTION VI	28

Program Evaluation, Measurement and Verification	28

A.  The Evaluation Approach	28

B.  Potential Contractors	29

SECTION VII  Qualifications	30

A.  Primary Implementers	30

B.  Subcontractors	31

C.  Resumes	34

SECTION VIII  2004-2005 Budget	35

APPENDIX A  References (hard copy only)

APPENDIX  B (hard copy only)

2nd Quarter Report 2003:  Local Area Programs From 2002-2003

APPENDIX  C (hard copy only)

Customer Comments from Mobile Home Customers on Like Program

# SECTION I  Program Overview

## A.  Program Concept

This residential, hard-to-reach third party proposal is designed to complement SCE’s and SoCal Gas current filing for 2004 and 2005 by reaching mobile home customers that would not otherwise receive program benefits from public purpose funding.  There are many enhancements in this mobile home proposal (to the program we are currently delivering to mobile home customers of SCE and of SoCal Gas).  There is also a significant carryover feature (from our current mobile home contract #171-02 ).  American Synergy Corporation (ASC) has worked closely with both SCE and SoCal Gas in the delivery of existing third party local program.  Both utilities have indicated that there are specific customer classes (and specific geographic portions of their service areas) which they are unable to serve in 2004 and 2005.  This proposal focuses on those measures (and the geographic segments) which both the utility and their customers have found desirable and which the proposed mix of utility programs for 2004/5 will not address.  Our program has been designed to provide a comprehensive energy program to an estimated 8,000 to 11,000 mobile home customers in the SCE and SCG service territory, collaborating with local communities within this service area to maximize service to the citizens of their cities and towns.

The proposed combined budget and goals for this program are as follows (including Administration, Marketing, Direct Implementation, and EM&V).

| The Proposed Combined Program Budget | Southern California Edison Allocation | Southern California Gas Allocation |
| --- | --- | --- |
| Program Budget | $4,877,015 | $1,778,834 |
| Potential Performance Award | $341,391 | $129,670 |
| Combined Program Budget, with PPA | $5,218,406 | $1,903,352 |
| The Projected TRC Ratio | 2.59 | 3.68 |
| The Projected PT Ratio | 14.27 | 24.72 |
| The Net Projected Energy Effects |  |  |
| The Projected Net Coincident Peak kW | 6,066 |  |
| The Projected Annual kWh Savings | 14,687,461 |  |
| The Projected Annual Therms Savings |  | 891,068 |

A joint narrative and a separate implementation plan are submitted for each service area for this proposal.

## B.  Program Rationale

The basis for this SCE and SoCal Gas mobile home proposal is to continue to reach under-served and hard to reach mobile home customers of SCE and SoCal Gas.  In the past 4 years, our prior mobile home programs for these two utilities have reached nearly 4500 mobile home customers, but this number is less than 10% of the nearly 60,000 qualifying and needy mobile home customers in the service areas of these utilities.

If this proposal is selected, the Commission and mobile home customers we have identified in our proposal, are assured that the program will be delivered promptly and will deliver long term and cost effective savings.  Our past performance with both utility and Commission programs has been to meet or exceed contract milestones and EM&V requirements. We are aware there are many deserving customer classes awaiting benefits from public purpose funding programs.  This program has been designed to ramp up or down should the Commission wish to have that flexibility.

The attached WORKSHEETS show a cost effective program with a TRC of 2.59 (Electric) and a TRC of 3.68 (Gas).  However, trying to maximize the numerical TRC was not the sole objective of this program.  Rather, we have designed a comprehensive mobile home program which will assure ratepayers and the Commission of long-term energy savings.  The combined TRC could be increased to >3.5 should that be the primary objective (by increasing the number of short-lived  measures or by decreasing the broad range of measures and services identified in section IV).  We are willing to discuss alternate measures options should that be of desire to you.

Our program will provide the following turnkey services for this direct install mobile home program:

- Administrative oversight

- Marketing

- Direct purchase and installation of materials & equipment

- All M&V and evaluation activities as well as providing mobile home educational packets

- On-going, long-term, high quality customer service

The program will focus on the hard-to-reach mobile homes units within the service areas of Southern California Edison and Southern California Gas which the utilities have indicated are their most under-served sectors.  The program is designed to overcome market barriers of location, culture, park management, information, and cost.  It is innovative in four distinct ways:

- There is synergy in how the program will complement current utility filings.

- New energy efficiency measures have been included which have previously not been delivered in a cost-effective manner to these HTR customers.

- Additional energy savings benefits (not included in the TRC evaluation) will be provided by bidder’s on-going “Neighborhood Community” training programs within each mobile home community.

- In addition, we will work with local water agencies serving the customers identified in this proposal to significantly enhance the overall utility and environmental benefits achieved by customers served in this program.

## C.  Program Objectives

To facilitate your review of our proposal, we have provided a brief overview of the projected accomplishments of our proposal in addressing each bid criteria identified by the CPUC for this solicitation.

- Cost Effectiveness and Program Net Benefits

The program net benefits and cost effectiveness for the 2004 mobile home program are demonstrated to exceed those for our current third party mobile home programs.  In our current mobile home program, we assumed deemed savings values which were (in many instances) more conservative than the DEER and DOE/2 library data made available by the CPUC to bidders.

We had not wished to use deemed savings values greater than we had previously demonstrated in prior mobile home programs...until such time as we had successfully demonstrated through EM&V studies that higher deemed savings were warranted.  The enhanced measures we utilized, combined with the installation procedures we implemented last year, demonstrated significantly higher measured overall performance for some measures than we claimed last year.  This proposal uses the higher DEER values in those instances where our on-going EM&V programs warrant.  The program net benefits summarized in the proposal workbook analyses provide additional (non quantified) energy and environmental benefits.

The non-quantified program benefits accrue from:

- Neighborhood workshops in which we demonstrate (to both park management and mobile home occupants) the measures being offered by this program, how they will affect their power bill and be more energy efficient.  In these neighborhood community functions, we provide materials on other available utility rebate and appliance programs and training on how to enhance the overall energy savings for customers.

- Training and educational materials

- Supplemental water and sewer benefits offered with support from local water districts.

While the WORKSHEET exhibits demonstrate a strong TRC for both gas and electric measures, this program has not been designed for optimal cost effectiveness (as that could lead to a program that could sacrifice a fully comprehensive program).  A more cost-effective program could be achieved by:

- Offering only 1 or 2 measures that did not require some form of customer co-payment, or

- Focusing solely on the geographically “rich target” areas for HTR customers, or

- Manipulating penetration rates of measures so as to make the final TRC “appear” large.

Instead, this proposal has been developed to meet 3 important criteria:

- be comprehensive on energy and peak demand savings

- reach LOCAL HTR segments previously ignored or not reached through prior utility programs

- provide a focus on providing lowest possible cost measures prices will maximize use of public purpose funds (rather than trying to artificially achieve the highest possible TRC).

- Long-Term Annual Energy Savings

Our companies have a proven record in California for developing and implementing programs for delivering long-term savings to hard to reach mobile home customers. For the current solicitation, our Team has already identified over 50,000 mobile home units in the geographic local areas which the utilities have stated are their most under-served sectors. Long-term savings will be achieved through this program for the following reasons:

- This program uses proven and reliable energy savings measures which customers have accepted. (see Appendix C)

- This program is currently meeting or exceeding the CPUC and utility milestone and EM&V contract requirements (for contract #171-02).  Appendix B is a compilation of those parties who did file quarterly reports through July 2003. This exhibit shows both dollars budgeted (and actual installations achieved) for all third party programs...and demonstrates that ASC is achieving or exceeding contract goals and milestones.

- A separate factor which can influence long-term savings is that the measured results meet or exceed the deemed saving values identified in the contract. Each of our prior Commission and utility contracts have been based upon a rigorous and conservative EM&V plan. In addition to the achievement of milestone goals (on or ahead of each contract requirement), we have also received high marks from the CPUC staff and independent EM&V consultant for our measurement and evaluation plan.

- While some short lived measures are provided, there are many additional energy efficiency measures (having long measure lifetimes), which will provide substantial long term value to the customer.  The workbook portion of our proposal demonstrates that the average life of all measures exceeds 10 years.

- Our program is provided by a proven administrative team.

- Our delivery team is proven.

- A collaborative approach in working with utilities, the Commission and the most important party, the CUSTOMER.

- Electric Peak

Typical energy efficiency measures focusing on hard-to-reach sectors tend to focus more heavily on annual kWh or therm savings than on summer peak kW peak load demand.  This program has been carefully designed to achieve a balance in comprehensiveness, reducing energy bills from this sector, and reducing summer peak demand.  This is achieved by:

- Providing measures in this program which have a strong contribution to both the transmission & distribution system and to the customer.  Electric water heat timers (at 0.43 kW per customer) will provide a substantial reduction to a customer’s on-peak water heating loads.

- Other major residential contributions to summer peaks in California include lighting and air conditioning loads for the market sectors we are addressing in this proposal.  Our program will directly address and reduce these peak loads through lighting, duct Sealing, AC diagnostic/balance and infiltration reduction improvements.

There are a limited number of measures in the residential and small commercial market sectors which can significantly reduce summer peak loads during the period of noon to 8:00 p.m.  Clearly, measures which reduce loads during the late evening hours would contribute less to reducing peak loads than would measures that directly reduce on-peak usage for water heating, space cooling, or common area lighting that otherwise remains on during the peak hours.

Our companies have participated in the delivery of many energy efficiency programs throughout California.  Where appropriate, our expertise has focused on seasonal energy usage (typical of the goals of the 1998 RES-SPC and the 1999 and 2000 Residential Contractor Programs implemented in California).  But different programs are required to obtain primarily on-peak load reductions.  Water heat timers, enhanced HVAC diagnostics and enhanced duct sealing programs were introduced and approved for residential programs by bidders (for the hard to reach sectors) in the 2000 Summer Initiative Program.  These are not temporary savings relying upon behavioral changes, but permanent peak demand savings which contribute to both peak demand and permanent energy savings.  We have the proven capabilities to implement the summer peak demand savings as proposed herein.

- Equity

This proposal addresses the following equity issues for mobile home customers:

- Equitable geographic distribution (focused in geographic areas identified by the utilities)

- Diversity of target markets

- Equity between gas and electric programs

- Diversity of program offerings

- Multiple languages offered to participants

We were heartened by the CPUCs continuing priority to address the needs of under-served or hard-to-reach sectors.  A principle inequity in recent years is that public purpose funds collected from this residential sector, until very recently have not been returned to this sector.  In 2002, the Commission awarded several contracts to hard to reach bidders for mobile home programs.  However, even with the program awards in 2002, current filings demonstrate that over 8% of all public purpose funds come from California’s mobile home customers, but less than 4% is returned to this sector.

We recognize that other constraints may prevent an equitable allocation of funds from reaching each market sector.  However, when a very cost effective program and proven program can be implemented (while also reaching customers which current utility programs can not), then we believe that the priority recognized by the CPUC for equity is appropriate.  This proposal focuses on mobile homes as they are one of the largest users of both electricity and of natural gas.  However, in many instances, the homeowner does not have the same incentive or capabilities to improve their dwellings and many are fixed or lower income (yet above the federal poverty guidelines and thus unable to qualify for low income programs or assistance).

Our company have specialized in the development and implementation of programs for mobile home programs in all western states.  Each region has unique equity issues to address. Our bid encompasses the best features of our combined 20 years of delivering mobile home programs to the mobile home sector.

- Ability to Overcome Market Barriers

Current market barriers for mobile home energy efficiency programs include:

- Insufficient prices for comprehensive measures or requiring some form of co pay from homeowners or renters.

- Inability to develop and implement programs which meet the needs of both the homeowner the part managers.

- Utilities choose not to put both duct seal and A/C diagnostic programs due to the high administrative costs.

Our program addresses each of these primary market barriers.

- Innovation

This proposal brings together two respected and experienced contractors.  The synergy of linking a proven California contractor with experience in delivering programs to all HTR sectors (ASC, Program Implementer) with a proven developer, administrator, and performance based program evaluator (UCONS, sub contractor) ...has been done to the benefit of all of California’s under served residential customers.

This program is also innovative in the:

- Comprehensiveness of measures and services offered.  We could provide fewer items (being less comprehensive) and serve more homes, but in the long run this would actually be less efficient in having to spend more marketing dollars to go back to the customer. We have found that we are more efficient in providing a comprehensive program while our technicians are in the home, addressing the needs of mobile home customers.

- Use of enhanced AC diagnostics, and use of water heat timers to reduce system peak load which is new to this market sector.

- Coordination with Programs Run by Other Entities

While this is a stand-alone program funded and implemented independent of utility administration, the utility recognized that a third party program sponsored by proven contractors could better benefit its customers.  Customer needs are more effectively met by contractors and ESCOs working with California’s utilities in a new and collaborative manner.  We have successfully demonstrated the ability to coordinate our duct seal and AC diagnostic work with other existing utility programs.  This provides a real compliment of valuable energy savings measures to other statewide programs being offered.

There are current utility sponsored programs which offer funding for a variety of services. Our program will not compete with either utility or other third party programs. Our marketing and installation teams will make the property owner/manager aware of the separate programs which are available and facilitate identifying other programs when customers are interested.

The synergy of saving customers on both their energy bills and their sewer and water bills is also important.  This synergy is achieved by installing both energy and water conservation measures and collaborating with local water districts to leverage these savings even further

- Alleviating Transmission Constraints

ASC has previously worked with utilities and with independent system operators to mitigate transmission or distribution loads in constrained areas.  To the extent that a need may arise from the System Operator (which does not conflict with other requirements of this program), we would facilitate the delivery of this program to those geographic locations which may provide other system benefits.

# SECTION II.  Program Process

## A.  Program Implementation

This proposal is an evolved version of the third party mobile home program developed in coordination with SCE and SoCal Gas in 2002 (contract # 171-02)).  If selected, ASC will work closely with the utilities (and other non-IOUs) to ensure that there is neither double dipping nor any confusion with the customers.  In prior RCP and SIP programs for SCE-SCG, we have established a well-developed and respected position with many mobile home owners and park managers within the utilities’ area.  Should contracts be awarded which could be over-lapping, we will cooperate on the marketing aspects (so as to minimize customer inconvenience or confusion) and on the record keeping and data reporting (so as to ensure no double counting and proper allocation of benefits)

This program is an enhancement of the programs for SCE-SCG’s customers in the following respects:

- Neighborhood meetings. This is an outstanding experience where the energy efficiency program is explained to members of the neighborhood and mobile home community, usually in the facility clubhouse or meeting room, where programs are being implemented.  We explain the details of the program with samples of the measures to be installed in their apartments and homes.  Questions and answers take place and individuals that are interested can take literature on the program or schedule their installation date.  We often follow-up with a second visit after many of the residences have had the opportunity to have measures installed within their complex.  Almost without exception, these meetings are welcomed and well received.

- Our targeted list of energy efficiency measures reflects our research over the past year which demonstrates that a slightly different list of measures and services will be required to address customer energy efficiency needs.  In particular, our current market research demonstrates that the following measures are most appropriate: CFL lights and exterior fixtures; Duct Seals, AC Diagnostics, and Programmable Thermostats.

## B.  Marketing Plan

Our market research has indicated that there are 143,741 mobile homes in San Bernardino, Riverside, Orange, and Los Angeles Counties.  Approximately 45,000 or 31% have been served with some energy efficiency measure and an estimated 12% have had comprehensive work completed.  Our market research has already identified 50,000 units that can be marketed to for installation of the comprehensive measures outlined in this proposal.

Marketing and outreach plans have been carefully developed to address the primary market barriers.  Prior marketing efforts in the under-served sectors demonstrate that it is not feasible to acquire resources in this market segment conditioned upon a customer contribution.  Many efforts have been made to acquire at least a partial contribution from this customer class, but experience has demonstrated it is often more costly (in marketing and customer support) to collect funds from this hard to reach segment, than the amount of the contribution itself.  Worse, if our efforts should increase such a requirement (rather than mitigate existing market barriers) will only serve to prevent Public Goods Charge funds collected from this sector … to continue to not be spent in this sector.

Mobile Home occupants and property managers will receive information regarding the mobile home energy efficiency program.  Interested homeowners will call our toll free hotline to schedule the work to be done in their home.  On the scheduled date our technicians complete a walk through of the home with the customer, provide energy efficiency education, and install the needed measures to maximize energy efficiency.

Customers are found through the following activities:

- Working directly with property managers and associations.

- Working with local community organizations such as senior citizen centers, associations of retired people, Chambers of Commerce, local libraries with community information.

- Working with local communities and cities to target specific communities and areas within their cities.  Once an area is identified, customers will be found through billing inserts and community newsletters.

- Flyers

- Word-of-mouth

## C.  Customer Enrollment

Customer enrollment takes place as described above by responding to a toll-free number on our marketing literature and schedule the work to be completed.  Response comes as a result of personal contact, flyers, neighborhood meetings and word-of-mouth.  This process is explained in more detail in the “marketing section”, above.

## D.  Materials

Materials are procured by our purchasing, control and warehouse staff through our production planning model.  All energy efficiency materials and measures are in fully accordance with the procurement specifications of both SCE and or SoCal Gas.  In addition to meeting utility specifications, all materials are energy star rated and have proven by experience to provide reliable and dependable results.  Each of our technicians has been trained, has extensive on the job experience and is EPA certified for the work that is outlined in the proposal. A brief description of how measures and materials provide maximum benefit to this market sector is summarized below.

The AC diagnostic allows for an assessment of the Freon levels for a smooth running air conditioning system.  If there is too much Freon in the lines, the system is overwhelmed to process the excess volume and has to work overtime.  If there is not enough Freon in the AC system, it is always playing “catch-up” and must run overtime because there is not adequate capacity to keep the building cool enough.  When the unit is properly balanced, the AC runs smoothly and just enough to keep the building cool.  This provides and optimal energy efficiency.

Water heat timers (plus AC diagnostics; enhanced duct sealing programs and appropriate application of lighting measures address the electric peak objectives of our program.  Energy efficient CFL’s provide immediate, but shorter lived benefits (without on-going training and feedback with the neighborhood communities).  Hard wired fixtures have a sustainable and long life.  The duct test and seal will identify and seal of costly leaks and wasted energy that literally would go right out the door, or in this case up the collective vent.

Procedures for Installation

Proposers are currently meeting or exceeding all utility and state of California standards and specifications for the delivery and installation of energy efficient measures to this hard to reach sector.

Mobile homes owners, park managers, and renters will receive information regarding the energy conservation program via direct mail and/or contact with property owners and managers.  As customers respond to the information, their work will be scheduled through our central scheduling for work completion.  The owners will choose from the energy conservation options presented (depending upon the need that exists in each dwelling). Installation crews will complete the work outlined.  Information for work will be completed and added to the database for reporting to the CPUC.

Upon notice of completion, the work will randomly be inspected through qualified Inspectors.  The predefined California and local IOU standards for retrofit will be used to measure quality and correctness of installed measures.  Surveys of managers and owners will be conducted as work is completed (these reports serve as part of the quality control system, as well as input to the EM&V consultants).

## E. Payment of Incentives (not applicable)

## F. Staff and Subcontractor Responsibilities

The contact person for this project will be Steven Shallenberger of American Synergy.  The prime contractor for the project is American Synergy who has selected Cal-UCONS as its principle sub contractor (to oversee program design, engineering analyses and oversee customer liaison activities.  The key staff and subcontractor roles are briefly summarized below.  Section VII provides a complete qualification review of the key staff for this project.

| Name | Title | Responsibility |
| --- | --- | --- |
| David C. Clark | CEO-Owner ASC | Administration, Marketing, Production |
| Steven Shallenberger | President-Owner ASC | Administration, Marketing, Production, EM&V |
| Thomas G. Eckhart | CEO-Owner Cal/UCONS | Administration, program design and engineering, EM&V |
| Shani Taha | Vice-President, Marketing & Ops Cal/UCONS | Administration and customer liaison |
| Douglas Price | Operations Manager-ASC | Administration, Marketing, Production, EM&V |
| Russell Jacobsen | Controller-ASC | Administration, EM&V |
| Sal Vaccaro | Operations Manager | Administration, Marketing, Production |
| Jim Amos | Marketing Manager | Marketing |
| Rod McPherson | Marketing Operations | Marketing and Outreach. Production |
| Jeremy Price | Outreach | Marketing and Outreach |
| Kent Walker | Outreach | Marketing and Outreach |
| Maureen McCarty | Customer Service and Scheduling | Administration |
| Donna Hardin | Customer Service and Scheduling | Administration |
| Patricia Espinoza | Receptionist and Admin. | Administration |
| Aaron | Data Entry and Scheduling | Administration |
| Scott Price | Quality Assurance Manager | Production and EM&V |
| Roger Thornton | Quality Assurance Manager | Production and EM&V |
| George Burge | Warehouse Manager & Procurement | Production and EM&V |
| Julie Richardson | Direct Marketing Manager | Marketing |
| Jose Antonio Garcia | Warehouse and Procurement | Administration and Production |

## G.  Work Plan and Timeline for Program Implementation

Program Performance Goals

| Date | Description |
| --- | --- |
| Nov 2003 | CPUC Awards bid to Winners |
| Dec 2003 | Contract with SCE/SCG finalized and signed |
| Jan 2004 | Marketing and Outreach Program Launched |
| Feb 2004 | Begin Monthly Reports on Program Progress |
| Feb 2004 | Begin installation of measures |
| Feb 2004 | Begin in-house inspections and Quality Assurance Effort |
| Mar 2004 | Begin EM&V work |
| Mar 2004-Dec 2005 | Work for successful realization of Program Goals and Objectives. Complete Monthly Report on a timely basis |
| March 31, 2006 | Program Completion and Evaluation Report is |
|  | Complete |

Program Benchmarks

| Date | Projected Units Complete | Progress Measurement |  |
| --- | --- | --- | --- |
| Mar 21, 2004 | 100 | Monthly Progress Report for Previous Month and Invoice |  |
| April 21, 2004 | 200 | Monthly Progress Report for Previous Month and Invoice |  |
| May 21, 2004 | 350 | Monthly Progress Report for Previous Month and Invoice |  |
| Jun 21, 2004 | 500 | Monthly Progress Report for Previous Month and Invoice |  |
| Jul 21, 2004 | 550 | Monthly Progress Report for Previous Month and Invoice |  |
| Aug 21, 2004 | 550 | Monthly Progress Report for Previous Month and Invoice |  |
| Sept 21, 2004 | 550 | Monthly Progress Report for Previous Month and Invoice |  |
| Oct 21, 2004 | 450 | Monthly Progress Report for Previous Month and Invoice |  |
| Nov 21, 2004 | 350 | Monthly Progress Report for Previous Month and Invoice |  |
| Dec 21, 2004 | 250 | Monthly Progress Report for Previous Month and Invoice |  |
| Jan 21, 2005 | 200 | Monthly Progress Report for Previous Month and Invoice |  |
| Feb 21, 2005 | 200 | Monthly Progress Report for Previous Month and Invoice |  |
| Mar 21, 2005 | 250 | Monthly Progress Report for Previous Month and Invoice |  |
| Apr 21, 2005 | 350 | Monthly Progress Report for Previous Month and Invoice |  |
| Jun 21, 2005 | 450 | Monthly Progress Report for Previous Month and Invoice |  |
| Jul 21, 2005 | 550 | Monthly Progress Report for Previous Month and Invoice |  |
| Aug 21, 2005 | 550 | Monthly Progress Report for Previous Month and Invoice |  |
| Sept 21, 2005 | 550 | Monthly Progress Report for Previous Month and Invoice |  |
| Oct 21, 2005 | 400 | Monthly Progress Report for Previous Month and Invoice |  |
| Nov 21, 2005 | 250 | Monthly Progress Report for Previous Month and Invoice |  |
| Dec 21, 2005 | 200 | Monthly Progress Report for Previous Month and Invoice |  |
| Jan 21, 2006 | 200 | Monthly Progress Report for Previous Month and Invoice |  |
| Total | 8,000 |  |  |

# SECTION III  Customer Description

## A.  Customer Description

The target customers to be reached through this program are the mobile home parks and residences in Southern California which have proven the most difficult to reach by other energy efficiency programs in recent years.  We have found that the customer in this hard-to-reach mobile home market would typically be senior citizens and the elderly (in many cases single senior citizens), people who are living on a fixed income, disabled individuals (because of costs of medical care), immigrants, single-parent families, and young couples.  These customers are frequently in the moderate income or fixed income brackets.

We find that these individuals are most grateful for our programs, because energy efficiency resources are foreign to them and hard to understand.  They are individuals who generally have the least capacity to get up on a ladder and put a light in.  To install a permanent hardwire CFL is not only a wise long-term energy efficiency choice, but also saves individuals from potential health hazards.

Many of the incentive levels set by the utilities for residential projects have been too low in recent years to encourage the acquisition of significant load reductions in the under-served markets.  Too low an incentive level can encourage “cream skimming” with only 1 or 2 measures delivered to program participants or non-participation should a customer contribution be required from this sector to qualify for additional measures.  Mobile home customers have indeed been hard to reach, because they are hard to identify, costly to reach, and suffer from the "split incentive" conundrum that stifles energy efficiency investments in tenant-occupied housing.

## B.  Customer Eligibility

We have previously worked with many of the mobile home owners and park managers in the Southern California area.  There are three primary criteria which need to be addressed before treating mobile home units in this area:

- We will meet with the Mobile Home Park Manager and do a needs assessment.  Have the mobile homes been treated?  With what measures?  How many mobile homes have been treated?

- If it is determined by the outreach associates that the residents of the park would benefit from the program, flyers, notification, and neighborhood meetings would be scheduled to inform residents of the program.

- Interested residents would call the toll free number to schedule a technician to pass by their coach to complete an assessment for work and provide education to the customer.

Mobile home customers are also hard to reach by virtue of the difficulty in identifying park owners and managers, and being able to successfully set up production times that work for all decision makers.

C.  Customer Complaint Resolution

Our companies maintain an experienced customer service department that responds to customer complaints within 12-24 hours.  Our creed is to “Treat People Right”.  Each customer is provided a toll-free customer service line with personal service from our trusted customer service associates Maureen McCarty and Donna Hardin.  During our current third party mobile home program, there were a few customer calls. All were handled quickly and a time was set to meet at the customer’s convenience to evaluate the issues. All customer issues were promptly resolved. A check of our references will establish that we provide both excellent initial service, and also promptly address any customer issues or problems.

According to the EM&V contractor’s in-house surveys done on the 2002-2003 programs, the following statistics were found in terms of customer satisfaction:

- Over-all Customer Satisfaction - 100% (i.e., 10 points out of 10)

- Satisfaction with Energy Education Tips (usefulness, presentation, accuracy) - 90%

- Satisfaction regarding program demonstrating linkages between energy efficiency, bill savings and comfort - 94%

- Comments - “great program, really happy with program, marvelous program, no complaints.”

## D. Geographic Area

SCE and So Cal Gas have identified the areas of San Bernardino, Riverside, Orange, Los Angeles, and Ventura Counties as the hard-to-reach and underserved mobile home residences that a mobile home program should focus on for 2004.

# Section IV  Measure and Activity Description

## A.  Energy Savings Assumptions

This section provides a description of each measure and the engineering assumptions used to calculate energy savings.  The bid instructions for this solicitation directed parties to use the current DEER data base. The DEER data base specifies single family and multi family applications. For those mobile home applications not identified in the current DEER data base, cost effectiveness savings have been derived through the use of other public energy efficiency data, and savings derived through actual experience in working with prior mobile homes projects.  This project will focus primarily on climate zones 9, 10, and 18, with the projected savings being average values for these climate zones.

There are several methods for determining base energy use and energy savings for an energy efficiency measure.  These methods include using measured data, taking estimates from results of previous surveys, taking estimates from forecasting models developed by the California Energy Commission or by utilities, or estimating energy use and savings with engineering models that are consistent with the assumptions used in the forecasting models.

Where appropriate, estimates of energy use and savings and load impacts for weather-sensitive technologies and measures were prepared in this study using building simulation analysis with the DOE-2 model. This simulation-based engineering analysis was used as the approach for this study because it is appropriate for measures that are highly sensitive to differences in weather among California’s diverse climate zones and because it can easily accommodate the large number of measure, climate zone, building type, and fuel types for which results are desired.

Assumptions applicable to all prototypes are as follows.  Natural infiltration is modeled using Sherman-Grimsrud method and Effective Leakage Area (ELA) to Floor Area ratio of 0.0006.  Baseline duct leakage is modeled with a duct-air-loss of 29%.

Window shading during summer months is modeled using DOE-2.2 interior drape commands.  The model uses a shading coefficient drape multiplier of 0.75 whenever direct solar radiation through the windows exceeds a threshold of 30 Btu/ft2-hr in summer and 50 Btu/ft2-hr in winter.  A probability of 50% is included to open the drapes when the direct solar radiation drops below the threshold.  The model resets the drapes to open each day at midnight.

Natural ventilation during the cooling season (June 15 through October 15) is modeled using the Sherman-Grimsrud method to calculate air changes per hour (ACH) with an upper limit of 1 ACH.  The effective window leakage area per unit floor area from window openings is set at 0.05. Windows are only opened if the ambient temperature is greater than 65 F, and only during the hours of 7 to 9 PM on weekdays and weekends.  A probability of 75% is included to account for occupants being home to open windows.

- Mobile Home Prototypes

Mobile home prototypes are modeled with a crawl space skirt foundation, 1,000 ft2 of conditioned floor area, central heat pump and gas heating systems.  Prototypes are modeled as built prior to 1976 with R-11 ceilings and R-7 walls and floors.  Thermostat settings vary by climate zone. Lighting and miscellaneous internal loads were calibrated to average UEC values. Peak occupancy is 3 people.

This section provides a description of each measure and engineering assumptions used to calculate energy savings.

Duct Testing and Sealing

Duct testing and sealing savings are based on sealing both supply and return ducts to a leakage reduction of 60 cfm/ton or 15 percent of measured system flow at 25 Pascal pressure (supply and return).  Baseline duct leakage is modeled with a duct-air-loss input of 29%. The measure is modeled with a duct-air-loss input of 15%.  The measure lifetime is 20 years as per the CPUC.  Mobile home energy savings are shown in Table 1.

According to the 2001 DEER study savings are calculated as follows with a weighted average being calculated for all mobile homes served, both in terms of location and age of home.

Through independent on site research and calculations by an independent EM&V engineer it was found that actual savings from duct testing and sealing for mobile homes has been equal to and better than 48 therms in climate zone 10 and 96 therms in climate zone 18 (15).

Table 1 Mobile Home Duct Testing and Sealing

|  | Savings | Peak Demand | Gas Heating |
| --- | --- | --- | --- |
| Climate Zone | kWh/yr | kW | therm/yr |
| MH Climate Zone 9 (Burbank) | 152 | .23 | 24 |
| MH Climate Zone 10 (San Bernardino) | 241 | .28 | 48 |
| MH Climate Zone 18 (Palm Springs) | 545 | 0.32 | 96 |
| Average | 241 | 0.22 | 48 |

AC Diagnostic Tune-up

AC diagnostic tune-up savings are based on checking and correcting the refrigerant charge and airflow on central air conditioning (CAC) units and central heat pump units. EPA-certified refrigerant technicians will perform the “AC diagnostic tune-up” (i.e., correct charge and improve airflow) and thereby raise the air conditioning efficiency by approximately 13%.  We will detect leaky Schrader valves with leak detection equipment and replace leaky Schrader valves with new valves and core repair tools.  Measure lifetime is 10 years. Cooling savings estimates are based on DOE-2.2 simulations assuming proper charge and proper airflow improve the air conditioner Energy Efficiency Ratio (EER) by roughly 13% based on average measured savings from seven field studies. The field studies show an efficiency loss of 10-20% for overcharging and 20% for undercharging.  Assuming an equal distribution of over- and undercharging the average efficiency loss is approximately 13%.  The same studies showed an average efficiency loss of 7% for improper airflow across the air conditioning coil. The average combined loss from both problems is approximately 17%.  We only take credit for 13% savings to be conservative

According to the 2001 DEER study savings are calculated as follows with a weighted average being calculated for all mobile homes served, both in terms of location and age of home.

Table 2 Mobile Home AC Diagnostic and Tune-Up

|  | Savings | Peak Demand | Gas Heating |
| --- | --- | --- | --- |
| Climate Zone | kWh/yr | kW | therm/yr |
| MH Climate Zone 9 (Burbank) | 315 | .54 |  |
| MH Climate Zone 10 (San Bernardino) | 496 | .69 |  |
| MH Climate Zone 18 (Palm Springs) | 1173 | 0.99 |  |
| Average | 175 | 0.31 |  |

Mobile Home Programmable Thermostat

Programmable thermostat savings are based on the DEER statewide studies of 2001.  These are found in the DEER worksheet model.  Current Energy Star requirements and specifications for Programmable Thermostats cycle the thermostat past from 12-8 p.m. providing greater savings during the peak demand.  Measure lifetime is 15 years. Through work done on 2002-2003 CPUC programs #171 and #201 analysis of on-site work by EM&V engineering calculated that the Mobile Home Programmable Thermostat has produced a higher therms (in excess of an average of 89 therms) value than DEER.  This amount has been claimed for therm savings.  Average estimated savings are 256 kWh and 0.15 kW and 89 therms per home as shown in Table 3.

Table 3  Mobile Home Programmable Thermostat

According to the 2001 DEER study savings are calculated as follows with a weighted average being calculated for all mobile homes served, both in terms of location and age of home.

|  | Savings | Peak Demand | Gas Heating |
| --- | --- | --- | --- |
| Climate Zone | kWh/yr | kW | therm/yr |
| MH Climate Zone 9 (Burbank) | 373 | .54 | 48 |
| MH Climate Zone 10 (San Bernardino) | 415 | .69 | 58 |
| MH Climate Zone 18 (Palm Springs) | 488 | 0.99 | 52 |
| Average | 256 | 0.15 | 54 |

Water Heating Measures

Water heating measures are modeled using engineering algorithms based on measured data. Modeling assumptions for each measure are discussed below.  Average annual UEC value is 154 therm/yr for individual-unit gas water heaters and 2,598 kWh/yr for electric water heaters.  Estimates of energy consumption by end use, distribution loss, and tank loss are shown in Table 4.  These values are used to develop annual energy savings estimates.

Table 4 Single-Unit Water Heater Energy Consumption by End Use

| End Use or Standby Loss | Electric Water Heater Relative Energy Consumption % | Gas Water Heater Relative Energy Consumption % |
| --- | --- | --- |
| Shower | 26 | 23 |
| Tub | 10 | 9 |
| Sink | 10 | 9 |
| Clothes washer | 18 | 16 |
| Dishwasher | 8 | 7 |
| Pilot Loss | - | 13 |
| Distribution Loss | 16 | 13 |
| Tank Loss | 12 | 10 |
| Total | 100 | 100 |

Water Heater Time Clock

Water heater time clock savings are derived by utilizing known load shapes for water heater usage (peak demand in early morning and evening hours).  The actual savings are derived from turning off the electric water heater during the period of peak demand.  The period of interruption is controlled so that the household does not run out of hot water.  The control of the timer can be set both at the factory and at the site (by the park manager and bidder, should the system operator or utility wish to adjust the peak demand period).

This proposal has been based upon an assumed peak demand period that requires the time clock to turn the electric water heater off during the afternoon peak demand period (e.g., 12 PM until 6 PM).  This corresponds to a low level of demand for a water heater, thus ensuring there will not be a loss of hot water to the customer.  Most peak demand and energy savings during this afternoon interval result from the reduced standby service whereby the water heater thermostat calls for the tank to “turn on” (which occurs nearly 10% of the time during the afternoon peak demand period)

Tank insulation of R-16 overall will greatly reduce savings associated with time clocks.  If the time clock is set to turn off the tank from 12 PM until 6 PM during weekdays and midnight until 4 AM at night, then the savings will be approximately 2.4 percent. Estimated annual energy savings are approximately 91 kWh. Peak demand savings are 0.430 kW as shown in Table 5.

Table 5 Water Heater Time Clock

|  | Estimated Savings |
| --- | --- |
|  | Peak Demand | Electric | Gas |
| Measure | kW | kWh/yr | therm/yr |
| Water Heater Time Clock, Electric Water Heater | 0.430 | 91 |  |

Water Saving Showerhead (2.5 gpm)

Water saving showerhead savings are based on engineering estimates and M&V studies (SoCalGas).  Energy savings are based on assumed pre- and post-retrofit flow rates.  Non-conserving showerheads use greater than 3.5 gpm and water-saving showerheads use 2.5 gpm. Water-saving showerheads are assumed to reduce water flow by 50 percent.  Estimated annual energy savings are 337 kWh and 0.047 kW per showerhead for electric water heaters and 17 therms per showerhead as shown in Table 6.  Measure lifetime is 10 years.

Table 6  Water Saving Showerhead

|  | Estimated Savings |
| --- | --- |
|  | Peak Demand | Electric | Gas |
| Measure | KW | kWh/yr | therm/yr |
| Water Saving Showerhead, Gas (per Showerhead) |  |  | 17 |
| Water Saving Showerhead, Electric (per Showerhead) | 0.047 | 337 |  |

Faucet Aerator

Energy savings are based on assumed pre- and post-retrofit flow rates.  Non-conserving faucet aerators use greater than 3.5 gpm (at a flowing pressure of 80 psi) and water saving faucet aerators use 2.2 gpm (at a flowing pressure of 80 psi).  Water saving faucet aerators are assumed to reduce water flow by roughly 37 percent. Estimated annual energy savings are approximately 33 kWh and 0.005 kW for electric water heaters and 5 therms for gas water heaters.  Empirical studies show similar levels of savings as shown in Table 7  Measure lifetime is 10 years.

Table 7  Faucet Aerator

|  | Estimated Savings |
| --- | --- |
|  | Peak Demand | Electric | Gas |
| Measure | kW | kWh/yr | therm/yr |
| Faucet Aerator, Gas Water Heater (per Aerator) |  |  | 5 |
| Faucet Aerator, Electric Water Heater (per Aerator) | 0.005 | 33 |  |

Lighting Measures

Savings from lighting measures are based on four variables:

- Wattage consumed by pre-existing lamp/fixture (Wpre)

- Wattage consumed by replacement lamp/fixture (Wpost)

- Hours of Operation (H)

- Number of lamps/fixtures (N)

Typical Hours of Operation for Lighting in different space types are summarized below in Table 10.  Savings for typical fixtures installed in our program are shown in Table 11.

Table 10  Lighting Operating Hours by Space Type

| Space Type | Hours of Operation |
| --- | --- |
| Indoor Common Area | 8,760 |
| Indoor Special Use Common | 4,380 |
| Indoor Dwelling Unit | 1,428 |
| Exterior Dwelling Units | 4,380 |
| Exterior Common Area | 4,380 |

*Special Use Areas include those areas subject to periodic occupancy, such as kitchens, game rooms, laundry rooms, and exercise rooms.

Energy Savings for lighting measures are provided for interior and exterior Energy Star CFLs and interior Hardwired Energy Star fixtures.  Savings can be calculated accurately if the above variables are known and are used in the following equation.  An average savings rate is extrapolated from the following Table as calculated from the DEER studies.

Calculated Energy Savings = N ( H ( (Wpre - Wpost )

Table 11  Lighting Savings Mobile Homes and Parks

| Measure | Pre Watts | Post Watts | Operation Hours | Measure Life Years | Peak Savings KW | Electric Savings kWh/yr |
| --- | --- | --- | --- | --- | --- | --- |
| Energy Star CFL Interior- | 60 | 15 | 1,428 | 7 | 0.08 | 72 |
| Energy Star CFL– Interior | 100 | 25 | 1,428 | 7 | 0.08 | 128 |
| Energy Star Hardwire Fixture CFL– Interior | 120 | 30 | 1,428 | 16 | 0.08 | 264 |
| Energy Star CFL Exterior | 100 | 25 | 4,380 | 7 | 0.08 | 328 |
| Energy Star Hardwire CFL Exterior | 80 | 20 | 4,380 | 16 | 0.08 | 328 |
| Energy Star Interior—Common | 100 | 25 | 8,760 | 7 | 0.08 | 355 |

## B. Deviations in Standard Cost-Effectiveness Values

This proposal is based upon the use of DEER data for measures and applications which pertain to the mobile home sector.  Both American Synergy (and our prime sub contractor UCONS), are recognized for our conservative and rigorous use of deemed savings in our energy efficiency programs.  In many instances, we have used lower assumptions (than DEER) when available EM&V studies (performed by consultants or by independent third parties) indicated DEER levels may not be realized for the mobile home application we expected to provide.  For that reason, we have consistently received high marks by utilities and by regulators in adhering to this conservative approach.  Long term energy savings are assured when ex poste evaluations demonstrate that proposed deemed savings were met or exceeded.

We have claimed 89 Therms savings for use of a programmable thermostat.  These savings are supported through work done on 2002-2003 CPUC programs #171 and #201 analysis of on-site work by EM&V engineering calculated that the Programmable Thermostat has produced a higher therms value than DEER (in excess of an average of 89 therms).  From the EM&V field examinations and subsequent testing and analysis of savings data, it was also found that the therms savings for Duct Test and Seal proved to be higher than the deemed savings or those calculated in the DEER study.

In addition, we continue to use 17 therms for gas showerheads (although the DEER value for some residential applications is 9 therms). 17 therms was the deemed basis for our current third party mobile home program for SCE and SoCal Gas.  The final EM&V report for our current program has not been released, but the average savings from the nearly completed in-field measurements by our independent consultants (Robert Mowris and David Robison) demonstrate that our mobile home program gas showerhead savings will exceed 20 therms.

Other than the deviations noted above, there were no material deviations in Standard Cost Effectiveness Values from imputed DEER values and engineering studies.

## C. Rebate amounts (not applicable)

## D. Activities Description

The following activities provided through this program will provide supplemental benefits (to the quantified benefits detailed in the WORKBOOKS: Audits; Education materials left at time of installation; Diagnostics-only; on-going training through neighborhood workshops; Supplemental water and sewer programs

In accordance with instructions to bidders, all dollar (costs and benefits) from non measurable services have been excluded from our WORKBOOK summary used in the calculation of the project TRC and participant test.  Only direct install costs have been identified in the “Measurable EE activities” worksheet.

# Section V  Goals

The following table provides a brief review of our goals for 2002 (Mobile home program #171-02).  The quarterly reports we have filed with the CPUC demonstrate that we will achieve, on time, the following savings:

| Number of Customers Served in 2002-2003 Program #171-02 | 6,000 | 6,000 |
| --- | --- | --- |
| The Net Energy Effects |  |  |
| The Net Coincident Peak kW | 4,000 kW |  |
| The Annual kWh Savings | 6,000,000 kWh |  |
| The Annual Therms Savings |  | 175,000 Therms |

Our ability to conclude all phases of the 2002/3 goals on or before December 31, 2003 is an indicator that our modest goals for 2004/5 are attainable.  In brief, we are mindful of the primary and secondary selection criteria for bids and have provided details with our submittal dealing with these criteria.  For the current solicitation, our Team has already identified over 75,000 mobile home units in local areas that can benefit from the program.  The current utility programs proposed for 2004 and 2005 do not address some of the principle market barriers which will impact the areas identified by this program.  Long-term savings will be achieved through this program for the following reasons:

- Use of proven and reliable energy savings measures which customers have accepted and which provide the best economies of energy savings for the investment.

- A proven administrative team.  This team consistently met or exceeded milestone benchmarks in the 2002-2003 third party program, producing savings on and ahead of schedule.  We have submitted the monthly and quarterly reports on time in accordance with Commission policy.

- A proven delivery team.  The delivery teams are certified technicians with a high level of competency.  This team worked well with an aggressive and thorough EM&V sub-contractor improving quality assurance and production processes.  It delivered the estimated savings as outlined in its proposal, at times installing more items than were called for to be sure to hit the savings originally outlined.

- A collaborative approach in working with utilities, communities, the Commission and the most important party, the CUSTOMER

Program Objectives (measurable results) are:

- By December 31, 2005, retrofit approximately 8,000 to 11,000 HTR mobile homes.

- Average savings per typical program participant is projected to be approximately 1,800 kWh, and 111 therms  for a total average bill reduction of at least $300.00-400.00 per household. (actual savings will vary based on occupant’s energy use, as well as local energy prices). Energy and peak demand savings can be determined by using savings data from Table 4.1 times the applicable measure penetration rates identified for this program.

Secondary Objectives for this program are:

- It must be cost effective.

- It must provide much needed energy efficiency measures to the hard-to-reach mobile home parks and residence.

- Inspection and Quality Assurance processes should provide a high level of confidence to CPUC and local IOUs.

- Evaluation (including billing analysis) will be performed to provide support for future program design and performance reliability.

# SECTION VI

# Program Evaluation, Measurement and Verification

## A.  The Evaluation Approach

The EM&V portion of our bid is to continue to perform a rigorous program evaluation in full accordance with IPMVP procedures.  We have fully complied with all utility and CPUC requirements on all past and current public purpose funded programs.  Where measured results have so warranted, we have increased our deemed savings assumptions above 2002 levels, but in no event above DEER established levels without appropriate notice in the DEVIATION portion of this proposal. In accordance with the requirements of the RFP, we have recommended that two unassociated and unrelated independent contractors be considered to support the EM&V objectives for this program.  These individuals would provide independent and objective evaluation of the program results.  They would work with the utilities and independent EM&V consultant of the CPUC as directed.

The third-party evaluation will consist of both a process and an impact evaluation. The EM&V evaluation will be conducted throughout the program period and consists of the following elements.

We would suggest eight tasks will be undertaken by the EM&V effort. The eight tasks are briefly summarized as follows:

- EM&V Plan

The EM&V Plan will contain a detailed description of all activities required to complete

the EM&V study.

- Tracking Database

The tracking database will provide a listing of jobs that are completed including statistical samples of on-site measurements of installed measures.  We will provide data from their program tracking database for evaluation purposes.

- Sample Design

A statistical sample design will be used to select a sample of customers or projects from

the utility local program participant populations.  Samples will be selected

to obtain a reasonable level of precision and accuracy at the 90 percent level per CPUC

Energy Efficiency Policy Manual (EEPM).  The 90/10 confidence might need to be

adjusted downward for some measures that have a high degree of variation.

- Process Surveys

Process surveys will be used to evaluate what works, what doesn’t work, and customer

satisfaction.  Process surveys will also obtain suggestions for improvement in the

program's services and procedures.  Market research and saturation data will be used to

assess whether or not there is a continuing need for the program.

- On-Site EM&V Inspections

On-site EM&V inspections and measurements will be used to assess deemed energy and

peak demand savings.  Site visits will be also be used to verify that measures are properly

installed.  Sites in the statistical sample will include spot and short-term measurements.

- Statistical Analyses

Statistical analyses will be used to extrapolate measurements of baseline and measure

assumptions (i.e., duct leakage reduction, etc.) from the sample level to the program

population.

- Progress, Draft and Final Reports

Progress, draft, and final reports will include a description of the study methodology and

all deliverables as per the CPUC EEPM.  The reports will provide results of the impact

evaluation including gross and net energy and peak demand savings for each measure

and the program as well as results.

## B.  Potential Contractors

The CPUC and the IOU administrator will have direct access to these subcontractors.  We will make every effort to ensure that these subcontractors are allowed to conduct their work in an independent manner.  The two contractors we wish to propose for consideration to submit bids would be:

- Robert Mowris and Associates

- Stellar Processes

Each firm has extensive knowledge of both utility and non-utility programs for the hard to reach sectors and is well respected as independent program evaluators.  The bidder has provided a budget for a comprehensive third party evaluation.

# SECTION VII  Qualifications

## A.  Primary Implementers

American Synergy Corporation

Mr. David C. Clark,  CEO and Owner

Mr. Clark has been actively involved in energy efficiency programs in the State of California for close to 20 years.  He has worked with all four major IOU’s with a wide variety of programs.  He has a bachelor’s degree in Accounting and Business from Brigham Young University.  He has served as the President of the Insulation Contractors Association of California.  He has also served on numerous governmental committees regarding energy efficiency programs.

Mr. Steven R. Shallenberger,  President and Owner

Mr. Shallenberger has served on the Board of Directors for American Synergy Corporation.  Steve is a member of the Executive Committee and Board of Directors and also the World President’s Organization. He is actively involved in working with the Commission and Utilities in serving the energy efficiency needs of the Small Commercial and small commercial markets.  He graduated in Accounting from Brigham Young University and from the Harvard Business School.

Mr. Douglas Price, Chief Operating Officer (Central and Northern California) and Project Manager. Mr. Price has never missed a benchmark and has maintained 95% + pass rate on workmanship. He has been with the firm for 18 years with a strong background in managing work crews in attic and groundwork, minor home repairs, multifamily, duct testing and sealing, and energy efficient lighting. He organized the quality assurance and training of our crews.  Mr. Price has worked in implementing energy efficiency programs with all four major utilities in the State of California.  Doug is assisted in this work by Rod McPherson, Kent Walker, Scott Price, and Roger Thornton and a team of talented associated.

Mr. Sal Vaccaro, Chief Operating Officer (Northern California) and Project Manager

Mr. Vaccaro graduated from Santa Clara State University in History and Finance. He is a member of the Asbestos Hazard Emergency Response Act Board and California Department of Health Services. He is a specialist in structural design, energy efficiency, and hazardous waste removal. Mr. Vaccaro is a member of the board of the California Environmental Information Association (CEIA).

Mr. Vaccaro, a former professional baseball player, has a solid reputation for getting the job done with a commitment to serving the customer with satisfaction and quality. As President of Synergy Environmental Services, a sister company to American Synergy, he has established himself as someone that gives attention to the finer details of completing jobs with the highest standards on schedule. Mr. Vaccaro has been with Synergy since 1989.

Mr. Jim Amos, Marketing and Energy Specialist

Mr. Amos has been with American Synergy since 1987. He has supervised hiring, training, and managing of all energy specialists. He has interviewed candidates for energy specialists, organized  and conducted daily meetings with energy specialists. He made sure that canvassing reports and marketing reports were kept up to date and that forms and uniforms were in stock. He does quality assurance on the education through ride along with energy specialist and phone quality assurance with the customer. Mr. Amos implements marketing strategy in order to maximize productivity in completing energy efficiency contracts.  He is joined in Marketing and Outreach by Jeremy Price, Kent Walker and Rod McPherson.

Mr. Russell Jacobsen, CPA

Mr.  Jacobsen has been associated with the Synergy Company for 14 years as a consultant and accountant. He worked with Pacific Bell for 16 years in corporate accounting. He is now the Controller and CFO for the Synergy companies. He graduated in Accounting from Brigham Young University. He is a CPA in the State of California.

American Synergy  Significant Projects

CPUC Local Area Programs 2002-2003, Programs #171-02 and #201-02.

Statewide IOU Multifamily and Small Commercial Express Efficiency Programs

Energy Partners 1988-1996, 2001-2002

SCE/SCG 1999, 2000, 2001 RCP Multi-Family Programs

SCE/SCG 1999-2001 RCP Programs

SCE/SCG 2001 Summer Initiative Program

SCE-SCG Zip and Weatherization Programs 1983-1999.

SCE-SCG RCP Single Family Insulation

SCE-SCG RCP Multi-Family Programs

SCE-SCG 2001 Summer Initiative Program

SCE-SCG Express Efficiency Program

City of Palo Alto 1999-2001:  Windows and Insulation Programs

SDGE 3rd Party Hard to Reach Mobile Project

SDGE RCP Single Family Programs

SDGE RCP Multi-Family Programs

SDGE 2001 Summer Initiative Program

## B.  Subcontractors

American Synergy will be the primary implementer.  This is a turnkey project for which we have chosen Cal UCONS to be our principle sub contractor.  A summary of UCONS’ capabilities and key staff is provided.  Our two companies have successfully worked together in prior hard to reach California programs.  Our ability to work collaboratively to bring new programs to underserved market sectors is established.  We plan to stay directly involved with all phases of this project to ensure continuity and success.  It is not anticipated that additional parties or sub contractors will be required to support this program.

CAL-UCONS, Inc.

UCONS is a national leader in the development and implementation of Small Commercial conservation programs focusing upon under-served sectors, especially renters and multifamily customers. In the past 20 years, UCONS has provided direct install energy efficiency programs to over 300,000 renters and multifamily customers in California, Texas, Utah, Washington and Oregon (more than any contractor and many than most utilities). As an executive board member and co-chair of Small Commercial programs for NAESCO (National Association of Energy Service Companies) Mr. Eckhart and UCONS have been an active voice in the advancement of Small Commercial program nationally and in the development of appropriate M&V programs for measuring performance in Small Commercial sectors.

Mr. Thomas G. Eckhart,  Chief Executive Officer UCONS, has 37 years experience in the design, development and implementation of demand and supply-side resource programs. A licensed California professional engineer and contractor, Mr. Eckhart graduated from US Maritime Academy in 1965 and began his career with the N/S Savannah before joining Westinghouse Electric and Portland General Electric Company. He holds an M/S in nuclear science and an MBA degree. He has coordinated the development and marketing of independent power projects for NEPCO in the United States and Canada. He also directed Puget Sound Energy’s award-winning Small Commercial conservation programs prior to joining UCONS.

Mr. Eckhart is responsible for assuring the development of cost effective program designs, which will meet the needs of customers. He also manages overall project accountability and EM&V requirements against contract requirements for resource savings and cost effectiveness.

Ms. Shani Taha, Executive Vice President, Marketing & Operations, served for two years as marketing advisor to UCONS before joining our management team.  Her professional credentials include service as Deputy Superintendent with the Hardy administration at Seattle City Light, the nation’s seventh largest municipal utility.  There she was responsible for retail operations and demand-side resource planning and program implementation.

Ms. Taha is nationally recognized for her leadership in helping the public power industry address issues of conservation, competition and customer service.  She served on EPRI’s  Research Advisory Committee, was an officer and Chair of the American Public Power Association’s Customer & Energy Services Committee and participated in several international delegations on demand-side management and integrated resources planning.

Ms. Taha will be responsible for coordinating customer and employee relations and education activities to include the implementation of marketing and education strategies and to maintain effective communication among customers and employees alike.

CAL-UCONS, Inc.  Significant Projects

•	Puget Sound Energy

Bellevue, Washington

Since 1995, UCONS provided space and water heating conservation services to over 11,000 Puget Sound Energy multifamily customers. This program provided comprehensive inspection and repair of areas below the floor including: cross-over duct repair & replacement; duct sealing; rodent and vapor barrier repair and replacement.

In addition, customers were provided new energy efficient set-back thermostats; low flow showerheads, faucet aerators and pipe wraps. the program provided customers with water and sewer savings of 25,000,000 gallons annually and reduced electrical usage by 3 aMW.

•	PacifiCorp

Portland, Oregon

During 1995 and 1996, UCONS provided over 30,000 multi-family dwellings in Oregon with energy conservation measures. This program included the delivery, installation, service and monitoring of floor and ceiling insulation measures; compact fluorescent lights (CFLs); line-voltage thermostats; low flow showerheads, faucet aerators and pipe wraps. This program provided Pacific’s customers with over 7 aMW of new conservation resources. Water conservation savings of 69,000,000 gallons annually were also achieved.

•	Portland General Electric

Portland, Oregon

In late 1996 PGE had a conservation shortfall of nearly 4 aMW. They turned to UCONS in September 1996 to meet their goal. In the last four months of 1996, UCONS provided 13,000 multi-family dwellings with energy conservation measures. This program included the delivery, installation, service and monitoring of floor and ceiling insulation; low flow showerheads, faucet aerators, pipe wraps, and efficient, line-voltage thermostats. This program provided PGE customers with over 4 aMW of new conservation resources. Water conservation savings of 30,000,000 gallons annually were also achieved.

UCONS participated in a 1.5 aMW comprehensive multi family program for PGE in May 2002. This hard to reach program reached 10,700 tenants and provided lighting, floor and ceiling insulation, heat anticipating thermostats and infiltration measures.

•	Southwestern Public Service

Amarillo, Texas

UCONS was selected in 1997 by SPS to provide a water heating DSM peak load reduction program to 30,000 Small Commercial customers throughout their service territory. This program focused on fixed and low-income customers residing in both single and multi-family dwellings. This performance-based program was completed in July 1999. It will provide up to 4MW of summer peak demand savings.

•	Pacific Gas & Electric

San Francisco, California

CAL-UCONS, Inc. participated in SCE-SCG’s initial RES-SPC in 1998 and completed all phases on this program within 4 months of contract award. 	UCONS was the principle designed of the RES-Team program and participated in SCE-SCG’s Summer Initiative Program in 2000.

•	Southern California Edison

Rosemead, California

CAL-UCONS, Inc. participated in SCE’s initial RES-SPC in 1998 and completed all phases of this program within 8 months of contract award. UCONS has also participated in SCE’s 1999 and 2000 RCP programs and SCE’s 2000 SIP program. UCONS is currently supporting the Small Commercial third party program under CPUC contract #

## C.  Resumes

A summary of professional credentials have been provided, above, for each management position.

# SECTION VIII  2004-2005 Budget

| Item: Two-Year Budget | SCE | SCG | Combined Budget |
| --- | --- | --- | --- |
| Administrative Costs |  |  |  |
| Managerial and Clerical (administration, scheduling, customer service) | $547,500 | $281,750 | $829,250 |
| Human Resource Support and Development | $109,100 | $54,722 | $163,872 |
| Travel and Conference Fees | $27,885 | $15,015 | $42,900 |
| Overhead (General and Administrative) | $143,975 | $77,525 | $221,500 |
| Total Administrative Costs | $828,510 | $429,012 | $1,257,522 |
| Marketing/Advertising/Outreach Costs | $488,925 | $195,775 | $684,700 |
| Direct Implementation Costs | $3,316,918 | $1,035,735 | $4,352,653 |
| Evaluation Measurement and Verification Costs |  |  |  |
| EM&V Labor and Materials | $175,880 | $85,050 | $260,930 |
| EM&V Overhead | $66,862 | $34,262 | $101,124 |
| Total Evaluation Measurement and Verification Costs | $242,662 | $119,312 | $361,974 |
| Total Budget | $4,877,015 | $1,778,834 | $6,655,849 |
| Potential Performance Award | $341,391 | $124,518 | $465,909 |

# Footnotes

A leakage ratio of 0.0006 is typical for an average residence, see page 2.86, DOE-2 Supplement, Version 2.1E, Lawrence Berkeley Laboratory, Berkeley, CA  94720, 1993.

Conditioned floor area of 1,000 ft2 is an average of singlewide and doublewide mobile home units. Baseline values for doublewide mobile homes (i.e., 1,440 ft2) would be greater than the values shown in Table 2.3.

EPA Certified Refrigerant Technicians as required by 40CFR part 82 subpart F.

National Energy Savings Potential from Addressing HVAC Installation Problems, Chris Neme, Vermont Energy Investment Corporation, John Proctor, Proctor Engineering, Steve Nadel, ACEEE, prepared for US Environmental Protection Agency, March 1998. Studies include: Blasnik, M., Assessment of HVAC Installations in New in SCE’s Service Territory, EPRI, 1995; Hammarlund, J., Enhancing the Performance of HVAC and Distribution Systems in Residential New Construction, Proceedings of 1992 ACEEE Summer Study on Energy Efficiency in Buildings, Volume 2, pp. 85-87; Neme, C., Southern Maryland Electric Cooperative Power Saver Home Program Impact Evaluation, 1997; Palani, M., O’Neal, D., Haberl, J., The Effect of Reduced Evaporator Air Flow on the Performance of a Residential Central Air Conditioner, The Eighth Symposium on Improving Building Systems in Hot and Humid Climates, 1992; Parker, D., Impact of Evaporator Coil Air Flow in Residential Air Conditioning Systems, FSEC-PF-321-97; Proctor, J., et al, Performance of Reduced Peak kW Air Conditioner at High Temperatures and Typical Field Conditions, 1998; Rodriguez, A., The Effect of Refrigerant Charge, Duct Leakage, and Evaporator Air Flow on the High Temperature Performance of Air Conditioners and Heat Pumps, EPRI, 1995.

Market Segment Analysis based on the 1991 Residential Weatherization Survey, prepared by Business Economic Analysis and Research and RER, prepared for Southern California Gas Company, 1992.

California Energy Demand: 1995-2015, P300-95-008, California Energy Commission, 1516 Ninth Street, Sacramento, CA  95814, 1995.

These values are averages taken from the following studies: Water Conservation in California, Bulletin 198-84, California Department of Water Resources, Sacramento, CA, July 1984. Supply Curves of Conserved Energy: A Tool for Least-Cost Energy Analysis, A. Meier, T. Usibelli, Proceedings of Energy Technology Conference, Government Institutes Inc., Rockville, MD, pp. 1264-1265, March 1986.  Residential Hot Water Use Patterns, D. Stevenson, Canadian Electrical Association, Report #111U268, Montreal, July 1983. Water Heater Innovations, Progressive Builder, Howard Geller, pp. 24-26, September 1985.

Peak demand period kW savings are based on water heater load shapes for Northern California and IPMVP EM&V studies for UCONS’ peak demand projects in California (2000 SIP) and Texas. Average energy savings for time clocks are based on 6 hours per day (noon until 6pm) 5 days per week. Total time “off” is approximately 20 percent multiplied by 12 percent total tank loss for 2.4 percent total energy savings.

Measured flow rate reduction of 2.7 gpm or 50% is based on random measurements of 3,850 showerheads in a population of 126,639 showerheads. The pre-retrofit mean flow rate was 5.1 gpm and the post-retrofit flow rate was 2.4 gpm. See Residential Standard Performance Contract Program Database Manual, prepared for Southern California Gas Company, prepared by Robert Mowris & Associates, July 2000.

# Text boxes

Rulemaking 01-08-028

Pursuant to Decision 03-08-067