Section 13

HUMAN RESOURCES

Human Resources handles recruitment, hiring, testing, training, time-reporting, benefits, and personnel information for staff.  Human Resources is undergoing transformation, possibly to become a division with a director reporting to the Executive Director.  Both the Human Resources Interim Project Manager, and Human Resources Manager report to the Executive Director.

TWO TO THREE YEAR OUTLOOK

In 1998, we will continue focus on the objectives laid out in our 1997 Business Plan. Our major focus in 1997 was on outreach to achieve a collaborative partnership with CPUC line divisions, and to be proactive in meeting their expressed needs.   Several critical projects were completed in support of this objective, including streamlined examination and recruitment processes.

During our 1997 survey of Management, we learned that the Divisions’ most critical needs from Human Resources are leadership, communication, and developing alternative strategies to meet hiring needs in a more efficient manner.  During 1998, we will work with our process consultant to address these issues further, and develop more detailed objectives.

1998 HUMAN RESOURCES OBJECTIVES

Objective A:	      Streamline and Improve all Human Resources

Transactions Processes

Strategy 1	Work with a process consultant and division liaisons to examine systems and processes within human resources operation, and develop strategies for creating efficiencies to streamline and integrate critical processes and improve accuracy and timelines of available information by automating these functions.

(February)

Strategy 2	Appoint a dedicated, full-time position control specialist to 	oversee roster maintenance and Schedule 8 production.

(March/April)

Strategy 3	Develop and implement position control database on Oracle to

integrate position information which will allow us to issue

management reports from a single source in a more timely and

efficient manner.                                                                   (April)

Strategy 4	Appoint a Transactions Supervisor to streamline personnel

transactions processing and to provide day-to-day supervision of

the transactions unit.                                                (March/April)

Strategy 5 	Designate a full-time Workers Compensation/Return to Work

Coordinator to manage workers’ compensation claims and develop strategies for early return to work of employees injured on the job.                                                                      (March/April)

Objective B:    Improve Human Resources Interaction with Division

Management and Staff and Control Agencies

Strategy 1	Each personnel analyst will conduct monthly meetings with their assigned division(s) to review status of projects and attend to the divisions’ Human Resource concerns.                              (Ongoing)

Strategy 2:	Communicate Human Resource policies and procedures by publishing “on-line” an updated edition of the HR portion of the EE handbook.                                                                        (May)

Strategy 3	Refill the vacated Labor Relations Analyst position.  An examination to refill this position is currently in process and interview will be held at the end of February.

Strategy 4	Interaction with the control agencies to be enhanced by engaging in pro-active series of meetings with control agency staff assigned to CPUC.

Objective C:	  Testing/Examining Reform

It is the Commission’s objective to ensure that selection decisions for all positions take place within the spirit of the Consent Decree, and that they result from a rigorous selection process which is fair and documented.  A number of strategies have been established for validating exams and for streamlining the examination process.

Strategy 1	Appoint a Testing Manager.  Interviews will be scheduled for the week of February 23, 1998 to complete the selection process for this position.

Strategy 2	Conduct and administer critical examinations on an on-going

basis in concert with filling key vacancies and ensuring

promotional opportunities to retain key staff.

Strategy 3	Exam Validation:   Work with Testing Manager or approved

selection consultant to develop a strategy for creating validated

exams for all existing classifications.                           (June 1999)

Strategy 4	Testing Strategies:   Develop alternative strategies/techniques to

expedite components of the Commission’s existing testing process.                                                                        (June 1999)

Strategy 5	Automated Testing:   Explore options for automating the testing

function in order to streamline exam processes.           (July 1998)

Strategy 6	Testing Policies:   Develop and disseminate written department

testing policies and procedures.   Develop methodologies for

evaluating effectiveness of testing strategies.             (March 1999)

Strategy 7	Augment HR Examination staff to administer needed examinations:  Develop an interagency or inter-jurisdictional agreement with a governmental agency with a well-established testing and validation program to provide support and validation services currently not available from the State Personnel Board.

Objective D:     Staffing/Recruitment       Conduct vigorous recruitment efforts to enable the Commission to fill all its vacancies so that line programs

can meet their business plan objectives.

Strategy 1	Appoint two project managers to conduct a vigorous recruitment

campaign addressing critical program vacancies and to review our hiring processes.

Strategy 2	Incorporate program resources into planned recruitment activities

to maximize recruitment efforts.

Strategy 3	Project Manager to give status reports to Directors to insure

proper monitoring of the recruitment efforts.             (Bi-monthly)

Objective E:    Develop a Training Program Responsive to the Changing

Job Demands of CPUC staff

Strategy 1	Long-term Needs: Identify current and long-term program needs by working with senior management. Report to management team.                                          (September 1998)

Strategy 2	Skills Survey:  Identify current employee skill base by conducting a skills survey.                              (September 1998)

Strategy 3	Skill Development:  During the first half of 1998, identify needed areas for skill development to meet changing program needs. Skills survey will be used on a short-term basis; performance evaluations will be used once they become formalized in 10/96 and 3/97.

Strategy 4	   Training Resources:   Identify external resources for providing

formal training.                                                        (June 1998)

Strategy 5	Staff Development:   Work with HR Task Force to create informal development opportunities such as rotation, training and development assignments).                       (December 1998)

Strategy 6	    Skills Database:   Identify in-house resources by using skills

survey to create a skills database.                   (September 1998)

Strategy 7	Leadership Training:  Develop resources for providing managers with ongoing training in effective leadership.

(December 1998)

Strategy 8        Process individual employee training requests.           (Ongoing)

Strategy 9	    Develop methodology for tracking effectiveness of training

Programs.                                                                (June 1998)

Strategy 10	    Automate training function to expedite processing of training

requests and facilitate management reports as required under

the Consent Decree.                                                 (June 1998)

Strategy 11	  Reactivate the Training Steering Committee.  Convene first

meeting in March 1998.

Objective F:   Maximize use of current HR resources by developing

performance contracts between HR and Divisions to prioritize HR workload.

Objective G:   Evaluate Classification Structure to implement Vision 2000

Strategy 1	Establish a Task Force to review classifications to incorporate needed changes to reflect reorganization and Vision 2000 concepts.

Strategy 2	Review and identify processes for participation in the State Personnel Board’s Demonstration Project Authority. Assess suitability of Broad Banding to current CPUC structure and objectives.

HUMAN RESOURCES KEY PERFORMANCE INDICATORS

Within the strategies to achieve each objective are deliverables with due dates, and these serve as measures of Human Resources performance.

RESOURCES

| Objective | Authorized | Filled | Vacancies |
| --- | --- | --- | --- |
| A - Streamline and Improve all Human Resources Transactions Processes | 13 | 13 |  |
| B - Improve HR Interaction with Division Management and Staff |  |  |  |
| C - Maximize use of current HR resources |  |  |  |
| D - Evaluate classification structure to implement Vision 2000 Recruitment |  |  |  |
| E - Testing/Examining | 4 | 3 | 1 |
| F - Recruitment | 1 | 1 * |  |
| G - Training | 1 | 1 |  |
| Totals | 19 | 18 | 1 |

*  Position temporarily filled by person on loan from Public Advisor’s Office

Impacts

At this time, since we do not expect an augmentation to our staff, Human Resources plans to redirect current work among existing staff and improve processing efficiencies in order to accomplish all established objectives.