IV.	TIMELINE

Task		Description					Begin		End

Work Effort 1:  Public Outreach Campaign

Task 1.1	Market Research/Polling

Pre-poll/Market Research			Sept 00	Oct 00

Post-poll					Aug 01		Sept 01

Task 1.2	Development of Campaign Theme		Sept 00	Nov 00

Task 1.3	City outreach					Sept 00	Apr 01

Task 1.4	Television Commercial Spots

Develop					Nov 00		Feb 01

Run						Apr 01		Aug 01

Task 1.5	Direct mail

Develop					Dec 00		Mar 01

Run						Apr 01		Aug 01

Task 1.6	Radio

Develop					Mar 00		Apr 01

Run						May 01	Aug 01

Task 1.7	Billboard/Bus/Print Advertisements

Develop 					Feb 01		Mar 01

Run						Apr 01		Aug 01

Task 1.8	Website

Development					Sept 00	Dec 00

Launch						Dec 00		Aug 01

Task 1.9	Verification energy demand reduction

Pre-research					Oct 00		Nov 00

Post-research					Sept 01	Oct 01

Task 1.10	Summary report				Sept 01	Oct 01

Work Effort 2:  City Efficiency Outreach and Incentive Package

Task 2.1	Establish subsidy criteria and procedures	Sept 00	Nov 00

Task 2.2	Develop energy upgrade package		Sept 00	Nov 00

Task 2.3	Initial ID of partner cities			Oct 00		Nov 00

Task 2.4	Training and coordination with cities		Dec 00		Feb 01

Task 2.5	Document upgrade achievements		Apr 01		Aug 01

Task 2.6	Summary report				Sep 01		Oct 01