| EXPEDITED QUALIFYING FACILITY RESTRUCTURING DOCKET (“EQFRD”) TIMELINE (Days from Filing to Approval) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Revised to Reflect Consensus from Workshop |  |  |  | No Substantive Protests appear |  | Substantive Protests appear and are resolved by workshop |  | Substantive Protests appear and are not resolved by workshop |  | Factual or technical issues cannot be resolved after workshop in writing & substantive opposition remains, ALJ may convert the EQFRD into a conventional application by written ruling |
| - Utility Files QF Contract Modification |  |  |  | 0 |  | 0 |  | 0 |  | 0 |
| - Commission schedules contract modification on Daily Calendar |  |  |  | 1 |  | 1 |  | 1 |  | 1 |
| - Commission Schedules Workshop (10-25 days after protest filing deadline) |  |  |  | x |  | x |  | x |  | x |
| - Comment Period (within 20 Days) |  |  |  | 1-20 |  | 1-20 |  | 1-20 |  | 1-20 |
| - Protests & Discovery Period (within 20 days) |  |  |  | 1-20 |  | 1-20 |  | 1-20 |  | 1-20 |
| - If no Substantive Protests appear, ALJ Cancels workshop |  |  |  | x |  |  |  |  |  |  |
| - Responses to Protests (within 10 days from Protest) |  |  |  |  |  | 2-30 |  | 2-30 |  | 2-30 |
| - Written Objections to Discovery Requests (within 5 working days) |  |  |  |  |  | 2-27 |  | 2-27 |  | 2-27 |
| - Responses to written Objections to Discovery Requests (10 working Days from orig Disc. Req) |  |  |  |  |  | 3-34 |  | 3-34 |  | 3-34 |
| - Commission Workshop (10-25 days after protest filing deadline) |  |  |  |  |  | 30-45 |  | 30-45 |  | 30-45 |
| - Written Resolution of Factual or technical issues still disputed after Workshop (15 days) |  |  |  |  |  |  |  | 31-60 |  | No |
| - ALJ prepares Proposed Decision (PD) with Assigned Commissioner input (within 10 days) |  |  |  | 21-30 |  | 31-55 |  | 32-70 |  | ALJ may convert to conventional application |
| - Delegated Assigned Commissioner Approves PD |  |  |  | 21-30 |  | 31-55 |  | 32-70 |  | N/A |
| - Assigned Commissioner circulates draft to other Commissioners and other parties (within 5 days) |  |  |  | 21-35 |  | 31-60 |  | 32-75 |  | N/A |
| - Decision scheduled to next Commission meeting's consent agenda (can take up to 2 weeks to get on schedule) |  |  |  | 21-49 |  | 31-74 |  | 32-89 |  | N/A |
| - Commission Approves PD as part of Consent Agenda (approx 2 weeks after scheduling occurs) |  |  |  | 35-63 |  | 45-88 |  | 46-103 |  | N/A |
| - Approval Time in Months |  |  |  | 1 to 2 |  | 1 ½ to 3 |  | 1 ½ to 3 ½ |  |  |