Pacific Bell

OSS Master Test Plan

The California Public

Utilities Commission

Version 3.0

June 28, 1999

TABLE OF CONTENTS

1.	DOCUMENT UPDATES	1

1.1	Master Test Plan Change Control	1

1.2	Reasons for re-issue and changes	1

2.	EXECUTIVE OVERVIEW	2

3.	INTRODUCTION	4

3.1	Purpose and Goals	4

3.2	Scope	5

3.3	Audience	8

3.4	Open Issues	8

4.	ENVIRONMENT	9

4.1	Architectural Blueprint	9

4.1.1	Account Environment	10

4.2	Operations Support Systems (OSSs)	10

4.2.1	Pre-Ordering	10

4.2.2	Ordering	12

4.2.3	Provisioning – Backend Systems	14

4.2.4	Maintenance and Repair	14

4.2.5	Billing and Usage – Backend Systems	15

4.2.6	End Users	17

4.2.7	Network	17

4.3	Test Environment Management	18

4.3.1	The Test Environment Checklist	18

4.3.2	Environmental Change Management	18

4.3.3	Environment Needs	19

4.3.4	Environment Cleanup	21

5.	ADMINISTRATIVE PROCESS	22

5.1	Timeline	22

5.2	Roles and Responsibilities	23

5.2.1	Commission	24

5.2.2	Pacific Bell	24

5.2.3	Technical Advisor to Commission Staff	25

5.2.4	Test Administrator/Manager	26

5.2.5	Test Generator	27

5.2.6	CLEC Network Element Providers	27

5.2.7	The Technical Advisory Board (TAB)	28

5.2.8	The End Users	28

5.3	Management of Tests	29

5.3.1	The Test Administrator/Manager	29

5.3.2	Daily Report	30

5.3.3	Test Metrics	32

5.3.4	Problem Reporting Procedures	33

5.3.5	Escalation Process	33

5.3.6	Test Management Jeopardy Process	34

5.3.7	Change Control Process	35

5.3.8	Risk Management	35

6.	REQUIREMENTS AND ASSUMPTIONS	37

6.1	Interface Flow-Through Development Requirements	37

6.2	LSC/LOC Scalability Requirement	38

6.3	Functionality Test Requirements	38

6.3.1	Test Scenario LSR Coverage Process Review	39

6.3.2	Scenarios	41

6.3.3	Types of Orders	43

6.3.4	Features, Feature Compatibility’s and Directory Listings	44

6.3.5	Processes	46

6.4	Capacity Testing Requirements	53

6.4.1	Capacity Test for Pre-Ordering	53

6.4.2	Capacity Test for Ordering	54

6.4.3	Capacity Test Volume	54

6.4.4	Capacity Test Mix	55

6.4.5	The Scalability Analysis	57

6.5	Test Evaluation Requirements	58

6.5.1	Test Documentation Requirements	58

6.5.2	Success Criteria	61

6.5.3	Test Populations and Performance Measure Computation	64

6.5.4	Test Data Collection and Management Issues	66

6.5.5	Test Accounts/End User Data	67

6.5.6	Test Centers	68

6.6	Assumptions	71

6.6.1	General	71

6.6.2	Environment	73

6.6.3	Staffing	74

6.6.4	Functionality Testing	74

6.6.5	Capacity Testing	76

7.	FUNCTIONALITY TEST PROGRAM	77

7.1	Organization Of Functionality Test Section	77

7.1.1	Goals of the Functionality Test	78

7.1.2	Roles and Responsibilities	78

7.1.3	Functionality Test Overall Process	79

7.2	Entrance Criteria to Functionality Test Planning and Preparation Phase	80

7.3	Functionality Test Planning and Preparation Phase	81

7.3.1	Functional Test Planning and Preparation Entrance Criteria	81

7.3.2	Functional Test Planning and Preparation Activities	81

7.3.3	Functional Testing Planning and Preparation Exit Criteria	87

7.3.4	Functionality Test Execution Phase	88

7.3.5	Functional Testing Execution Entrance Criteria	88

7.3.6	Functional Testing Execution Activities	88

7.3.7	Functional Test Execution Exit Criteria	89

Definition	89

7.4	Functionality Test Report Phase	90

7.4.1	Functional Testing  Report Entrance Criteria	91

7.4.2	Functional Testing  Report Activities	91

7.4.3	Functional Testing  Report Exit Criteria	92

8.	CAPACITY TESTING PROGRAM	93

8.1	Organization Of Capacity Test Section	93

8.1.1	Goals of the Capacity Test	93

8.1.2	Roles and Responsibilities	93

8.1.3	Capacity Test Overall Process	95

8.2	Capacity Test Planning  and Preparation Phase	96

8.2.1	Capacity Test Planning and Preparation Entrance Criteria	96

8.2.2	Capacity Test Planning and Preparation Phase Activities	96

8.2.3	Capacity Testing Planning and Preparation Activities by Role and Responsibility	97

8.2.4	Capacity Testing Planning and Preparation phase Exit Criteria	97

8.3	Capacity Test Execution Phase	98

8.3.1	Capacity Testing Execution Entrance Criteria	98

8.3.2	Capacity Testing Execution Activities	98

8.3.3	Capacity Testing Execution Exit Criteria	98

Definition	99

8.4	Capacity Test Report  Phase	100

8.4.1	Capacity Testing  Report Entrance Criteria	100

8.4.2	Capacity Testing  Report Activities	100

8.4.3	Capacity Testing Report Exit Criteria	101

9.	Conclusion and Summary	102

10.	TERMINOLOGY AND GLOSSARY	103

11.	APPENDIX A:  ATTACHMENTS	108

11.1	Attachment 1 – Test Scenario Coverage Matrix	108

11.1.1	Attachment 1A - Functionality Test	108

11.1.2	Attachment 1B - Capacity Test	109

11.2	Attachment 2 – Test Case Specification Template and Example	110

11.3	Attachment 3 - Proposed Daily Report - Test Status and Assessment Form	116

12.	Appendix B:  Special Change Management Process	119

13.	Appendix C:  Military-style Testing	122

14.	Appendix D: Pacific Flow-through Plan	123

# DOCUMENT UPDATES

| Update Version | Updated by | Date | Description of Updates |
| --- | --- | --- | --- |
| 2.0 | Pacific Bell | 6/2/99 |  |
| 2.03 | Telcordia | 6/12/99 | Changes made during OSS Test workshop, June 7 through 15, 1999 |
| 3.00 | Telcordia | 6/28/99 | - Reflects Commission decision on open issues. - Reflects industry comments on test scenarios. |

## Master Test Plan Change Control

This document has been issued by the CPUC under its ACR dated June 28, 1998.  Comments from all parties will be expected by July 11, 1999.  Once comments have been reviewed, this document will be placed under Change Control by the Commission.  Any further change being considered for this document will be published to the industry before being included in this document.  The Commission reserves the right to include or exclude any changes to this document.

## Reasons for re-issue and changes

There are no changes to this document at this time. Prior versions of this document have been drafts, issued for comment. This is the first baseline issue of this document; hence there are no changes. If any changes occur, they will be summarized here and indicated within the body of the document as appropriate.

# EXECUTIVE OVERVIEW

This Master Test Plan, once executed, will evaluate for the California Public Utilities Commission (CPUC), Federal Communications Commission (FCC) and Department of Justice (DOJ), the operational readiness, performance and capability of Pacific Bell (hereafter referred to as Pacific) to provide pre-ordering, ordering, provisioning, maintenance & repair (M&R) and billing Operations Support Systems (OSSs) functionality to the Competitive Local Exchange Carriers (CLECs). This Master Test Plan (MTP) is the result of a rigorous process initiated by the CPUC with collaborative workshops in the summer of 1998 and continued in June 1999.  In the Commission’s decision, D.98-12-069, on Pacific’s draft 271 Application issued on December 17, 1998, the Commission set forth various parameters that this Master Test Plan must meet.

The goal of the test plan is to provide a plan to validate/assess Pacific’s readiness and capability to provide pre-ordering, ordering, provisioning, maintenance and repair and billing OSSs functionality to CLECs.  The MTP results will be summarized and reported in an OSS Compliance Final Report, that will be written by the Test Administrator and submitted to the Commission for its use. These tests will primarily take place in addition to normal retail and CLEC activity in a production environment.  The test focus, including performance/parity, consists of:

- End-to-End/Functionality Test  - will test end-to-end processes from pre-ordering through provisioning and billing, and maintenance and repair.  Testing will be performed with Pacific’s production OSSs and processes.  Test will focus on Unbundled Network Element (UNE) Loop with Port, Basic Loop and Asymmetric Digital Subscriber Line (xDSL) types of services and LNP.  (Note: An additional test will be completed for stand-alone Directory Listings).

- Capacity Test  - will test the capacity of Pacific’s pre-ordering and ordering processes for Resale, UNE Loop with Port, Basic Loop with and without Number Portability (NP), and stand-alone Local Number Portability (LNP) types of service.  Testing will be performed with Pacific’s production systems and processes. An analysis of scalability of Pacific’s systems and procedures will also be performed.

The test strategy and approach, test case scope and focus, timeline, responsibilities, risks and various phases (planning, preparation, execution/analysis/assessment and approval) and their associated activities are a part of this plan.  Successful completion is required by Pacific to achieve approval for entering the interLATA telecommunications market.  Focusing the scope of testing in various phases, identifying teaming, roles and responsibilities and specific accountabilities will help expedite the necessary steps to achieve completion.  Implementation requires the involvement of independent third parties to perform three distinct roles: Test Generator, Test Administrator/Manager, and Technical Advisor to the CPUC.  The CPUC will provide overall project management, the Technical Advisor will assist the CPUC Staff, and the Test Administrator/Manager will oversee the execution and assess the processes and test execution.  Implementation also requires Test End-Users, which will consist of employees of Pacific and the Test Administrator/Manager and others to be determined.  The Test End-Users will be used to primarily provide for the usage related needs of the testing.  This Master Test Plan provides the framework for the detailed test plans, which will be developed by the Test Administrator.

# INTRODUCTION

The California Public Utilities Commission (the Commission) is currently investigating Pacific Bell’s entry into the interLATA telecommunications market, pursuant to Section 271 of the Federal Telecommunications Act. As part of this investigation, the Commission is undertaking an evaluation of Pacific’s OSSs, including the interfacing process which allow CLECs to compete with Pacific in providing local telephone service.  These OSSs include those that provide for the mechanized CLEC interfaces for pre-ordering, ordering, provisioning, maintenance and repair and billing capabilities necessary for CLECs to provide Local Service in Pacific’s serving areas.  The evaluation will test whether Pacific OSSs provide parity or nondiscriminatory access with meaningful opportunity to compete with CLECs by using a Third Party performing CLEC activity providing service in Pacific territory in California.

## Purpose and Goals

This Master Test Plan has been developed to assess Pacific’s OSS readiness to support CLECs in the state of California.  It outlines the strategy for the evaluation of the readiness of Pacific’s OSS to handle CLEC business.  It includes the test scope, requirements, overall schedule/timeline, test environment, entrance and exit criteria for each phase, test approach and responsibilities among the test participants.  It provides the framework for the development of detailed test cases and test scripts.  By defining the overall test process, this document will serve to reduce the amount of unanticipated problems that may impede progress of this test.

The test scenarios defined by Pacific and the CLECs that will be verified by the Test Administrator/Manager are included in this Master Test Plan document.  The details will be provided in the Test Specifications document to be created by the Test Administrator as part of its test planning process defined in the Functionality and Capacity Test planning sections.

The Goals of this Master Test Plan include:

- Define the Scope  of testing.

- Define the testing process and methodology that will be used to perform the Pacific OSS evaluation following the OSS recommendations specified by the Commission, including, but not limited to, D.98-12-069, and the applicable Performance Measures

- Provide overall framework for the test activities and validation of the testing

- Provide for a collaborative approach among the CLECs, the Commission, Pacific, and the Third Parties as appropriate

- Provide expeditious sequencing of activities

- Define project dependencies and provide the approach for managing them closely

- Maintain consistency with generally accepted industry practices and processes.

- The testing approach will be “military” in nature, that is, test until success as described in Appendix C.

- “Testing Load” – A predefined number of pre-order transactions and local service requests specified on both an hourly and daily basis, that are to be processed in the capacity tests, which should, when combined with the appropriate scalability analysis (to be prepared by consultants), provide the Commission with sufficient information to determine the commercial readiness and robustness of those aspects of Pacific’s OSS under test.

- “Mix of Services” – The percentages of different types of services and/or UNEs that the parties have agreed to, or the Commission has ordered, can be used in the functionality and capacity tests to guide the test administrator in determining how many local service order requests of each type should be processed.

## Scope

The evaluation will cover order types associated with the various modes of CLEC entry: Resale, LNP, UNE Loop with Port, Basic and Assured Loops, xDSL, DS1-capable loops and stand-alone Directory Listings.  For UNEs, the functional areas of pre-ordering, ordering and provisioning, billing, and maintenance and repair will be tested.  Testing will include both residence and business orders and will encompass new, reconfigurations “as specified”, change orders, outside moves, disconnects, cancellations, and suspend and restore order types.  From an ordering perspective, the Pacific OSSs will generate acknowledgements, error rejections, Firm Order Confirmations (FOCs) and Service Order Completions (SOCs).  In addition, testing will also include items such as a variety of feature combinations, directory listings (“as is” and “as specified”), hunting, 900/976 blocking, and toll restrictions.  Detailed requirements for the functionality to be tested are given in Section 6.

There are two types of tests that will be conducted:

- A Functionality Test will focus on both the mechanized and manual support functions.  The evaluation will cover the various order types associated with four modes of CLEC entry:  UNE Loop with Port combination, stand-alone LNP, UNE 2-wire loops with and without number portability, number portability, UNE DS1 loops with and without number portability (see Table 6-1). It will also include the evaluation of Pacific OSSs’ ability to meet a set of applicable Performance Measures.  These Performance Measures will be used to evaluate parity or applicable benchmarks between the service Pacific provides to its own retail customers and the service it provides to its CLEC customers.

- A Capacity Test will focus on the ability of the Pacific OSSs to support a given mechanized workload [Local Service Requests (LSRs) that are Automatic Order Generator (AOG) eligible]. Some errors that can be handled by mechanized processes will be introduced as part of this test. Orders will be processed to service order distribution (FOC).  The evaluation will cover order types associated with various modes of CLEC entry: UNE loop with port combination, UNE 2-wire loops with and without LNP, stand-alone LNP, resale, and stand-alone directory listing (see Table 6-3).  It will also include the evaluation of Pacific OSSs’ ability to meet a set of applicable Performance Measures.  These Performance Measures will be used to evaluate parity or applicable benchmarks between the service Pacific provides to its own retail customers and the service it provides to its CLEC customers.

Table 3-1 provides a summary of the test areas and types of testing to be performed.

Table 3-1: Test Areas and Types of Testing

| Function | Functionality Test | Capacity Test |
| --- | --- | --- |
| Pre-ordering | X | X |
| Ordering | X | X |
| Provisioning | X |  |
| Maintenance and Repair | X |  |
| Billing | X |  |
| Flow-through Tests | X | X |
| Performance Measures | X | X |

In general, testing will be conducted for a pre-determined set of error free test scenarios.  However, for the Functionality Test, a set of the most common error scenarios will be covered under this evaluation.  The Test Administrator/Manager will define the number and type of error scenarios to be covered.  The number and defined type of error scenarios will not be shared with Pacific so as to maintain a level of “blindness”.

The Competitive Checklist (i.e., 271), the Public Interest and Section 272 compliance issues defined in D.98-12-069 will not be addressed directly.

## Audience

The audience for this document is expected to be  Pacific, the Test Administrator/Manager, the Test Generator, the FCC, the DOJ, and the CLECs.

Note: In an Assigned Commissioner Ruling (ACR) dated May 21, 1999, the CPUC Telecommunications Division has been ordered to convene informal workshops to finalize this Master Test Plan.  The collaborative sessions were held June 7 through June 15, 1999.

## Open Issues

There are currently no open issues. If they were to occur, they would be summarized here and throughout the document, they would be indicated within braces { }.

# ENVIRONMENT

## Architectural Blueprint

The systems included in this test environment are expected to be production systems.  Pacific Bell and MCIW are responsible for their liability associated with using their production environments for this test.  They are responsible for modifications made to their systems, potential disruption to or impairments of their telecommunications services or customers as a result of this test. Any tools required for this test will be supported, administered and maintained by the respective participants. The following depicts the architectural blueprint of the environment to be used for testing.  In addition, an Electronic Bonding Interface (EBI) from MCIW to Pacific’s maintenance and repair system is included as is an MS Gateway from the test generator to Pacific’s 911 gateway.

Figure 1: Architectural Blueprint

### Account Environment

Pacific, under the direction of the Test Administrator, will provide test accounts that will be used to reconfigure, change, and disconnect services for the purpose of Third Party OSS Interface Testing. These test accounts are a combination of local exchange company facilities and database entries in Pacific’s systems.  Pacific will create dummy accounts with TNs and customer records (CSRs) that will be used in the testing process.  Pacific will input this data before the test begins, establishing these test accounts as in-place lines of various types.  This information in the form of name, address, TN, of the live (but created for the test) service will be provided to the Test Administrator/Manager.

The Test Generator will develop and submit orders against these test accounts.  Test calls will be made from the test line (connected to telephones dedicated to testing) so that billing information (daily usage feeds and telco charges) can be collected.  The test accounts will be on Pacific’s real production systems and will be set aside for the use of the Test Generator.  The Test Administrator/Manager, based on the Master Test Plan, will determine the test account requirements.

## Operations Support Systems (OSSs)

This section details the various systems included in this test.  Details are provided on the new systems developed by Pacific to handle CLEC customer service requests which provide for a mechanized process flow and those that provide the CLEC access to the Pacific OSS in case they do not have their own mechanized (i.e., application to application) interface developed.  The releases associated with these systems are typically expected to remain the same for the duration of the tests.  However, since the environment to be used for testing is the production environment, changes are expected to be required.  Therefore, deviations from the baseline environment must be identified to the Test Administrator/Manager along with an impact statement associated with the changes within the release that may impact this testing.  Then a decision will be made relative to subsequent actions/activities.

The environment will be the current Pacific production environment, with inputs supplied according to the PMO (Present Method of Operation).

### Pre-Ordering

Verigate provides the GUI for pre-ordering functionality, and DataGate will provide the app-to-app connectivity for the pre-ordering functionality.  DataGate and Verigate allow a CLEC to perform the following information on-line:

- Customer Service Record (CSR) - view current service records as a result of a customer providing authorization for a change

- Address Verification/Dispatch - verify service address information as registered

- Request for Telephone Number (TN) - reserve one or more telephone numbers for new connections.  Reserved TNs are available for 30 days.  TN assignment and cancellation is also included.

- Service Availability/Product and Feature Availability (PFA) - retrieve a list of services and features that are provided from a particular local serving office.  Common Language Location Identification (CLLI) Code represents the switch that provides service to the telephone number requested.

- Service Appointment Scheduling - Due Date - view available dates and appointment times for the verified address [Note: Applicable for Resale (Capacity Test only) and UNE Loop with Port.]

- Facility Availability - Access to LFACS Information (ALF) – allows the CLEC to view whether dispatch is required for connection of a new line of service at a verified residential address.  This transaction also provides Facilities, spare and defective pair information for residential customers at the verified address.

- Primary Interexchange (IXC) Carrier (PIC) selection/Local Primary Interexchange Carrier (LPIC) selection/Carrier Identification Code (CIC) – identifies the available IXC selections for customer PIC/LPIC selection at the switch level.

- Number of Rejects/Failed Inquiries

- Support K1023 pre-order processing for xDSL (available via fax transmission).

#### DataGate – Mechanized Access

DataGate is a Pacific-developed interface, which provides for pre-ordering capabilities from an application to application interface.  Therefore, with DataGate, CLECs can build a mechanized (i.e., electronic) interface to the Pacific pre-ordering OSS.

#### Verigate – GUI Access

Verigate provides for pre-ordering capabilities from a GUI interface.

### Ordering

There are several Pacific systems involved in the ordering process. They include LEX, EDI, LASR, WSM, AOG, and SORD.

#### Local Service Request Exchange (LEX) – Manual Access

LEX is the GUI that provides online manual access to create, maintain, submit and status (e.g. issued, FOC, SOC, etc.) LSRs submitted to Pacific.  LSRs submitted by CLECs which pass initial edits are processed by Pacific OSSs to create service orders and provide for subsequent provisioning of the requested services.

#### Electronic Data Interchange (EDI) Interface- Mechanized Access

The EDI Interface receives LSRs from the CLECs and translates them to a format acceptable by Pacific internal systems.  For LSRs that are received via this interface their status is also returned via this interface (e.g. acknowledgement,  reject notification, FOC, SOC, etc.).  The CLEC LSRs, which pass initial edits, are processed by the Pacific OSSs to create service orders and to provide for subsequent provisioning of the requested services.

#### Local Access Service Request (LASR) – Mechanized Access

LASR provides for the mechanized editing of the LSRs. LASR receives LSRs from either the EDI Interface or LEX.  If LASR receives the LSR with an error rejection condition across the EDI interface, it returns the rejection notification through that interface. If LASR receives the LSR with an error rejection condition via LEX, it returns the rejection notification through that interface. After the LSR passes LASR edits, LASR determines if an LSR is “AOG eligible”.

#### WSM (Wholesale Service Manager)

This system provides for mechanized editing of resale LSRs.  WSM receives LSRs from either the EDI interface or LEX.

#### Automatic Order Generator (AOG)– Mechanized Access

Automatic Order Generator (AOG) creates a service order from the entries on the LSR as well as from additional tables, to obtain data that is not required on the LSR but is necessary for service order creation.  AOG then processes it and creates the service orders.  If the service orders are successfully created, AOG attempts to distribute them to SORD for downstream processing.  During processing, AOG encounters one of the following situations:

- Creates one or more service orders on AOG eligible LSRs and thus, successfully distributes the service order to SORD

- Creates the service order but is unable to successfully distribute the service order to SORD

- Finds “Non Fatal” Error in which the LSR must be processed manually. Service orders will be manually created or  a reject notice will be manually created and electronically transmitted to the CLEC.

#### Folders – LSR Database

Folders is a database system for LASR that provides Pacific Local Service Center (LSC) representatives with the ability to view LSRs and provide reports of LSR status during the processing of CLEC LSRs.  LSRs input to LASR from either the EDI Interface or LEX are stored in the Folders database.  For the test, LSRs will have any of four (4) new test OCNs.  This is to enhance anonymity of the test cases.

#### Service Order Retrieval and Distribution (SORD) – Mechanized Access

Service Order Retrieval and Distribution (SORD) provides the service order distribution and assignment processing and associated information.  SORD provides the FOC and SOC status back to the CLEC via LASR or WSM to either EDI or LEX, whichever mechanism in which it was received.  The FOC is a response from the service order processor that represents the acknowledgement of receipt of an order from a CLEC.  The SOC is a response from the service order processor that represents the acknowledgement of successful completion of the service order.  Manual input is provided to create the service orders for complex orders and non-AOG eligible orders.

#### MS Gateway

This interface system is used to populate E911 database information in support of emergency services.

### Provisioning – Backend Systems

Several Pacific backend systems provide for the provisioning functions.  These systems are generally not directly accessed by the CLECs.  These systems support processing for functionality provided to the CLECs as they do for Pacific retail customers.  They will provide for the  assignment of facilities as needed.

### Maintenance and Repair

#### Pacific Bell Service Manager (PBSM)

Pacific Bell Service Manager (PBSM) is a Pacific developed character based stand-alone system that provides access to Pacific’s maintenance and repair functionality.  PBSM enables the CLECs to submit trouble reports for its end-users, check the status of a trouble report, view trouble history and perform Mechanized Loop Test (MLT) as described below.  PBSM will support trouble reporting on Resold Plain Old Telephone Service (POTS) UNE, including Loop with Port and 2-wire Loop (Basic, Assured, four-wire DS1 & xDSL).

PBSM has the capability of initiating a MLT and receiving test results for UNE Loop with Port.  The MLT test can be performed without initiating a trouble report.  The MLT functionality of PBSM will provide the capability of performing a full MLT test.  The MLT test provides results for Direct Current (DC) and Alternating Current (AC) K-OHM measurement for Tip to Ring, Tip to Ground, and Ring to Ground.  It also displays Tip to Ground and Ring to Ground DC voltages and if Ringers are detected on the loop.  The test also displays the Central Office (CO) line check and dial tone check.  The test also provides capacitance test readings and estimated loop length.  The MLT test code is returned along with its English Translation, such as “Test OK”.

The MLT results will allow the CLEC to determine if trouble exists on the Pacific loop and associated Customer Premise wiring and equipment (CPE) to which it is connected.  MLT does not provide any method of sectionalizing the trouble report between the Pacific network or the CPE unless a Maintenance Test Unit (MTU) exists in a Standard Network Interface (SNI) at the end-user’s premise.

PBSM does not support reporting trouble on disconnected services or Telephone Numbers (TNs) that have been ported out of Pacific.

#### Electronic Bonding Interface (EBI)

Electronic Bonding is an industry standard for Maintenance and Repair.  Pacific will provide the EBI interface to communicate with MCIW’s EBI application.  This interface will be used for selected Maintenance and Repair test cases.

### Billing and Usage – Backend Systems

Many backend systems provide for billing and usage.  These systems are not directly accessed by the CLECs.  These systems support the same processing for the same functionality provided to the CLECs as used to provide for Pacific retail customers.  They provide for the production of the wholesale bill to the CLECs.  The next section describes the main system that provides for the UNE bill.

The Functional Testing will be limited to a manual review of the paper output of the billing and usage systems (customer bill) and the usage mag tapes normally provided to CLECs.  It will not include the testing of mechanized transmission of these outputs.

#### Carrier Access Billing System (CABS)

The Carrier Access Billing System (CABS) is a Pacific system that provides for CLEC billing.  CABS receives feeds from Toll/Usage, Service order and Payment systems on a daily basis in order to render CLEC bills.  The UNE billable elements are:

- Charges:

- Monthly Charge From/Through Dates

- Usage Charges (by Jurisdiction), OC&Cs (by Jurisdiction), Monthly Charges, Surcharges, Taxes (by tax authority), and Total Current Charges

- Originating (Overall Company Code)

- Detail of Adjustments:

- Adjustment Description

- Adjustment From Date, Adjustment Through Date

- Audit (Claim) Number

- Exchange Carrier Circuit ID (ECCKT)/Telephone Number

- Adjustment Amount (By Jurisdiction)

- Rate Element Quantity

- Discount and Zone Information (if applicable)

- Detail of Other Charges and Credits (OC & C):

- OC&C From Date, OC&C Through Date

- Invoice Number, Purchase Order Number

- Telephone Number

- OC&C Charge Description/Explanation

- OC&C Amount (By Jurisdiction / PIU (percentage interstate usage

- Rate Element

- Quantity

- Fractional Amount, One Time Amount, Monthly Amount

- Discount and Zone Information (if applicable)

- Detail of Usage and associated summary

- -	State Usage from Date, Usage through Date

- -	Jurisdiction

- Summary By Access Service Group (ASG); Total by Billing Account Number (BAN)

- -	Minutes/Messages

- -	Rate

- -	Rate Change Date

- -	Usage Amount

- -	Rate Element:  Common Transport, Blended Transport, Tandem Switching, and Local Switching

- -	Third party (e.g. Calling Card Usage)

- Detail of Surcharges (if applicable) and taxes:

- State

- Type of Surcharge and Tax

- Monthly Access, Other, Usage and associated Tax Amounts

### End Users

A set of Test End-Users will be used to participate in the UNE Loop with Port, LNP and UNE Loop (Basic & xDSL) tests.  In many instances additional telephone line(s) will be installed at the Test End-Users premises.  This secondary test line will be used solely to conduct the test.  Collocation cages at specific company locations will be used to provide for the LNP, UNE Loop (Basic & xDSL) tests.

### Network

CLECs recognize that comprehensive, end-to-end testing of these order types will necessitate direct involvement of CLECs and the use of physical CLEC facilities.  For example, UNE orders with LNP clearly require a physical switch and collocation space of a real CLEC in order to be fully completed.  Furthermore, even though the LSRs could be submitted by the Third Party Test Generator, orders would need to use actual CLEC values and facility assignments and the Coordinated Hot Cut, or TBCC, processes would need to be coordinated with actual CLEC provisioning groups.

Therefore, the following CLECs will participate and provide facilities required to execute Functionality Test scenarios for the above-named critical order types, provided that geographic arrangements and resource requirements are manageable and can be worked out with the Test Administrator in advance:

AT&T

Cox

ICG

NEXTLINK

Northpoint

Covad

The CLEC network faciliities that will be provided include local switch and loop facilities to evaluate LNP and Digital Subscriber Line Multiplexer (DSLAM) facilities to evaluate DSL.

## Test Environment Management

### The Test Environment Checklist

The following items will be checked based on the test methodology being used:

- Terminal, workstation or Personal Computer for all Test Generator personnel who are to execute the test cases.

- Tools (e.g., test management system, test drivers) and communications expectations available (e.g., including website access, systems access from remote site, etc.)

- File permissions are correct (e.g., OSS access, access to website for reports, etc.)

- Printer access defined and available (e.g., to create the reports)

- Logins to systems as necessary with applicable security

- Access to data as necessary

- Communications verification to ensure connections have been established relative to Pacific and Test Generator production LEX or EDI Interfaces

- Provide test environment details pertaining to the platform, interfaces, a contact for each system, and the physical links the system uses.

### Environmental Change Management

Typically changes and upgrades to the software under test are not expected to occur during the test intervals.  In addition, typically the tables, links and other environmental changes, which may impact this testing, are expected not to occur during the test interval.

However, since this testing will be performed in a production environment, release levels are expected to change on a pre-announced schedule, which may be within the Functionality Test execution window.  These changes will be managed under the standard Change Management Process. In addition, other environmental changes (e.g., table updates) are expected to occur.  Adverse impacts from these changes will become problems to be considered for the test evaluation.  Major problems (e.g., a new release causes many tests to fail) may force the release to be backed out or the test to be rescheduled.  Conversely, if changes go smoothly, this demonstrates that changes can be managed successfully.  If changes to the environment are planned or occur as a direct result of the OSS test, Pacific must describe the changes in the Pacific systems that may impact the testing and define their impact as soon as they are known.  To allow for the timely execution of the tests, a special Change Management Process as  defined in Appendix B will be followed for changes needed as a direct result of the OSS test.  All affected CLECs will be informed as to this temporary alternative process.

### Environment Needs

#### Environment Needs - Functionality Tests

The environment used for the Functionality Test consists of the mechanized (i.e., EDI, DataGate) interfaces built by the Test Generator using documentation it acquired from Pacific using procedures that CLEC’s currently use in identifying and acquiring this information.  In addition, to validate Pacific’s OSS readiness, testing must include an interoperability test with the Test Generator initiating LSRs through their EDI Interface or LEX.  The Test Generator will also initiate pre-order queries through Verigate. EDI pre-order The Test Generator must have the ability to test and validate the various services and conditions defined in the test scope.  To accomplish this, the Pacific production systems that provide for the mechanized processing interface to the Test Generator will be used.

The Functionality Test will assess the DataGate and Verigate interfaces for pre-ordering, and the EDI and LEX Interfaces for ordering.  In addition, the MS Gateway for E911 database population will be assessed.  The OSSs required to perform the provisioning, maintenance and repair, and billing are used by Pacific’s retail customers and CLECs, and primarily consist of Pacific legacy systems.  Thus, they are included in the Functionality Test, but are not defined here.  It is also noted that these backend systems currently support both mechanized and manual effort required to support commercial level volume.

The Test Generator will initiate Maintenance and Repair functionality tests into PBSM.  In addition, MCIW will initiate Maintenance and Repair test cases into Pacific’s EBI..

To support the Test End-Users for the Functionality Test, the accounts must be established correctly in the Pacific production database.  See Section 6.5.5 for more details.

#### Environment Needs - Capacity Tests

The Pacific production systems will be used to conduct the Capacity Test.  The Capacity Tests will include DataGate and Verigate and EDI pre-order for the pre-ordering process.  Systems to be included in the Capacity Test order process are EDI, EDI pre-order and LEX,.  This Capacity Test will be through SORD distribution.  Moreover, the backend systems that provide for SORD distribution (FOC) needs are included.

### Environment Cleanup

#### Environment Cleanup - Functionality Test

Once the Functionality Test is complete, the environments used for this test must be restored back to their original state relative to the events imposed by the testing (i.e., test related items are removed from the systems).  This cleanup is expected to occur within 30 days after completion or no later than when the Test Administrator/Manager’s and the Technical Advisor’s Evaluation Report is issued.  In addition, if other systems were used in the test, the test data on these must also be removed.

Cleanup items to address consist of:

- Telephone Numbers

- Facilities

- Billing

- Directory Listings

- 911 database updates

- Customer data - total purge relative to the test orders (each participant needs to assure this is the case).  The Test Administrator/Manager will randomly request verification.

- Purging of EB trouble tickets

#### Environment Cleanup - Capacity Test

Once the Capacity Test is complete, the production environment must be restored back to its original state within 3-5 days.  The major cleanup is associated with the pending orders.  An extended due date will be used for the Capacity Test (e.g., 12/24/99) to help prevent the provisioning process, and identify test orders for data extraction and cleanup purposes.  However, a FOC must be received prior to employing this cleanup methodology.  A clean up of LSRs that exception to Folders will need to be purged, but will not be part of the test results.  Otherwise, Pacific will provide cleanup by removing the orders associated with the Test Operating Company Numbers (OCNs) and the extended due date.

# ADMINISTRATIVE PROCESS

This section defines the processes that will help govern the test activities.  The terminology section at the end of the document defines the terminology used within this Master Test Plan.

## Timeline

A summary of the key milestones/critical path items for the success of this project is described in this section.  This summary represents a high-level overview of the major milestones associated with the tests. A separate work project plan developed and managed by the CPUC will be used to manage and track project status. The Test Administrator will have its own internal plan that supports this timeline and the detailed activities required to meet the major milestones.  The Test Generator and Pacific will operate in accordance with the Test Administrator plan, as will the end-users.  The project plan will be used as the controlling timeline for the test events.  The content of the project plan should be re-visited at a minimum every week and revised if necessary since key elements may vary over time.

The test procedures will also include a test management jeopardy process (see Section 5.3.6) to manage potentially missed milestones .  The work project plan also includes assignment of responsibility for each task in the project that needs to be completed.

## Roles and Responsibilities

Whereas the Commission and Technical Advisor can provide valuable and cost-effective advice and solutions, the ultimate accountability for implementation of this Master Test Plan is  the Test Administrator’s with the support of the Commission and the Technical Advisor.

This section details the overall roles and responsibilities of the test participants with respect to this testing effort.  Additional roles and responsibilities specific to each test will be detailed later in Sections 7.1.2 and  8.1.2.  It is expected that test participants will execute their responsibilities in a timely manner, according to the process defined in this document.

### Commission

The role of the Commission is to:

- Provide overall project management

- Own the test plan.

- Create the testing implementation timeline

- Provide support for the collaborative process in enhancing the Master Test Plan

- Provide final approval of Master Test Plan

- Appoint a Test Administrator/Manager to manage the test activities.  The Test Administrator/Manager responsibilities are defined in Section 5.2.4

- Appoint a Test Generator to develop the testing interfaces and conduct related activities.

- Review and approve the Final Report prepared by the Test Administrator/Manager.

### Pacific Bell

Pacific is a direct participant in the tests.  The role of Pacific is to:

- Provide the Pacific OSS environment to be used for the test (i.e., production environment)

- Support Test Plan needs, as necessary

- Provide list of primary, Subject Matter Experts (SMEs) and escalation contacts to all parties

- Provide for preparation, setup, and access to the Pacific production components for the tests as necessary (primarily for monitoring by Test Administrator/Manager)

- Provide system processing data necessary to understand the resource usage for the test workload

- Extract data and compute the Performance Measures.

- Assign an account team to interface with the Test Generator

- Provide documentation to the Test Administrator to enable scalability analysis of system interfaces and work center operations (LSC and LOC).

### Technical Advisor to Commission Staff

The Technical Advisor’s role is to:

- Assist in development of Commission Master Test Plan

- Review Test Cases

- Evaluate documentation assessment and process analysis

- Provide technical advice to Commission Staff

- Provide on-site observing of actual test, as needed

- Evaluate data and reports prepared by Test Administrator/Manager

- Provide oversight for Test Generator until Test Administrator/Manager is selected

- Analyze data and write report

- Submit final report

### Test Administrator/Manager

The Test Administrator/Manager’s role is to:

- Define MTP scope to assure coverage and the ability to test scenarios expected.

- Gather test data

- Compile a detailed daily log of events capturing the details of its experiences in dealing with all participants.

- Prepare end-user test scripts

- Provide on-site observing

- Compile and evaluate data

- Administer testing implementation timeline

- Prepare reports

- Provide oversight for Test Generator

- Submit test observations, test results attestation and draft final report

- Provide Documentation Assessment and Process Analysis (i.e., LSC/LOC scalability of appropriate systems)

- Assist Technical Advisor in validating  Performance Measures Process/System

- Develop test cases based on the test scenarios, including number of error scenarios.

- Assess the operation of the LSC for consistency, timeliness and accuracy.

- Assess the operation of the LOC for consistency, timeliness and accuracy.

- The Test Administrator/Manager will assure the test scenario selection will cover both access mechanisms (LEX, EDI).

- Assess the scalability of the OSS test interfaces using documentation provided by Pacific Bell.

- Identify the end-user participants (80% Pacific Bell locations, 20% TBD by Test Administrator).

- Assess the operations scalability (force management) of the LSC and LOC.

- Assure statistically valid approach to testing.

- Chair the Technical Advisory Board (TAB).

- The Test Administrator/Manager will take the necessary steps to make sure the Test Generator does not receive any information that a CLEC would not receive under the normal course of business.

### Test Generator

- Develop interfaces

- Install connectivity

- Create LSRs

- Input  LSRs/

- Document results of interface development and order generation

- Acquire appropriate documentation, attend training and assess quality and completeness of documentation, training, etc. to mirror CLEC activity to build an automated interface.

- Create and input pre-order queries.

- Compile a daily log of events capturing the details of its experiences in dealing with Pacific.

#### MCIW as EBI Test Case Generator for Maintenance and Repair

MCIW work center personnel will execute appropriate Maintenance and Repair test cases under the direction of the Test Administrator/Manager.

### CLEC Network Element Providers

Under the administration of the Test Administrator/Manager, AT&T, COX Communications, ICG, NEXTLINK, NorthPoint, COVAD will provide local switch, loop and DSLAM facilities to support DSL and LNP testing.  The TAB will be the forum for this participation.

### The Technical Advisory Board (TAB)

A Technical Advisory Board will be convened at the start of testing.  Its membership shall be CPUC, the Test Administrator/Manager, Test Generator, Pacific representation and from three to five CLEC representatives. Its charter is to participate in the special Change Management Process on the test architecture (Figure 4.1) in accordance with the procedures in Appendix B, and to provide CLEC support as requested by the Test Administrator/Manager.  This CLEC support consists of providing appropriate network elements for EBI interface operation.

In addition, TAB members (as determined by the Test Administrator/Manager), the Test Administrator/Manager and the CPUC will review periodic test results and offer advice, observations and provide input to the test process.  This will be done to enable the CLECs and Pacific to provide feedback on the testing as requested by the Test Administrator/Manager.

### The End Users

The end user will execute defined telephone calling/usage scripts as directed by the Test Administrator.  The Test Administrator will identify the quantity of end users.  These end users will be business and residence locations for which Pacific will provide facilities.  The end user population will come from a variety of sources as determined by the Test Administrator.

The purpose of the end user test scripts will be to generate usage for billing and usage evaluation as well as to provide a network-based test bed to support maintenance, and repair.

## Management of Tests

### The Test Administrator/Manager

A Test Administrator/Manager will be assigned to ensure that testing will be conducted expeditiously and that test participants are aware of the test status.  The Test Administrator/Manager must perform the following functions for the Functionality Test, since the planning and execution of this test will take place over many days:

- Problem Management and Action Item Management

- Track testing Action Items (e.g., requests for information relative to testing using a daily log)

- Distribute a tracking summary of action items to resolve problems identified by the Test Generator, the Test Administrator or Pacific.

- Assign accountabilities and track resolutions to issues/problems identified

- Track test management jeopardies if milestones are missed.

- Test Schedule Management

- Assign accountabilities and track resolutions as necessary for the test activities, with support from the Commission and the Technical Advisor

- Collect daily test status from Pacific, Test Generator, the End User and report to the Commission.

- Communications Management

- Provide overall communications management within the testing interval

- Maintain daily contact with the Test Generator and other participants

- Maintain an electronic contact list (e.g., subject matter experts, escalation) for each test participant, the Technical Advisor and the Commission

- Distribute test management jeopardies reports to appropriate audience as determined by the Test Administrator/Manager

- Distribute daily summary of the compiled test metric information forwarded by the test participants the same day it is collected or the day after as necessary

- Create and distribute weekly high-level summary, including test progress, problem identification, action items, issue resolution progress and potential jeopardies status review.

- Convene the TAB

A typical Test Administrator/Manager contact list is shown below.  The Test Administrator/Manager will determine those that will get certain communications.  Most communications  will be distributed to the Commission and the Technical Advisor.

Table 5-2: Test Administrator/Manager Contact List  FOR ILLUSTRATIVE USE ONLY.   To be filled out by Test Administrator prior to Testing

| Contact | Responsibility | Telephone Number |
| --- | --- | --- |
|  | California Public Utilities Commission |  |
|  | Pacific Bell Lead Person |  |
|  | Test Generator |  |
|  | Technical Advisor |  |
|  | OSS Subject Matter Expert |  |
|  | TAB |  |

### Daily Report

The following information will be reported on a daily basis during test execution. Test participants will provide the test status information to the Test Administrator/Manager.  The Test Administrator/Manager will create the daily report.  The Daily Report provides a review of the current progress of testing and gives an indication of potential areas of concern and technical issues.  Actual metrics data will be counts of occurrences in the various categories and are further detailed in Section 5.3.3.

The Test Administrator/Manager will take the necessary steps to make sure the Test Generator does not receive any information that a CLEC would not receive under the normal course of business.

- Pacific  input to Daily Report includes;

- For systems included in the test, provide system availability

- Describe system and communications problems/issues that may affect availability

- Describe discovered software issues (e.g., problems discovered during testing or production)

- Describe Methods and Procedures (M&P) issues

- Propose MR’s  to Test Administrator to fix identified system problems

- Test Generator input to Daily Report includes;

- Status of LSRs

- For Test Generator systems included in the test (i.e., systems interfacing to the Pacific OSSs), provide system availability

- Describe system and communications problems/issues that may affect availability

- Describe discovered software issues (e.g., problems discovered during testing or production)

- Describe error/reject conditions (unplanned ones), error identification, and proposed root cause

- Describe any M&P issues

- Provide Test End-Users  status and schedule, including any delayed or unscheduled activity

- Describe any Test End-Users-reported problems

- Daily log

- Test Administrator/Manager  input to Daily Report includes;

- Status of test management jeopardies and escalated problems

- Other problems and action items

- Schedule review

- Update of test metrics

- Preparation of test scripts

- Management of MR’s

- Daily log

### Test Metrics

The test metrics to be used will be defined in the Test Administrator’s test plan. The test metrics must include at least the administrative and technical metrics listed below.

#### Administrative and Control Metrics

- Total number of test cases

- Total number of test cases executed

- Total number of test cases completed (from an end-to-end functionality perspective)

- Total number of test cases with problems reported

- Total number of end-user test scripts

- Total number of end-user test scripts executed

- Total number of end-user test scripts completed

- Total number of end-user test scripts with problems

- Total number of problems reported (test cases and test scripts).

- Test schedule slippage

- Test phase interval: planned versus actual

#### Technical Analysis Metrics

The issues surrounding LSR flow-through and LSR rejects should be managed through metrics in the Capacity and Functionality Tests, including but not limited to, Performance Measure #4 Percentage of Flow-through Orders.  These will help focus some of the analysis activities.  For flow-through, the following measures should be computed by Pacific and reported to the Test Administrator/Manager and Technical Advisor on a daily basis. See Attachment D, flow-through Matrix.

- Pacific EDI Interface flow-through (from Test Generator input)

- Pacific LEX flow-through (from Test Generator input)

#### Test  Case Tracking Matrix

The Test Administrator/Manager will maintain, with daily inputs from the Test  Generator, a Test  Case Tracking matrix for the Functionality Test.  This tracking tool is an extension of the material in Attachment 1 allowing an individual status to be placed on each Test  Case in the test.  The Test  Case Tracking Matrix allows a comprehensive view of test status.

### Problem Reporting Procedures

All problems will be reported to and managed by the Test Administrator/Manager. The Test Administrator will determine format and procedure for problem (trouble) reporting (MCIW to provide comments).

### Escalation Process

Problems encountered by the test generator that cannot be resolved through the use of resources available to CLECs, in the normal course of business or which threaten the attainment of scheduled milestones, shall be brought to the attention of the Test Administrator as an "escalation". If the underlying facts or the resolution of the escalation would require an amendment to an OSS interface or business practice, then the Test Administrator shall apprise the TAB of the escalation and the potential resolution of the situation. The escalation process does not include activities that the test generator performs outside the scope of normal CLEC activities. This would be escalated directly to the Test Administrator.

Escalations will be handled by the Test Administrator/Manager.  Problems which cannot  be resolved by the Test Administrator/Manager will be referred to the Commission staff for mediation and resolution.  The Technical Advisor will assist in the resolution of problems with the intent of obtaining a quick, reasonable resolution that will not affect the test schedule or compromise the test results.

In the event issues need to be escalated a contact list developed by the Test Administrator/Manager will be used.  Pacific Bell and the Test Generator will identify their escalation contacts.  The Test Administrator/Manager will maintain a contact list for escalation issues.

The Test Administrator/Manager will determine those that will get certain communications.  Most communications will be distributed to the commission staff and the technical advisor.

### Test Management Jeopardy Process

Test management jeopardies will be managed by the Test Administrator/Manager.  Test management jeopardies are used to help ensure the project remains on schedule.  A test management jeopardy will be created when an event causes an impact on the projects’ goals and expectations (usually, the schedule) as defined in the Master Test Plan.  The jeopardy can be identified by any team member and requires an action plan be developed to resolve the situation.   Pacific Bell, or the Test Generator may be assigned accountability by the Test Administrator/Manager for an action plan to resolve a situation that can cause the project to be in jeopardy.  The Technical Advisor will assist in the resolution of test management jeopardies with the intent of obtaining a quick, reasonable resolution that will affect the test schedule a minimal amount and will not compromise the test results.

Major components of the test management jeopardy report consist of:

- Ownership – Test participant responsible for championing the jeopardy resolution such that an action plan is determined

- Issue/Problem description – brief summary

- Impact – how the issue/problem will impact the project

- Action Plan – plan to resolve the issue/problem while maintaining the Master Test Plan objectives and goals

- Exception Report – although the plan is to perform “military-style” testing, it is possible that an exception will be observed.  At the direction of the Commission, testing will continue and an exception report noted. If this occurs, consideration will be given to needed regression testing prior to the conclusion of the tests.  The Test Administrator and the Commission will be responsible for making this decision.

- Status – green (on schedule), yellow (cautionary) and red (in danger) relative to achieving the action plan, which supports maintaining the test goals (e.g., schedule, scope, etc.).

Test participants will be notified of jeopardies according to the contact list maintained by the Test Administrator/Manager.

### Change Control Process

The objectives of change control are to obtain initial agreement on a document and then to assure that any changes caused by developments unknown at the time of issue will be properly reflected into an update to the document.  This process employs the baselining concept.

The Commission will approve initial issues and updates to baselined documents, with input from the Technical Advisor.

Change management for the test environment is discussed in Section 4.3.2.

All change control information is supplied to the Test Administrator/Manager and is distributed according to the contact list maintained by the Test Administrator/Manager.

### Risk Management

The Test Administrator shall develop a risk management/contingency plan for testing.  The objective is to develop as complete a list of risks as possible. This  plan shall include the following:

Identify the impacts, primarily negative results, if a previously identified requirement, task/expectation or assumption is not delivered on time, completed on time, plus the alternative action plan and the responsible parties are:

- Work Project plan - task at risk

- Risk Event Identification - review of event

- Impact - impact risk would have if it occurs.  Assignment of likelihood can be portrayed in a High, Moderate, or Low fashion rather than quantitative, which may require more analysis.  The impact statement provides an assessment (most typically of the delay) caused by the occurrence of the event.

- Impact, Plan/Mitigation Strategies - various mitigation alternatives shall be considered for each identified risk and a primary option shall be selected, i.e., avoidance, retention, control, and deflection

- Risk Prioritization - rank order listing of the identified risk events based on the results of the risk analysis.

# REQUIREMENTS AND ASSUMPTIONS

The organization of this section is as follows:

- Section 6.1:  Interface Development Requirements Documentation

- Section 6.2:  LSC/LOC Scalability Requirement

- Section 6.3:  Functionality Test requirements

- Section 6.4:  Capacity Test requirements

- Section 6.5:  Test evaluation requirements

- Section 6.6:  Assumptions relating to all phases of test activity

## Interface Flow-Through Development Requirements

Common requirements must be used to implement the capability of flow-through among the (Test Generator and Pacific) systems.  The Test Administrator/Manager will validate that Pacific used the same set of requirements in the development of their system interfaces.  Many job aides (interface documents, handbooks, etc.) and accessible letters form the basis for understanding the requirements for the interface development.

Most of the pertinent documentation needed to perform the Test is located on Pacific Bell’s CLEC website at https://clec.sbc.com.  The following summarizes this documentation:

- CLEC Handbook

- Overview of Workshops and OSS Classes, Class Schedule and Rates

- Ordering Forms and Job Aids

- Carrier Coding Guide

- Common Carrier Tax Exemption Guidelines

- Forecasting Forms and Procedures

- Service Area Maps (LATAs, Prefixes, NPAs, etc.)

- USOC and FID Guide

- White Page Listings User Guide

- Directory Closing Date Schedules

- PBSM Guide

- Resale User Guide

- Local Service Ordering Requirements (LSOR)

- Local Service Pre-Ordering Requirements (LSPOR)

- Accessible Letters

- IS Call Center Job Aids, Interconnection (Connectivity) Requirements, System Status

- Web Listings Lookup

- Performance Measures

- CLEC-specific Information

Test Administrator requests for additional documentation should be provided by Pacific upon request.  Test Generator requests for additional documentation should be directed to the Pacific Bell Account Team drawn from existing Account Team members, and should be provided under the same terms and conditions as provided to CLECs during the normal course of business.  Additional documentation provided to the Test Generator should be simultaneously provided to CLEC representatives on the TAB.

Other documentation may be needed.  Pacific will establish an account team to answer questions concerning other documentation.

## LSC/LOC Scalability Requirement

To support the future workloads, the amount of staff needed to provide for the level of service agreed upon must be appropriately planned.  The test efforts will not test (directly or indirectly) to verify the appropriate amount of staff, as it is not feasible to train and hire at this point in time.  However, the staff planning process (e.g., process to determine amount of staff predicted to be needed and process to provide for the staff) will be  assessed by the Test Administrator. The staff scalability review will be performed for both the LSC and LOC staff.

## Functionality Test Requirements

The purpose of the Functionality Test is to determine whether a pre-determined set of customer ordering scenarios, representing a  set of customer ordering capabilities, can be originated based on information accessed from the Pacific pre-ordering system(s).  In addition, the Functionality Test will determine whether or not the ordering scenarios can flow through the ordering, provisioning and billing systems, such that service requested is provisioned and billed accurately.

The main documents from which requirements are drawn are:

- Test Scenarios (see Attachment 1)

- The amended Joint Partial Settlement Agreement (JPSA), filed May 3, 1999, regarding Performance Measures, contain the applicable Performance Measures that will be applied to the Functionality Test, and include a high-level definition of the expected results.  There are two kinds of Performance Measures that will help evaluate the outcome of the Functionality Test:

- Parity measurements are designed to assess, for those OSS functions with retail analogs, whether the Incumbent Local Exchange Carrier (ILEC) provides access to competing carriers equal to the level that it provides itself, its customers or its affiliates, in terms of quality, accuracy, and timeliness.

- Benchmark measurements are designed to assess, whether Pacific is providing OSS access to CLECs at a level of performance that satisfies a Commission ordered standard, (i. e. benchmark where no retail analog exists).  For those OSS functions with no retail analogs, whether the ILEC provides access sufficient to allow an efficient competitor “a meaningful opportunity to compete”.  AT&T will provide proposed re-write.

### Test Scenario LSR Coverage Process Review

Functionality Test coverage is important to assure functionalities to reflect the anticipated future business environment as determined by the CPUC.  Test coverage is given in Table 6-1, which was developed during industry workshop June 7 – 15, 1999.

The Test Administrator/Manager will finalize scenarios for the Functionality Test.  The Test Administrator will ensure each unique scenario provides value-added processing, thus reducing duplication of common processes.  These unique test scenarios will provide for several iterations of similar tests to help gain a reliable statistical sample of processing and Performance Measures within the test interval.  This effort is called the test case loading.

A core set of LSRs will be used. These are broken down to the following representative mix of residential and business scenarios:

Table 6-1: Core Set of LSRs for Functionality Test.

| PRODUCTS | % of Orders (approximate) | Scenario Types by Product/Activity | %of Orders (approximate) | Res/Bus |
| --- | --- | --- | --- | --- |
| UNE Loop with Port | 38% | Retail to UNE Loop with Port Reconfigurations | 19.0% | 80%Res 20%Bus |
|  |  | Resale to UNE Loop with Port Reconfigurations | 1.9% |  |
|  |  | UNE Loop with Port – New | 3.8% |  |
|  |  | UNE Loop with Port – Changes | 7.6% |  |
|  |  | UNE Loop with Port – Disconnects | 1.9% |  |
|  |  | UNE Loop with Port - Outside Moves | 1.9% |  |
|  |  | UNE Loop with Port - Suspends | .95 |  |
|  |  | UNE Loop with Port - Restores | .95 |  |
| Stand-alone LNP | 10% | Number Portability - Retail | 9.5% | 50% Res 50% Bus |
|  |  | Number Portability - Resale | .5% |  |
| UNE 2 Wire Loops with and without Number Portability | 36% | Retail POTS to UNE Basic Loop Reconfigurations | 9.0% | 90% Bus 10% Res |
|  |  | UNE Basic Loop – New | 6.3% |  |
|  |  | UNE Basic Loop – Disconnects | .9% |  |
|  |  | Resale POTS to UNE Basic Loop Reconfigurations | 3.6% |  |
|  |  | Retail POTS to UNE Assured Loop Reconfiguration | 9.0% |  |
|  |  | UNE Assured Loop – New | 6.3% |  |
|  |  | UNE Assured Loop – Disconnects | .9% |  |
| UNE DS1 Loops without Number Portability | 5% | UNE DS1 Loop-New | 4.75% | 100% Bus |
|  |  | UNE DS1 - Disconnects | .25% |  |
| UNE xDSL Loop without Number Portability | 6% | Retail ADSL to UNE ADSL | 1.0% | 20% Res 80% Bus |
|  |  | UNE xDSLs - New | 4.5% |  |
|  |  | UNE xDSL - Disconnects | .50% |  |
| Stand-alone Directory Listings / 911 | 5% | Req. Type J and MS Gateway 911 | 5.0% | NA |
| Totals | 100% | Totals | 100% |  |

The following sections detail the requirements for the types of scenarios to be included in the test, the requirements for each of the processes included in the scenarios and also the typical process flow expected in the Functionality Test.

### Scenarios

This section describes the types of orders, the directory listings, and the features that will be included in the test case scenarios.  These scenarios will be used as templates to create detailed orders/LSRs.  In certain instances, even though the LSRs have been correctly generated by the Test Generator, orders may require some form of manual intervention in the Pacific systems (e.g., orders that are not Automatic Order Generator (AOG) eligible).

The Functionality Test will contain both fully mechanized and partially manual service orders. Mechanized orders are LSRs that can flow-through Pacific’s electronic ordering systems without manual intervention (i.e., AOG eligible).  For orders that require manual assistance, the LSC is expected to process these manual LSRs as their Present Method of Operations (PMO) dictates.

The scenarios will consist of pre-ordering, ordering, provisioning, and billing. Some will also contain usage and maintenance and repair processing.  The following provides a high-level focus of the test scenarios based on the processes to be tested:

- Pre-Ordering (see also Section 6.3.5.1)

- Test Generator tasks include the obtaining of necessary pre-ordering information

- Must include the information the CLEC customer service representatives obtain from the pre-order systems (i.e., address validation, TN reservation, etc.) or via manual K1023 requests

- Ordering (see also Section 6.3.5.2)

- Order activities:

- New

- Reconfigurations  as specified

- Change Orders

- Suspends and Restores

- Outside Moves

- Disconnects

- Request types are:

- Original

- Supplement

- Cancellation

- Order types as listed in Table 6.1

- Initial Notification

- FOC

- Reject Notices

- Provisioning

- SOC

- Jeopardy Notices (i.e., those jeopardy situations that may occur as processing proceeds).

- Maintenance and Repair

- Planned

- Unplanned (i.e., those M&R situations that may occur as processing proceeds)

- Billing

- Daily usage tape

- Paper wholesale bill

### Types of Orders

Order types are defined as xDSL set forth in Table 6.1.  The order types defined below will be included in the Functionality Test.

Unless otherwise specified, the scenarios below include single and multi-line orders, business and residence orders, and supplementals.

#### Unbundled Network Elements (UNE)

The test scenarios to be included in this test  for Unbundled Network Elements (UNEs) are:

- Retail to UNE Loop with Port Reconfigurations - Pacific customer converts to CLEC

- Resale to UNE Loop with Port Reconfigurations - CLEC converts its own customer from Resale to UNE Loop with Port

- UNE Loop with Port - New - End-user establishes new service (UNE Loop with Port) with CLEC

- Retail to UNE Basic Loop - Pacific customer converts to CLEC, where Basic loop is leased from Pacific by CLEC

- Retail to UNE Assured Loop - Pacific customer converts to CLEC, where assured loop is leased from Pacific by CLEC

- Retail to UNE DS1Loop - Pacific customer converts to CLEC, where DS1 loop is leased from Pacific by CLEC

- Resale to UNE Basic – Pacific customer converts to CLEC where basic loop is leased from Pacific by CLEC

- Resale to UNE Assured – Pacific customer converts to CLEC where assured loop is leased from Pacific by CLEC

- UNE Basic Loop - New - End-user establishes new service (i.e., UNE Basic Loop) with CLEC

- Retail xDSL to UNE xDSL reconfigurations - Customer converts to CLEC, where xDSL leased from Pacific by CLEC

- UNE xDSL Loop - New - End-user establishes new service xDSL with CLEC

- UNE Loop with Port - Suspend and Restore - Service is suspended and restored at a later date

- UNE Loop with Port - Outside Move - End-user moves to different location/address

- UNE Loop with Port - Change - Request to change a feature

- UNE Loop with Port - Disconnect - Service is disconnected from the end-user

- UNE Basic, Assured and DS1Loops - Disconnect - Service is disconnected from the end-user

- UNE xDSL Loops- Disconnect - Service is disconnected from end-user

- UNE xDSL assured loop- Disconnect - Service is disconnected from end-user

- UNE DS1 loop- Disconnect - Service is disconnected from end-user

Note: During the Functionality Test, the end-user references above will most typically be simulated by the Test Generator executing the test (i.e., Test End-Users that represent the end-user will primarily be providing for the usage related needs of the test).

#### Other

The only other order activity included in the Functionality Testing is stand-alone Directory Listings.

### Features, Feature Compatibility’s and Directory Listings

Included within the order scenarios will be options for directory listings and features.  The following options exist for directory listings and will be tested and validated within the test scenarios:

- Main list

- Non-published

- Additional

- Dual name

- Non-listed

- Simple Caption listings.

Attachment 1 defines the list of feature types and combinations of features to be included in this test.

### Processes

Several business processes typically comprise a scenario within the Functionality Test.  The processes are:

- Pre-ordering

- Ordering

- Provisioning

- Billing

- Maintenance and Repair

#### Pre-Ordering

Pre-ordering is the process that allows CLECs the ability to query Pacific databases to verify certain information required to issue a valid LSR.  In order for the LSR to flow through the Pacific OSSs without any manual intervention, it is important that the LSR contains accurate information of the service that is being requested.  The Performance Measures will be applied to the measurements generated by the Functionality Test for pre-ordering.

The pre-order process of the Functional Test will include the following:

- Customer Service Record (CSR) - view current service records as a result of a customer providing authorization for a change

- Address Verification/Dispatch - verify service address information as registered

- Request for Telephone Number (TN) - reserve one or more telephone numbers for new connections.  Reserved TNs are available for 30 days.  TN assignment and cancellation is also included.

- Service Availability/Product and Feature Availability (PFA) - retrieve a list of services and features that are provided from a particular local serving office.  Common Language Location Identification (CLLI) Code represents the switch that provides service to the telephone number requested.

- Service Appointment Scheduling - Due Date - view available dates and appointment times for the verified address [Note: Applicable for Resale (Capacity Test only) and UNE Loop with Port.]

- Facility Availability - Access to LFACS Information (ALF) – allows the CLEC to view whether dispatch is required for connection of a new line of service at a verified residential address.  This transaction also provides Facilities, spare and defective pair information for residential customers at the verified address.

- Primary Interexchange (IXC) Carrier (PIC) selection/Local Primary Interexchange Carrier (LPIC) selection/Carrier Identification Code (CIC) – identifies the available IXC selections for customer PIC/LPIC selection at the switch level.

- Number of Rejects/Failed Inquiries

- Loop qualification via manual K1023 request.

#### Ordering

Ordering consists of the process by which the CLEC order/LSR requesting services and features is submitted to Pacific for processing.

##### Ordering Activities

During ordering, the ability of Pacific’s OSSs to provide for the processing of the CLEC’s order is being tested relative to the following ordering activities:

- Receipt and acknowledgment of LSRs

- Reject processing (i.e., mechanized edits and rejects)

- Manual or mechanized creation of the applicable service orders

- Receipt of a FOC, which is a response from the service order processor that represents the acknowledgement of receipt of an order from a CLEC.  For purposes of this test, the SOC is included in the provisioning process description area, as it represents the response from the service order processor of acknowledgement of service order completion (i.e., assignment).

- Processing through SORD distribution

- Supplemental

- Cancellations.

- During this time CLEC activity pertaining to LSRs for inbound and outbound transactions received and sent by Pacific systems will be observed for single and multi-line residential and business services.

##### Order Activities

- The Functionality Test will cover the ability of the Pacific OSSs to receive the following order activities as inbound transactions:

- New - establish a new account

- Reconfigurations - for the purposes of this test reconfigurations refers to reconfiguring from retail or resale

- Change - disconnect feature, change feature, add feature

- Suspend/Restore - suspend a customers’ service, restore the customers’ service

- Disconnect - disconnect service for an account

- Outside Move - change customer address

- The Functionality Test will cover the ability of the Pacific OSSs to send the following outbound transactions:

- Mechanized order rejection/error notification

- Order acknowledgement

- Firm Order Confirmation (FOC)

#### Provisioning

Provisioning is the ability of a system to provision features and services in the switch (and, where relevant, in the outside plant services), as requested in the LSRs.  This step will test the ability of the Pacific backend systems to provide the CLECs with the services and features being requested, as well as update the Listings and 911 databases.  The return of the service order completion notification to the CLEC indicates that provisioning is complete.  Provisioning will be considered complete once a SOC is received by the CLEC.

The  jeopardy process is included in the Functionality Test.  This process will be validated through observation of the jeopardy process.  A jeopardy is currently defined to be a condition that occurs on or before the due date, indicating that the due date is less likely to be met. Jeopardy notice conditions may occur during the process of the test. Some examples of what can cause a jeopardy are:

- No cable pair or bad cable (held order)

- xDSL binder group unavailable

- Various central office conditions (e.g. Busy CFA)

#### Billing

Billing is the ability of Pacific to provide the CLECs with an accurate wholesale bill and usage data, and billing records for the services, features, network items (e.g., loop, port) and functions that were ordered and provisioned. In addition, verification of the rate center specific charging must occur for recurring, non-recurring and usage sensitive charges and miscellaneous charges.  The primary OSS focus is to validate the ability of the billing systems to receive the input in a timely manner and process the bill accurately.

The billing test inputs for the Functionality Test consist of the test LSRs and Customer Service Records (CSRs).  The test output consists of the billing tape copies of usage feeds and wholesale bills.  The inputs will be compared with the outputs relative to the elements of each order to verify the account has been established and billed correctly, and with the same level of quality that Pacific provides to its end user customers.  In addition, the usage will be validated relative to correctness and accuracy.  This process will be done based on the Pacific printed invoice.  Inputs to the Test Administrator/Manager will be provided via paper or tape.

The Functionality Test will test the ability of Pacific to provide wholesale bills that are in compliance with Industry Guidelines such as the Ordering and Billing Forum (OBF) guidelines, excluding those guidelines that govern mechanized transmission.

Billing Validation will take place in the following manner:

- Identify and validate specific charges and adjustments

- Identify features subscribed to by customer

- Validate it is accurate and complete

- Validate timeliness (the printed invoice, and the usage transmission)

- Validate daily and monthly usage feeds for UNE records (originating and terminating records).

- The focus of the billing testing will:

- Ensure the bill complies with detail and format as indicated by Industry Guidelines such as the OBF guidelines.

- Ensure what is ordered is what is billed

- Ensure wholesale bill provides for non-recurring, recurring and usage sensitive charges

- Ensure rates are applied correctly for each product, service or element

- Ensure taxes and surcharges have been applied appropriately for the jurisdictions

- Ensure usage charges are billed within the timing limitations or criteria established by local or state jurisdictions

- Ensure products that are billed in advance, as well as, recurring and non-recurring charges are billed accurately

- Ensure discounts, adjustments and calculations are performed appropriately

- Ensure the timeliness of the bills (i.e., are they sent/received within the amount of hours/days required)

- Validate the bill data for accuracy and  understandability

- Check rounding rules are applied accurately

- Ensure prorated amounts are charged accurately according to the disconnect date

- Ensure disconnects are processed and appear accurately on the bill.

##### UNE Bill Elements

- Minimum bill elements for the UNE bill based on OBF consists of:

- Face Page

- Detail of adjustments

- Detail of Other Charges and Credits (OC & C)

- Detail of usage

- Detail of surcharges (if applicable)

- Detail of taxes

#### Maintenance and Repair

Maintenance and Repair (M&R) is the ability for the CLECs to report trouble to Pacific and check the status of the reported trouble through PBSM or EBI.  Any trouble that is related to the test scenarios and occurs within the test interval will be considered part of the test.  These unplanned troubles will require analysis and be reported by the  Pacific Bell, the Test Generator, the End User or the Test Administrator.  Therefore, the M&R testing will include planned and unplanned tests.  A select set of the Functionality Test scenarios will contain planned M&R tests.  The focus of this testing would be the evaluation of the trouble request process, status, and repair (i.e., ability to receive and process a mechanized trouble report) and the ability to perform a Mechanized Loop Test (MLT) where appropriate.  These tests will not include an evaluation of the Pacific staff to be able to perform their duties as that is already verified.  The focus of a limited set of maintenance and repair requests will be on validating the electronic process of inquiries, status, and requests.

The M&R test scope for UNE Loop with Port consists of:

- No dial tone (NDT)

- Static/Noise on the line

- Cannot call out (CCO)

- Cannot Be Called (CBC)

- Cannot Be Called (CBC intra-switch)

- Cannot call Long Distance (LD)

- Features not working

- Features not provisioned

- Cannot call 411

- Cannot accept collect calls

- Cannot call 555-1212

The methodology to be used for performing the M&R test scenario execution will consist of having a superficial (i.e., no real condition is induced or occurs) or induced (i.e., a pre-determined condition is created) condition, validating the induced conditions and then providing an M&R request.  In addition, the existing M&R process activities will be observed during the test interval.  For the UNE Loop with Port testing, the induced condition will be verified through the use of MLT (i.e., not through the use of Test End-Users) where appropriate.  Conditions will be induced at the CO and a person will be defined as the central point of contact to arrange for the condition to be induced without alerting the repair staff (there will be monitoring activities to validate various expectations and conditions of the test execution).  Table 6-2 defines potential trouble conditions and potential ways to induce the maintenance and repair test scenarios are (most inducements are expected to occur in the CO):

Table 6-2: Trouble Conditions and Associated Inducements

| Trouble Condition | Associated Inducements |
| --- | --- |
| No Dial Tone | Remove coil in CO |
| Static/noise on line | Install defective coil in CO |
| Cannot call out | Remove coil in CO |
| Cannot be called | Remove coil in CO |
| Cannot be called (intra-switch) | Translate incorrectly |
| Cannot call Long Distance | Change translations |
| Features not working | Change translations |
| Features not provisioned | Change translations |
| Cannot call 411 | Change translations |
| Cannot accept collect calls | Change translations |
| Cannot call 555-1212 | Change translations |

## Capacity Testing Requirements

The Capacity Test   evaluates whether the relevant Pacific systems have sufficient capacity to handle the additional workload introduced by the CLEC.

The balance between simplicity of testing and statistical soundness of the analysis must be reached in determining the appropriate test conditions.  For example, it will be necessary for the Test Generator to develop a tool that permits inputting a high number of LSRs required for the OSS Capacity Testing.

The Capacity Test will include tests for evaluating pre-ordering and ordering capacity.  For each of these tests and for each OSS in the pre-order and order processes, the Capacity Testing will help evaluate the selected Performance Measures (PMs).

For the ordering Capacity Test,  AOG-eligible LSRs will be used.  The intent is to validate the capacity of the systems and not the resources to perform the work as a result of manual activity.  Test conditions that provide for the mechanized error and rejections will be included.  Capacity Testing will also be performed in the production environment.  See Section 4.3.3.2 for capacity test environment needs.

Since these tests will be run in a production environment, special care is necessary to ensure there will be minimal impact on normal company business.

Special conditions (e.g., future due dates on LSRs) may be placed on the test data so that production processing is not affected.  Using an extended due date (e.g., 12/24/99) will also provide an alternative way to identify test orders for data extraction and cleanup purposes.

### Capacity Test for Pre-Ordering

The pre-order process of the Capacity Test will include the same activity list as the Functionality Test, with the exception of the manual K1023.  See Section 6.3.5.1.  For the DataGate and Verigate OSS evaluation, the Test Generator will provide Capacity Testing pre-ordering volume sufficient to cover the planned test workload at an hourly rate, which will be defined by the Test Administrator/Manager.

### Capacity Test for Ordering

LSR activities associated with the Capacity Testing for inbound and outbound transactions received by Pacific systems will be observed.  The Capacity Testing, which will generally consist of clean AOG eligible LSRs (i.e., in order to present the maximum workload), will cover the ability of the Pacific OSSs to receive residence and business, single and multiple line, and supplements and cancellations for the order types as inbound and outbound transactions as explained in Section 8.  Mechanized error rejects will also be included to test the systems ability to process these in a mechanized fashion within the volume defined.  The suspend/restore order type is not included and provisioning is not in scope.  Supplemental orders have been excluded because the Capacity Testing is flow-through only and supplements do not currently flow-through.  For EDI and LEX, the Test Generator will provide for the order volume, mix and arrival rate defined.

### Capacity Test Volume

This section describes the workload volume that will be simulated and entered directly to the Pacific systems that support CLEC business activity.   The LSRs to be included in the capacity test will be based on Table 6-3.  The Capacity Testing is limited to AOG-eligible LSRs.  Therefore, non-flow-through order types have been excluded.   These test cases are limited to the processes for pre-order and ordering.

The volumes for both the order and pre-order capacity tests will meet the equivalent of 8,400 LSRs per day.  The volume units in the order portion of the Capacity Testing are LSRs while the units for pre-orders are queries, which are estimated from the volume of LSRs.

#### Pre-Order Volume

The simulated workload volume for the pre-order Capacity Test  is estimated using the data from the order test (see Section 6.4.3.2) in addition to the data describing the distribution of the pre-order queries (see Section 6.4.4, which provides the distribution in aggregate form) for the test case scenarios.  The formula that Pacific used to determine pre-ordering volumes is as follows: 8,400 LSRs times 4.3 (average queries per LSR) equals 36,120.  Additional transactions will be processed to bring queries up to 40,000.  The hour by hour volume for pre-order testing will follow the same pattern as the order testing.

#### Order Volume

The simulated workload volume for the order Capacity Test will consist of 8,400 LSRs in a day.  The busiest hour of the day usually starts at 10 A.M.  The volume arrival rate and its associated boundaries, such as peak expectations, will be determined using historical data.  The specific hour by hour volume will be determined by the Test Administrator/Manager.

### Capacity Test Mix

The test scenarios for the Capacity Testing directly define the quantities of  order types that comprise the simulated order and pre-order transactions.  These test  cases  will be selected from the same basic group of test cases that  will be defined for the Functionality Test.  xDSL has been excluded because they are not AOG-eligible while Resale, Basic Loop with and without NP, and stand-alone LNP have been added.

For application testing, 20% of the volume will be run through the GUI interface and 80% will be run through app-to-app interfaces.

Table 6-3: Core Set of LSRs for Capacity Test

|  | % of Orders (approximate) | Scenario Types by Product/Activity | %of Orders (approximate) | Res/Bus |
| --- | --- | --- | --- | --- |
| UNE Loop with Port | 40% | Retail to UNE Loop with Port Reconfigurations | 20.0% | 80% Res 10% Bus |
|  |  | UNE Loop with Port – New | 8.0% |  |
|  |  | UNE Loop with Port – Changes | 8.0% |  |
|  |  | UNE Loop with Port – Disconnects | 4.0% |  |
| Stand-alone LNP | 10% | Stand-alone LNP | 10.0% | 50% Res 50% Bus |
| UNE 2 Wire Loops with NP | 40% | Retail to UNE Basic Loop Reconfigurations | 9.0% | 10% Res 90% Bus |
|  |  | UNE Basic Loop – New | 4.0% |  |
|  |  | UNE Basic Loop – Disconnects | 2.6% |  |
| UNE 2 Wire Loops without NP |  | Retail to UNE Basic Loop Reconfigurations | 11.4% |  |
|  |  | UNE Basic Loop – New | 4.0% |  |
|  |  | UNE Basic Loop – Disconnects | 2.5% |  |
|  |  | DS1 Loop – New | 4.0% | 100% Bus |
|  |  | DS1 Loop – Disconnects | 2.5% |  |
| Resale | 5% | Retail to Resale Migrations | 2.0% | 80% Res 20% Bus |
|  |  | Resale – New | 2.0% |  |
|  |  | Resale – Change | .5% |  |
|  |  | Resale – Disconnects | .5% |  |
| Stand-alone Directory Listings | 5% | Req. Type J | 5.0% | NA |
| Totals | 100% | Totals | 100% |  |

The Capacity Testing input mix will have these additional properties:

- It must create error conditions caused by purposeful mistakes in selected inputs which fail edit checks in the Pacific OSSs.  Although a failed transaction requires no manual work in this test, the natural occurrence of error/reject messages will be integrated into the test process.

- To attain a satisfactory volume of transactions, the mix may contain replications of transactions.

The distribution of the pre-order queries for the pre-order volume test will be determined by the Test Administrator/Manager.  The queries to be considered consist of: CSR, Address Verification/Dispatch, Request for TN, Service Availability, Service Appointment Scheduling - Due Date, Facility Availability, PIC/LPIC, and Number of Rejects/Failed Inquiries.  It is important to include each of these queries since each type of query produces a different level of processor capacity and yields a different response time (which is evaluated by at least one performance measurement.).  For example, the expected response time of the Dispatch query is about three times that of the other queries but may comprise a small percent of the query mix.

### The Scalability Analysis

The scalability analysis will be performed in two parts.  The first will assess the LSC/LOC’s ability to respond to increased workload level and provide satisfactory resources to complete the manual handling of the non flow-through LSRs.  LSC/LOC force modeling procedures and the baseline assumptions that create the resource capacity requirements on a daily basis will be examined.  The Test Administrator/Manager will perform an analysis to evaluate the scalability of staffing, workstation capacity, training, forecasting and responsiveness.

The LSC/LOC force model contains Average Work Times (AWTs) for each product included in the ordering Capacity Test.  Using the average daily workload LSC/LOC resource levels can be estimated, and the processes for the timely addition or movement of resources will be demonstrated.

An evaluation of the largely manual process for large project coordination, which is not included in the Capacity or Functionality Tests, will also be conducted by the Test Administrator/Manager.

The second part of the Scalability Analysis will assess whether Pacific’s OSS interfaces can quickly be made scalable to accommodate increases in CLEC volumes over the volume currently planned for the capacity test.  The Test Administrator/Manager will perform this analysis based on documentation provided by Pacific which details how it has designed its OSS interfaces to be scalable for increased demand.

## Test Evaluation Requirements

The requirements in this section clarify issues having to do with the test itself and how it will be conducted.  Effects on the production Performance Measures are also discussed.

### Test Documentation Requirements

There are several different kinds of documentation that will be produced to characterize the overall testing effort.  This section provides the name and intent for each of these key documents.

#### Master Test Plan

This document is the Master Test Plan (MTP).  It comprehensively describes the necessary test activities for completing the Functionality Test and the Capacity Tests.  Since this document sets an overall framework for the testing activity, it must be baselined.

One of the goals of the MTP is to help achieve a high level of joint planning, cooperation and partnering with participants in all phases of the project in order to minimize overall test time and maximize test coverage.

#### Test Generator Test Plan

The Test Generator must document their test activities in a test plan.  This plan is expected to follow a similar structure as the MTP. Specific details on the respective test approach for various activities will be provided.  This document comprehensively describes the work of that Test Generator.  The combination of the Test Generator Test Plan and the MTP together define the test specifics.  Therefore, the Test Generator Test Plan should also be baselined.

Detailed Test Plans are usually “living” documents to be updated as  modifications are made.  It provides an understanding of responsibilities and expectations of the work efforts required among everyone.

The structure of the Test Generator Test Plan will generally follow that of the MTP:

- Introduction is optional based on Test Generator’s needs

- Environment must specify the physical test environment in complete detail, most importantly the systems interfacing to the Pacific OSSs must be detailed

- Administrative Process should not be necessary as this is already part of the MTP and it is expected Test Generator will support these processes

- Requirements and Assumptions should include complete descriptions of the physical realizations of Section 6.5, especially data collection, test accounts, and Test Centers

- Test Program should include descriptions of the items listed under Functionality Test Program or Capacity Test Program depending on the type of test in the test plan.

#### Test Specification (test case)

The Test Administrator/Manager will specify the activities involved and the results expected in each planned test case within their Test Specification documents.  These documents also form the basis for the end-user Test Scripts.

The Test Specification defines the sequence of the testing and determines the contents and objectives for each  test case. Clear and concise step-by-step activities will be contained within the test specifications such that another person can execute and analyze the tests.

#### Test Scripts

Test Scripts come in two varieties. The end-user test script instructs the end-user when to place calls, invoke features, etc. during the usage test cases.  The load test script instructs the load generator which test cases and quantities are to be used during load testing.

The Test Administrator/Manager will produce Test Scripts detailing the execution of each test case.  The Functionality Test scripts will provide for the LSRs.  The Test End-Users will be used to provide for the call activities (e.g., use of the features) associated with particular LSRs (e.g., scenarios) relative to the Functionality Test.  The mechanized test inputs are the Test Cases for the Capacity Test.

#### Test Administrator/Manager Results Document

The Test Administrator/Manager will analyze the tests and produce a Test Administrator/Manager Results Document.  The Test Administrator/Manager will determine the structure and contents of the Results Document.

The Test Administrator/Manager Results should be planned so that data and calculations can be ready as soon as possible during and after the testing.  The Daily Report should be an aid in early reporting.

#### Test Administrator/Manager Evaluation Report

The Test Administrator/Manager will observe/monitor the test, evaluate the test results, and evaluate the Test Generator’s Final Test Report.  The findings will be documented in the Test Administrator/Manager’s Evaluation Report.

### Success Criteria

#### Functionality Test Success Criteria

The Functionality Test success criteria consists of the Exit Criteria for the Execution Phase of the Functionality Test (Section 7.5.3):

#### Capacity Test Success Criteria

The Capacity Test success criteria consists of the Exit Criteria for the Execution Phase of the Capacity Test (Section 8.5.3):

#### Performance Measures Success Criteria

The matrix below details the Performance Measures appropriate for Functionality and Capacity Test.  Most of the appropriate Performance Measures are associated with the Functionality Test.  The parity and benchmark expectations for these measures are as defined in the JPSA  or as ordered by the Commission (except for Measure 1, as agreed-to for this Test).

##### Functionality and Capacity Test Performance Measures

The applicable Functionality and Capacity Test related Performance Measures are defined in the matrix below.  The evaluation column indicates for which performance measures there will be a parity/benchmark comparison made.

Table 6-4, Performance Measurements

| Process | Perf Meas # | Performance Measurement |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Track FT | Evaluate FT | Track CT | Evaluate CT |
| Pre-Ordering | 1 | Average Response Time (to OSS Pre-Order Queries) | Y | Y | Y | Y |
| Ordering | 2 | Average FOC/Local Service Confirmation Notice Interval | Y | Y | Y | Y |
| Ordering | 3 | Average Reject Notice Interval | Y | Y | Y | Y |
| Ordering | 4 | Percentage of Flow-Through Orders | Y | N | Y | N |
| Provisioning | 5 | Percentage of Orders Jeopardized | Y | TBD | N | N |
| Provisioning | 6 | Average Jeopardy Notice Interval | Y | TBD | N | N |
| Provisioning | 7 | Average Completed Interval | Y | Y | N | N |
| Provisioning | 8 | Percent Completed Within Standard Interval | Y | Y | N | N |
| Provisioning | 9 | Coordinated Customer Conversion as a Percentage On-Time | Y | Y | N | N |
| Provisioning | 10* | PNP Network Provisioning | Y | Y | N | N |
| Provisioning | 11 | Percent of Due Dates Missed | Y | Y | N | N |
| Provisioning | 12 | Percent of Due Dates Missed Due to Lack of Facilities | Y | N | N | N |
| Provisioning | 13 | Delay Order Interval to Completion Date (For Lack of Facilities) | N | N | N | N |
| Provisioning | 14 | Held Order Interval | N | N | N | N |
| Provisioning | 15 | Provisioning Trouble Reports (Prior to Service Order Completion) | Y | TBD | N | N |
| Provisioning | 16 | Percentage Troubles in 30 Days for New Orders | Y | TBD | N | N |
| Provisioning | 17 | Percentage Troubles in 7 Days for New Orders | N | N | N | N |
| Provisioning | 18 | Average Completion Notice Interval | Y | Y | N | N |
| Maintenance | 19 | Customer Trouble Report Rate | Y | TBD | N | N |
| Maintenance | 20 | Percentage of Customer Trouble Not Resolved Within Estimated Time | Y | Y | N | N |
| Maintenance | 21 | Average Time to Restore | Y | Y | N | N |
| Maintenance | 22 | POTS Out of Service Less Than 24 Hours | Y | TBD | N | N |
| Maintenance | 23 | Frequency of Repeat Troubles in 30 Day Period | Y | TBD | N | N |
| Net. Performance | 24 | Percent Blocking on Common Trunks | N | N | N | N |
| Net. Performance | 25 | Percent Blocking on Interconnection Trunks | N | N | N | N |
| Net. Performance | 26 | NXX Loaded by LERG Effective Date | N | N | N | N |
| Net. Performance | 27 | Network Outage Notification | N | N | N | N |
| Billing | 28 | Usage Timeliness | Y | Y | N | N |
| Billing | 29 | Accuracy of Usage Feed | N | N | N | N |
| Billing | 30* | Wholesale Bill Timeliness | Y | Y | N | N |
| Billing | 31 | Usage Completeness | Y | Y | N | N |
| Billing | 32 | Recurring Charge Completeness | Y | Y | N | N |
| Billing | 33 | Non-Recurring Charge Completeness | Y | Y | N | N |
| Billing | 34 | Bill Accuracy | Y | Y | N | N |
| Billing | 35 | Duplicate Billing (Disconnect Bill Accuracy) | N | N | N | N |
| Billing | 36 | Accuracy of Mechanized Bill Feed | N | N | N | N |
| Database Update | 37 | Average Database Update Interval | Y | Y | N | N |
| Database Update | 38 | Percent Database Accuracy | Y | Y | N | N |
| Database Update | 39 | E911/911 MS Database Update Average | Y | Y | N | N |
| Colocation | 40 | Average Time to Respond to a Collocation Request | N | N | N | N |
| Colocation | 41 | Average Time to Provide a Collocation Arrangement | N | N | N | N |
| Interfaces | 42 | Percentage of Time Interface is Available | ** | ** | N | N |
| Interfaces | 43 | Average Notification of Interface Outages | ** | ** | N | N |
| Interfaces | 44 | Center Responsiveness | ** | ** | N | N |

Key for Table 6-4:

| Term | Definition |
| --- | --- |
| Track | Data will be gathered and reported |
| Evaluate | Data will be evaluated for parity performance or compliance with a benchmark |
| Y | The measure will be tracked or evaluated as a part of the results |
| N | The measure will NOT be tracked or evaluated as a part of the results |
| TBD | The Test Administrator will determine if sufficient statistical data is available for evaluation to be performed. The Commission may provide input on this. |
| * | Inclusion of this metric is inter-dependent on open issues pending CPUC decision. |
| ** | These cannot be isolated to Test Case input. Results of overall production environment reported during the test period will be considered by Test Administrator/Manager in preparing final report |

Unplanned trouble will be differentiated from planned trouble in these trouble reporting measures as applies to Measures 15, 16, 19, 22, 23.  Only unplanned troubles will be included in the report.

Parties will resolve benchmarks for 1 and 6.  Commission to determine benchmarks for 2, 3 and 18.

Performance Measure 11: Production numbers do include Due dates missed due to lack of facilities.  For the test, the Due Dates missed due to lack of facilities will be excluded.

### Test Populations and Performance Measure Computation

Both Functionality Testing and Capacity Testing will be performed in the production environment.  The workload activity presented to the system during the test execution interval will consist of activity representing three populations:

- Test Generator

- CLEC normal business

- Pacific population

#### Population Differentiation

In order to support analysis of the test and normal production, Pacific must be able to separate Test End-Users data into the “test related” and “normal business” populations.  This separation must be done in such a manner that the Performance Measures can be properly calculated.

There will be an agreement prior to the start of the Functionality Test that Test End-Users data will be distinguishable to allow easy separation from normal business production data.  The Test Administrator agrees to distinguish LSR orders by four unique Operating Company Numbers (OCNs).  The results of these LSRs will be combined for evaluation against Performance Measures.  The Purchase Order Numbers (PONs) will be required in order to track LSRs manually.  If the Capacity Test is run at a time of low production activity, the large numbers of test inputs would affect the computation of the production Performance Measures during the days of the test.

#### Production Performance Measure Computation

Pacific will be collecting the performance measure data for each production day.  The results of these measures (both raw data for computation validation and computed PMs) will be provided to the Test Administrator/Manager.  Using the collected data, Pacific must calculate the following (Note: Provision of the underlying data to the Test Administrator/Manager will assist in validation of the computations):

- The Performance Measures relevant to the Functionality Test (using only data from the Test End-Users and Pacific normal business)

- The Performance Measures relevant to the Capacity Tests (using only data from the Capacity Testing traffic, since there is no relevant Pacific normal business data for the Capacity Testing)

- The Performance Measures relevant to production (using only data from Test End-Users normal business and Pacific normal business, during like periods, insofar as possible).

Each of the above measures must be computed using only the relevant data so that there is no interaction between the tests through the data.  In addition, Capacity Test data must not affect existing production Performance Measures.  As an example to show the problem, if the Capacity Test data were to be mixed with production data, the Performance Measures would include thousands of orders with successful FOCs and no SOCs.

#### Data Collection Validation

The Test Administrator/Manager will validate that OSS performance measures that serve as criteria for OSS Testing are consistent with the business rules, method of calculation and measurable standards as defined by the Amended Joint Partial Settlement Agreement (JPSA).  Validation includes:

- Verifying that data for computation of performance measures are accurately captured from the OSSs and accurately reflect the OSS activity.

- Understanding and preventing possible sources of contamination/invalidation factors on the data.

- Securing/Storing the raw and processed data to allow for verification of test results, re-computation and re-analysis of data.

- Establishing an audit trail between processed computed data to the raw source data.

- Establishing other data collection requirements that may be required to perform established scientific standards in performing statistical analysis.

- Ensuring that data archiving is performed as defined in the OSS MTP

The Technical Advisor will review and validate that data is properly collected and properly used in computing the Performance Measures.  This will include an audit of the process for collecting and processing performance measure data relative to accuracy and clarity.  The complete set of Orders and Pre-orders will be sampled and the resulting sample tracked in DataGate, EDI, Verigate and LEX , and the associated data collection processes.  Analysis will determine that each LSR is appropriately reflected in each metric it supports.  The evaluation will emphasize the data sources and the definition of time stamps.

#### Test Data Aggregation

If a Performance Measure is to be calculated, then the test data will be used in the calculation (i.e., no test data will be eliminated unless a defined exclusion applies).  Depending on the amount of data collected during the test and factors such as geographical distribution, it may be possible to have both a sufficient sample size and the desired geographical distribution such that the measure can be computed separately for each  reporting region as identified in the JPSA. Otherwise, in order to assure that the Performance Measures will be computed only for large enough samples, the test data will be aggregated to the state level before computing the Performance Measures.

### Test Data Collection and Management Issues

The test data for each test should include:

- All test scripts

- All test inputs and outputs

- All user-oriented test activities

- All end-user-oriented test activities

- All outputs used for results analysis

Pacific and the Test Administrator/Manager will be responsible for Pacific data collection for the relevant Pacific OSSs.  The data to be used in the test must be specified as part of the test planning phase in order to allow for proper analysis and archiving.

#### Selective Sampling

In order to validate the tests, the Test Administrator must have access to test data.  For example, the Test Administrator must be able to track the progress of a specific Test End-User’s LSR through Pacific system-involved in both pre-ordering transactions and ordering for  the LSR.  If certain steps are manual, then part of the manual process must include manual tracking.

Ability to do selective sampling implies that the Test  Administrator may have access to any systems included in the testing in order to help resolve problems.  The Test  Administrator will have the choice of obtaining data directly or of having the data prepared by an appropriate SME.

If problems occur during the test execution, the Test  Administrator must have access to the data showing the failure.  In addition, the Test  Administrator must have access to SMEs who can explain the failure and indicate the scope of the impact.

#### Data Archiving

There must be an archiving period for the data.  When the tests are completed, there will be a period after the test where the data will be analyzed and referenced in order to prepare a test analysis and validation report.  Archiving the data allows for future reference to the data in case additional questions arise subsequently to the analysis period.  The archiving period shall be as agreed in the JPSA and Amended JPSA.

#### Proprietary Data Considerations

The Test Administrator and Test Generator will abide by non-disclosure agreements applying to interface development and design.

### Test Accounts/End User Data

Test accounts must be identified to provide for the functional/Performance Measures testing.  There must be enough test accounts defined to support the test loading during the functional tests in order to support acquiring the right sample amount to determine Performance Measures with a high degree of confidence (i.e., a given sample amount will help statistically assure a certain confidence level).  Since a production environment approach is being used, it must reflect “live” accounts and facilities.  These accounts and the process used to identify them are referred to as Test End-Users..  The Test End-Users will be used to primarily provide for the usage related needs of the testing.  The Test End-Users database (i.e., details of lines, customer data) will be managed by the Test Administrator/Manager, as they are responsible for the bulk of the Test End-Users related test.

A second or third line for the residential Test End-Users will be provisioned to each of the Test End-User’s homes in order to ensure their existing service is not disrupted.  Once the test has completed, these lines will be disconnected (i.e., taken out of service, the facilities will remain).

The process used to identify and manage the Test End-Users consists of:

- Determine number of Test End-Users required

- Determine distribution of Test End-Users and locations

- Identify Test End-Users/locations

- Map (e.g., services and feature test mapping) Test End-Users/locations to test scenarios/call scenarios

- Create database of mapping relationships for easy understanding and review

- Provide for environmental needs required for Test End-Users (e.g., install a second line and third line as necessary in homes)

- Determine the process of managing the Test End-User.

### Test Centers

#### Test Center Physical Description

The Test Centers include locations where OSS testing activities occurs.  This includes the LSC, the LOC, the Test Generator’s site, and selected wire centers.  There may be other sites as identified by the Test Administrator.

The Test Centers provide the physical location of the activities both in the Functionality and Capacity Tests.  There are more Test Centers expected to support the Functionality Test since it is more complex and broader than the Capacity Test.

Generally speaking, the Test Generator will initiate test activities and be the end-user of test outputs.  The Test Generator will utilize a simulated (i.e., non-production) approach with the only production part being the system interfacing to the Pacific OSSs (i.e., the systems sending data for processing).

Pacific Test Centers consist of the production operational environments, which will also process test data.  This includes Pacific Test Centers, which are responsible for producing the performance measurements.

Part of the Test Generator’s Test Plan is a complete description of each physical location where test activities are taking place and of what test activities are happening within the Test Centers.

Colocation cages in wire centers will also be identified to support DSL and LNP.

#### Test Monitoring and Validation Plan

Besides supporting the tests, these Test Centers must also be observed/monitored by the Test Administrator/Manager and/or Technical Advisor.  Part of test planning is to develop a monitoring plan which is both effective (i.e., proper observations are included) and efficient.  For a long-duration test with multiple Test Centers (e.g., like the Functionality Test), the plan will depend on effective data gathering for the Daily Report and selective physical visits to the various facilities.

##### Test Monitoring and Validation Plan Audience

The Test Monitoring and Validation Plan audience will primarily consist of the Test Administrator/Manager, Technical Advisor, the Commission   The Commission may also review and provide comments to the Monitoring and Validation plan and may participate in the monitoring and validation activities.  The plan will not be shared with Pacific to prevent the opportunity for inappropriate preparation activities to take place (e.g., key staff normally not part of the production processing environment available at the Test Center site unknowingly).  The following sections provide a high-level view of the monitoring and validation activities so as to set the stage on expectations and focus.

##### Test Monitoring Plan Needs

The following steps are necessary for the Test Administrator/Manager and Technical Advisor to develop a monitoring plan for the Test Centers:

- Obtain complete descriptions of each Test Center from the  Pacific Bell and the Test Generator.

- The Test Administrator/Manager will determine the key Test Centers to be monitored

- The Test Administrator/Manager will prepare a monitoring plan consisting of data gathering on a daily basis and of physical visits.  The physical visits will be scheduled during testing activities.  Most visits will be unscheduled (i.e., unannounced) so as to help maintain a level of “blindness.”

##### Test Monitoring and Validation Plan Structure

The Monitoring and Validation Plan will define expectations, processes, guidelines/approach and techniques of the Test Administrator/Manager required to meet the Master Test Plan responsibilities (i.e., primarily validate the test activities, most especially the results, and provide a final report).  Key sections of the plan consists of:

- Monitoring and Validation Team Structure (e.g., Test Center teams, data analysis team, etc.)

- Monitoring and Validation Team Roles and Responsibilities (e.g., monitoring visit activities, analysis focus, reporting to other team members, etc.)

- Administrative Processes (e.g., reporting processes, documenting activities, etc.)

- Test Center Monitoring and Validation Guidelines/Approach (e.g., generic guidelines, approach taken, specific activities to monitor and validation, etc.). These will be structured based on the type of Test activity being monitored/validated (i.e., Functionality, Capacity or Other)

- Monitoring and Validating Concluding activities (e.g., creation of final report cleanup, closing down)

- Other details associated with Feedback Session, Final Report and Assumptions.

##### Test Monitoring and Validation Plan Approach

The purpose of monitoring is to assure that testing operations are being properly carried out.  For Test Centers which are managing Test End-Users or with manual activities, the monitor should be able to observe actual testing activities.  In addition, the monitor should be able to view the test data collection manual processes and to talk with the test personnel to assess understanding of their assignments.

For Test Centers which are manually processing both test data and production data (e.g., the Pacific LSC), monitoring should assure that test and production work is handled the same way.  For Test Centers, which are production OSS sites, there should be no difference between processing test activities and processing production activities.  The Pacific LSC will be visited prior to the execution of the test in order for the Test Administrator/Manager to gain an understanding of specific monitoring needs based on the structure, activities within, processes and support focus of the LSC.

There is also a Test Center charged with producing production (and test) Performance Measures.  This Test Center will be visited prior to the Functionality Test in order for the Test Administrator/Manager to follow the generation of Performance Measures from data gathering through final computation.  The Test Center(s) providing test data will be monitored during the test.

The Test Administrator/Manager expects to assign monitors familiar with the normal operations of a Test Center as a monitor for that center.  The exact numbers of monitors will be determined as part of the monitoring and validation test planning.

#### Test Center Responsibilities Toward Monitors

Pacific and the Test Generator are responsible for providing for the needs of the monitors in their respective Test Centers.  All Test Centers must be prepared for monitor visits at any given point in time during the test execution and analysis phases.  There should be physical facilities for monitors to review data, observe activities and/or talk to staff.  There should be a contact for the monitor to work with to expedite data gathering; this contact could either work at the Test Center or be an individual from the  Pacific Bell assigned to travel with the monitor.

The Test Center test data records should be organized and available to the monitor, either for an overall inspection or for following details of a particular activity through the center (e.g., as part of a selective sampling).

## Assumptions

### General

The general assumptions that govern the testing consist of:

- Wherever possible, activities will be streamlined and conducted in parallel

- The Test  Administrator and Test Generator will ensure the testing does not disrupt existing customer services (e.g., E911 and other major services)

- Pacific does not participate in the monitoring of the tests (this is the Test Administrator/Manager’s and Technical Advisor’s responsibility) except as defined and/or requested by the Commission

- Test Generator access to all necessary documentation, systems (potentially including logins) and facilities (e.g., LSC, data center where system data is collected, etc.) is  identical to access provided to CLECs

- Capacity and Functionality Tests will be performed independent of each other

- Access to sites, data and other necessary information (e.g., documentation, systems) is provided to the Test Administrator within the timeframe defined

- Facilities for the Test  Administrator will be provided as necessary (e.g., desk, phone, system access, printer for reports)

- All legal and regulatory approvals have been obtained

- All test data will be collected and retained for a pre-determined amount of time

- This Master Test Plan will not include any Y2K analyses, assessment, remediation, testing or other services or deliverables related to the Y2K computer problem.

- The Test Generator test input is easily identifiable in order to support the data extraction and test cleanup needs.

- The cooperative test does not adversely impact Performance Measures

- To preserve “blindness” of testing, the following will not be shared with Pacific:

- % of mix of errors

- Details associated with the Test Specification and Test Cases

- Details associated with test interval specifics

- Details associated with test arrival rate

- Details associated with Capacity Test specifics (e.g., specific dates of the test, arrival rate)

- In addition, various monitoring techniques will be employed to validate “blindness” expectations and consistency

- A day refers to a business day consisting of a nine-hour workday of 8:00 A.M. to 5:00 P.M.

- Test data (e.g., Name, TN) will not be associated with “real” customers or existing test customers (i.e., those in the Test environment) so as to prevent clashes of data.

### Environment

The assumptions associated with the environment are:

- Testing will take place in Pacific’s production environment with input being driven from the Test Generator’s interfaces

- Environment changes will not occur without notification, including details of impacts, to the Test Administrator consistent with the special Change Management Process, where applicable

- Preparation of the environment needs for Test End-Users will not require significant infrastructure changes

- All test facilities for the Functionality Test will be disconnected/removed upon approval of test analysis exit criteria

- All testing will occur within a defined test environment (e.g., same release, communications, etc.) unless negotiated otherwise.  The releases used will be the normal business releases.  Release changes will be presented relative to impacts to the Test Administrator/Manager and other processing that may impact the testing (e.g., proposing a new release of LASR that provides for performance enhancements will impact the tests and thus testing needs to be scheduled appropriately).

- Test activity will not affect the calculation of production Performance Measures

- Capacity Test activity will not affect the calculation of Functionality Test Performance Measures.

### Staffing

The assumptions associated with staffing are:

- Pacific Staff performing the activities are the same as those performing those functions on behalf of CLECs. Test designers and executors (i.e., those creating the LSRs) are trained using standard Pacific Bell Training classes.

- Pacific will provide SMEs as requested by the Test Administrator/Manager and or the CPUC.

### Functionality Testing

#### Functionality Test – General

The assumptions associated with the Functionality Test are:

- The final number of test cases will be defined by the Test Admnistrator, and will be spread across the 4 reporting regions.

- Facilities to support -Users (e.g., additional lines, long distance charges, and coordination of activities) will be provided by Pacific under the direction of the Test Administrator.

- Computation of Performance Measures is not dependent on the length of the Functionality Test, but is dependent on obtaining a sufficient sample size

- The testing process will follow the typical processing order (e.g., pre-order, order, provisioning, and billing).  M&R can be done anytime after provisioning and posting has occurred.  The Test End-Users will be provided the usage activities for the test scripts.

- A separate report will be generated for each performance measurement

- The standard call centers are used for the test

- M&R tests require validating the service orders are posted to completion in the CABS billing system prior to execution, since only posted service orders are downloaded to the back office OSSs

- CABS BANs are established for appropriate bill periods

- Test lines are pre-established as retail, resale, and UNE Loop with Port to be used for reconfiguration, change, and disconnects for the Functionality Test.

#### Functionality Test - Execution and Analysis

The assumptions associated with the Functionality Test execution and analysis are:

- Test analysis will be done in parallel to execution where possible

- Test data from Test Generator and the End User delivered as soon as it is available and within the intervals define

- A defined bill period contains most test scenario execution (i.e., the scenarios occur within the bounds of the defined bill period)

- There are 3 bill periods (relative to the wholesale bill) within a month (i.e., the 1st, 14th and 26th usually), only 2 will be targeted for full completion of test scenarios

- A bill cycle is 30 days

- Ordering, primarily dealing with sending the LSRs, supplements and changes as a result of scenarios, will occur within the defined interval

- M&R tests require validating the service orders are posted to completion in the CABS billing systems prior to execution, since only posted service orders are downloaded to the backend OSSs.

### Capacity Testing

#### Capacity Test – General

The assumptions associated with the capacity testing are:

- The Capacity Test may be performed along with production activity

- AOG-eligible LSRs are used unless deemed otherwise based on test conditions (i.e., LSRs are accurate and the only error conditions incorporated will be those intentionally provided as part of the test)

- An extended “fictitious” due date (i.e., 12/24/99) used on the order will help prevent orders from being processed (i.e., FOC process occurs, but the provisioning process may be prevented)

- Relative to any off-hours test, it is expected minimal system activity unrelated to testing will be occurring during the testing interval

- A volume of  8,400 LSRs per test will be presented from the Test Generator  through the LEX and EDI Interface

- The volume mix is  designed based on Pacific Bell and CLEC discussions held (June 7 through 16, 1999).

- Hourly volumes will be determined based upon historical data by the Test Administrator/Manager

#### Capacity Test – Execution and Analysis

The assumptions associated with the Capacity Test execution and analysis are:

- Pre-ordering and ordering Capacity Tests can be executed independent of each other

- TNs associated with the Functionality Test will not be used for the Capacity Test

3.	The Test Generator will perform all the Pre-Ordering Capacity Testing using DataGate such that the volume will support the defined workload.

# FUNCTIONALITY TEST PROGRAM

During the Functionality Test, the pre-ordering, ordering, provisioning, maintenance and repair, and billing Functional Tests are executed.  The pre-order process includes the following functions that should be tested across the appropriate scenarios: CSR, Address Verification/Dispatch, Request for TN, Service Availability, Service Appointment Scheduling - Due Date, Facility Availability,  PIC/LPIC, and Number of Rejects/Failed Inquiries, and manual K1023 requests.  The ordering process involves the actual transmittal of the LSR from the Test Generator to Pacific with the necessary information for issuance of a service order.  Ordering/provisioning capabilities include order receipt, the return of acknowledgments, editing for valid information, the return of error information, order confirmation and the return of service order completion status.  The provisioning process provides for the assignment of facilities and associated activity with providing the service.  The billing process includes processing the wholesale bill and providing usage information.  The M&R process provides for the ability to electronically request and receive status information on requests for M&R.  It is not required that the M&R tests be run concurrently, but this can be done if it is convenient for the Functional Testing participants.

For more detail, see Sections 6.2 and 6.6.

## Organization Of Functionality Test Section

The organization of Section 7.1 shows how the process will work:

- Section 7.1.1:  lists the goals of the Functionality Test

- Section 7.1.2:  lists the roles and responsibilities of Participants involved in the

- Section 7.1.3: lists the major steps to be accomplished in the overall  process.

### Goals of the Functionality Test

The Functionality Test will validate the capability of Pacific’s systems from a mechanized and manual operations perspective . The goals are detailed below:

- Demonstrate the ability for the CLECs to obtain pre-ordering information within the Performance Measures defined

- Demonstrate the flow through capability for CLEC LSRs

- Demonstrate Pacific is providing appropriate notifications (i.e., FOCs, SOCs, jeopardies and error notices)

- Demonstrate Pacific is providing appropriate daily usage tapes and wholesale billing to CLECs to allow for timely and accurate billing and bill payment procedures

- Demonstrate Pacific’s OSSs correctly handle maintenance and repair requests initiated by the CLECs

- Demonstrate “within parity” or “within benchmark” through computation of applicable Performance Measures using test data.

It is recognized that the statistical soundness of the analysis must be considered in determining the appropriate test conditions.

### Roles and Responsibilities

This section defines the responsibilities of participants in the Functionality Test program. There are three major roles:

#### Pacific Functional Test Participant

Pacific is the provider of the OSSs under testing and has the following additional responsibilities in addition to those defined in Section 5.2.2:

- Supply Test End-Users or locations as  requested by the Test Administrator.

- Provide SME availability throughout the testing process.

#### Test Administrator/Manager

The Test Administrator/Manager evaluates the details of the Functional Test.  The Test Administrator/Manager’s responsibilities in addition to those defined in Section 5.2.4 include:

- Refine the workload mix and define scheduling of transactions

- Execute the testing in the Pacific production and Test Generator’s environment (production level interfacing software to be used) according to the Master Test Plan and associated Pacific and Test Generator Test Plan

- Monitor the testing during the Functionality Test based on monitoring the tests and analyzing the daily test progress reports produced by the Functional Testing Participants

- Validate the workload mix of transactions based on the expected load and the Test Scenario Coverage in Attachment 1

- Develop the feature matrix and combinations to be used in the tests

- Create test scripts and test cases

- Determine the number of scenarios and test cases necessary to have a statistically sound test.

#### Test Generator

The Test Generator inputs the Functional Testing data and receives the Functional Testing output.  The Test Generator’s responsibilities, in addition to those defined in Section 5.2.5, include:

- Input the workload mix of transactions based on the Test Scenario Coverage in Attachment 1

- Input the feature matrix and combinations to be used in the tests

### Functionality Test Overall Process

There are three phases to the Functionality Test Program: Planning and Preparation, Execution, and Reporting.  Each phase has three parts.  Entrance criteria describe the necessary conditions to start a phase.  Activities describe the work to be done during the phase.  Exit criteria states the necessary conditions to complete a phase.

The three major steps to be scheduled for the Functionality Test Program are:

- Functionality Test Planning and Preparation Phase.   Pacific Bell, MCIW, the Test Administrator and the Test Generator are responsible for this step.  See Section 7.3 for more detail. Entrance Criteria to Functional Test Planning and Preparation Phase.  These criteria are explained in Section 7.2.  This section is broken out separately from the rest of the Functionality Test Planning and Preparation Phase since there are more participants involved and since these high-level decisions are especially critical to the overall Functionality Test effort.

- Functional Test Execution Phase.  The Test Generator is responsible for this step.  See Section 7.3.4 for more detail.

- Functional Test Report Phase.  The Test Administrator/Manager is responsible for this step.  See Section 8.1 for more detail.

The exit criteria for test planning and preparation must be met before the test execution phase can begin.  The Test Administrator/Manager will deviate from these criteria only with the agreement of the TAB.  If the TAB does not agree, resolution will be sought with the Commission.

## Entrance Criteria to Functionality Test Planning and Preparation Phase

The following are decisions which need to be made as part of the entrance criteria to the Functional Testing Planning and Preparation Phase, as there must be a firm understanding of the technical basis and objectives of the Functional Test before the rest of the planning can be done.

- The Test Administrator selection has been finalized

- The Test Generator selection has been finalized

- The Master Test Plan has been finalized

Additional entrance requirements may be identified.  The assumptions in Section 6.6 should also be reviewed to understand additional expectations and to assure necessary up-front decisions have been made to support detailed test planning and preparation.

## Functionality Test Planning and Preparation Phase

### Functional Test Planning and Preparation Entrance Criteria

Functional Testing entrance criteria are described in Section 7.2.

### Functional Test Planning and Preparation Activities

Pacific Bell, MCIW, the Test Administrator and the Test Generator must prepare a test plan, which defines the testing approach and strategy, timeline, entrance and exit criteria for each phase.  The individual test plans are the major outputs from the preparation and planning phase. It is expected that this step will require one or more face to face meetings at which the Test Administrator/Manager and/or Technical Advisor can validate the appropriateness and accuracy of the proposed plan against the testing requirements and assumptions. Other planning and preparation outputs may include additional inputs to entrance and exit criteria specific to other Functional Test phases.

Items to be considered in the test plan are:

- Determine the complete test environment.  The Test Generator environment must be specified. It will include at least interfaces to: Verigate, DataGate, LEX, EDI and PBSM.

- Determine that the Functional Testing fits within the overall schedule and identify detailed timeline

- The Test Generator should anticipate that Functional Testing arrival rates will be designed to reflect the projected typical daytime distribution of inputs

- For any information not intended to be shared with all participants, determine specifics of how the data is to be handled

- Determine the method for storing and reporting measurements and outcomes. This includes specifying all reports to be used in the Functional Testing analysis.

- Functionality Test participants should disclose to the Test Administrator/Manager the intent to gather any necessary data

- Specify the geographical distribution of the Test End-Users

- Generate a plan relative to when, where, and how the Functional Testing should be monitored.  This includes the physical locations and facilities for each monitor.

- Determine test execution details if there is any difference from Pacific production PMO

- Identify Pacific systems that generate data used in any of the Performance Measures, together with the actual data source and how the data source will be archived

- Confirm the test data can be isolated from total production data, as explained in Section 6.5.3.  Specify how to isolate the test data from the total production data, including any Test Generator responsibilities to support data isolation.

- Identification of the Test End-Users

- Cooperative testing in a test environment where possible, in the same manner as testing with CLECs to assure readiness of the test platforms associated tools, and test scenarios.  If a test environment is not available for any GUI interface, the production environment will be used

- Identification of CLEC colocation sites and network facilities.

#### Complete Functional Testing Test Plan Execution Schedule

Since the Functional Test is an activity taking place over many days and since the preparations for test execution may be completed for some of the test scenarios before others, a detailed execution schedule can optimize the timeline by allowing some execution to start before some other scenarios are ready.  The Test  Administrator will use this methodology and timeline interval to develop their detailed test execution schedule. However, the start and end of the test execution phase will be maintained.  In addition, the Preparation Phase includes cooperative testing in a test environment, where possible, in the same manner as testing with CLECs to assure readiness of the test platforms, associated tools and test scenarios.  If a test environment is not available (e.g. GUI interface) the production environment will be used. The  cooperative testing (i.e., set of test scenarios) typically consists of a subset of the full test and provides coverage for the major functionality required for the full test.  Cooperative testing helps determine whether the test scenarios and environment are at a state to allow for continued testing.  This effort helps prevent “false starts”(e.g., all tests are executed immediately at the start of testing only to determine that a basic underlying functional need is missing.  Thus, all tests fail when a smaller subset of tests could have uncovered this situation.).

For the ordering and pre-ordering part of the Functional Testing, it should be possible to break test execution scheduling up by order type or by geography.  The additional tracking and management complications of this approach need to be addressed in the Test Plans.

For each separately scheduled part of the Functional Test, the planning and preparation phases may overlap. However, no separately scheduled execution may start until the planning and preparation phase for that separately scheduled execution are complete and approved, as determined by the Test Administrator on an exception basis.

Two (2) bill cycles will be spanned for the Functionality Test.  A billing cycle is 30 days.  The first cycle will consist of the majority of activities required for the tests.  These activities must be completed by the required completion date for the particular bill period so they are posted by the required post date and the billing can be validated.  The second will focus on potential errors and additional tests as deemed necessary.  This will also support late usage situations (e.g., late cycle disconnects). Although most scenarios will require two billing cycles, on an exception basis, some will not.

Figure 2 depicts a typical generic scenario associated with provisioning UNE Loop with Port.  This figure shows the progression of the test scenarios executed relative to activity initiated in Cycle 1.  Similar processing will occur for subsequent cycles where the test scenarios originate as shown in the Cycle 1.2 provisioning interval in the second and third weeks, which may be associated with the change order process validation.  This intends to also depict that it is not necessary to complete the entire ordering process for all test cases in Cycle 1.1 before Cycle 1.2 is started. Every scenario will be completed before the execution phase is completed, however.  This staging is done to ensure the maximum amount of value added testing is performed and the ability to have test scenarios in different states in the event that additional testing is required.  The test cleanups defined on the timeline will provide for the disconnect of all services and any other associated cleanup relative to the test activity.  The test plans of the Test Administrator need to provide for an efficient test execution schedule.  The failure of a test case will not preclude testing of other unrelated test cases.

Figure 2: Generic Scenario Execution Schedule

#### Functionality Test Planning and Preparation Activities by Role and Responsibility

##### Test Generator

The Test Generator has these responsibilities:

- Connectivity Test complete

- Obtain User ID’s  (User access to all systems and interfaces)

- Perform cooperative test in test environment or production environment if required

- Receive test cases from the Test Administrator and prepare them for input.

- Obtain Pacific documentation and training

- Develop needed interfaces

- Assess Training and Documentation

        - Test Administrator

The Test Administrator has these responsibilities:

- Train Test End-Users or contacts at locations to verify understanding of the role and receipt of the test script.

- Establish TAB

- Certify when the test environment is stable and ready for testing

- Assess Pacific documentation, training, etc.

- Assess Test Generator readiness

- Prepare detailed test scripts

- Prepare detailed test cases

- Assign test scripts to the test end-use locations and capture in documentation.

- Support the test end users.

- Support Test End-Users for UNE Loop with Port and UNE Loop (Basic & xDSL)

- Attend Pacific Bell Training

        - Pacific Bell:

The Pacific functionality test participant has these responsibilities:

- Support  the Test Administrator in data gathering or preparing for generating the test scripts as  requested

- Prepare the physical assignments of Test End-Users (e.g., new lines, etc.) to support test conditions without affecting customer service.

### Functional Testing Planning and Preparation Exit Criteria

At this time, activities in the Test Plans necessary for start of test execution must be complete.  See also Section 7.3.5.  This phase requires test script review by the Test Administrator/Manager and Technical Advisor.  The exit criteria for the Functional Test Planning and Preparation phase is that the work in the subsequent phases is understood by the Functional Testing participants and the Test Generator.  In order to validate that the planning and preparation phase is complete, the Functional Testing participants will supply the written planning outputs to the Test Administrator/Manager and will, in addition, describe these outputs to the Test Administrator/Manager in a scheduled review session.

The exit criteria for the test planning and preparation phase consists of:

- Baseline test plan for Functional Testing by Pacific Bell, MCIW, the Test Administrator and Test Generator

- Test specifications and end-user scripts reviewed by the Test Administrator/Manager

- The complete schedules, including critical path items and dependencies, defined.

- Baselined Project Plan

- Completed Risk Management assessment

- Test End User List complete

- Test Lines Installed

- Test end-users certified and trained

- Connectivity Test complete

- Appropriate CLEC network facilities are in place

- Cooperative Testing completed

- 2Q Release (ELI) is implemented successfully (currently scheduled for 8/14/99)

### Functionality Test Execution Phase

During the execution phase, the pre-ordering, ordering, provisioning, maintenance and repair, and billing elements of the Functional Testing are executed.

### Functional Testing Execution Entrance Criteria

All outputs of the previous phase.

### Functional Testing Execution Activities

The Functional Test execution activities will consist of executing the test cases as defined in the test specifications.

#### The Test Generator

The Test Generator Functional Test participant will:

- Execute Test Cases

- Report problems to Test Administrator/Manager

- Record all relevant data as defined in the Test Plan, including all data to be used in the Results.  This includes Test End-Users reports as well as systems and M&P reports.

#### The Test Administrator

The Test Administrator/Manager will:

1.	Prepare daily report (see Section 5.3.2)

2.	Monitor the testing.	Schedule weekly TAB meetings as needed

4.	Evaluate System Modification Requests (MR’s)

5.	Manage the Change Management Process

6.	Perform Scalability Analysis

7.	Produce Performance Measurements Reports

8.	Analyze Test Results

#### Pacific Bell

Pacific will:

- Induce maintenance troubles at the direction of the Test Administrator to initiate repair scenarios as agreed to during test planning

- Capture relevant data as defined in its Test Plan

- Prepare daily test activity report.

### Functional Test Execution Exit Criteria

The Execution Phase is complete when the Test Administrator/Manager concurs that the following conditions are met:

- Audit of Performance Measures applicable to test completed as provided for in JPSA and Amended JPSA, or validated in accordance with paragraph 6.5.3.3.

- All test specifications are executed 100% and classified as completed according to their plan

- All major system outputs (i.e. output files, user interfaces) have been produced and validated.

- All severity 1 and 2 modification requests have been closed or cancelled.

MR Severity guidelines to be determined by Test Administrator/Manager:

| Severity | # Definition |
| --- | --- |
| Severity Level 1 | Problem detected has halted testing progress; a fix required immediately for testing to continue. No acceptable workaround is available. The problem detected can prevent a major testing objective from being met in the current phase. Examples: abend, general protection fault, dialogue error “Critical path – requires immediate attention and action” |
| Severity Level 2 | Problem has been detected in a specific area of the system, however an acceptable workaround exists. Preferably, the problem should be fixed before using a workaround or fixed in the next run. Examples: data problem, technical environment problem, incorrect system file “Critical path – requires attention” |
| Severity Level 3 | Problem has been detected: however, progress can continue as planned. Problem investigation and resolution can be pursued the following business day. The problem should be fixed prior to the next scheduled run or test phase. It is transparent to the customer, but not the user. Examples: Validation discrepancies (base/test), dialogue branching incorrect “Non-critical path – should be fixed” |
| Severity Level 4 | Problem has been detected, however, progress can continue as planned. A determination must be made as to whether a fix will be required or deferred. Examples: Dialogue messages inconsistent, font is incorrect (screen or bill). “Non-critical path – fix may not be necessary – possibly deferred” |
| Severity Level 5 | An enhancement has been requested, however, it is not needed immediately. The enhancement may or may not be within the scope of this release. Examples: Future user requirement, change size of a window. “Non-critical path – enhancement may be deferred to a future release” |

- Test Administrator is assured that no re-testing is needed.

## Functionality Test Report Phase

In this phase, the data from the tests  has been analyzed and is being incorporated in the final report. See also Section 7.3.2.1.

### Functional Testing  Report Entrance Criteria

This phase requires the  exit criteria from the Execution Phase.

### Functional Testing  Report Activities

The Test Administrator/Manager will produce Functional Testing Results including at least:

- Test results, using criteria for success as described in the Test Plan

- Documentation of test inputs and outputs

- Documentation of the test environment.

Pacific will produce Functional Testing Results documenting at least the test environment, the applicable Performance Measures, environmental issues, outstanding issues, and problem resolutions.

The Test Administrator/Manager’s Evaluation Report will convey findings based on:

- Monitoring all phases of the Functionality Test

- Validating the Functionality Test data and results

- Evaluating the Functional Testing Results.

In addition, the Test Administrator/Manager will:

- Through sampling, verify the accuracy of each Functional Testing participant activity.  This includes validating that the test scripts are completed in the prescribed manner and that the Performance Measures are computed accurately.

- Verify the pricing in the wholesale bill is accurate

- Verify the usage extract information is accurate

- Verify the maintenance activities and measures.

### Functional Testing  Report Exit Criteria

The Test Administrator/Manager will be responsible of ensuring all documentation is complete.

These Results will be combined into a single report document and presented to the Commission as described in Section 2.0.

# CAPACITY TESTING PROGRAM

## Organization Of Capacity Test Section

A Capacity Test is very different from a Functionality Test, since it is constructed of a repeatable, controlled, simulated test workload.

The organization of Section 9.1 shows how the process will work:

- Section 9.1.1: lists the goals to be determined.

- Section 9.1.2: lists the roles and responsibilities of Participants involved in the Capacity Testing.

- Section 9.1.3: lists the major steps to be accomplished in the overall Capacity Testing process.

### Goals of the Capacity Test

The Capacity Test will assess the capability of the Pacific OSS interfaces to handle defined volumes of pre-orders and orders.  The validation process will consider two objectives:

- Establishing the stability of these systems under the  defined workload

- Determining the ability to scale for larger workloads.

### Roles and Responsibilities

This section defines the responsibilities of participants in the Capacity Test program.  There are three major roles.

#### Pacific Capacity Test Participant

Pacific must be a Capacity Testing participant as the provider of the OSSs under testing and has the following additional responsibilities as well as those in Section 5.2.2:

- Pacific will provide any OSS documentation required in the same manner as provided to CLECs and to the Test Administrator, as requested.

- Provide reports on current system use (e.g., transaction volume) and overall report of results, as requested.

- Define the log data to use for tracking required system performance analysis measurements.

#### Test Administrator/Manager

The Test Administrator/Manager is responsible for validating the Capacity Test.  Test Administrator/Manager responsibilities beyond those in Section 5.2.4 include:

- Refine the workload mix and scheduling of transactions.  An initial specification for transaction mix and volume is given in Section 6.4.4.

- Monitor and validate the pre-order and order Capacity Test activities

- Provide timely feedback throughout the process

- Statistically validate the workload (i.e., transactions) mix of transactions based on the  expected workload

- Validate test scripts.

#### Test Generator

The Test Generator inputs the Capacity Testing data and receives the Capacity Test output.  The Test Generator responsibilities, in addition to those defined in Section 5.2.5, include:

- Execute the testing using Verigate and DataGate for pre-ordering and LEX and EDI for ordering according to the workload staging during the test window

- Provide timely feedback throughout the process.

### Capacity Test Overall Process

Pre-order capacity testing and order capacity testing contain three phases:

Planning and preparation, execution, and  reporting. Each phase has three parts.  Entrance criteria describe the necessary conditions to start a phase.  Activities describe the work to be done during the phase.  Exit criteria states the necessary products to complete a phase. Pre-ordering capacity testing and ordering capacity testing are each managed according to separate timelines, as they are not interdependent.

The three major steps to be scheduled for the Capacity Test Program are:

- Capacity Test Planning and Preparation Phase.  Pacific Bell, Test  Administrator and the Test Generator are responsible for this step.  See Section s for more detail. Entrance Criteria to Capacity Test Planning and Preparation Phase.  These criteria are the same as the entrance criteria for the functionality test, described in Section 8.2. This section is broken out separately from the rest of the Capacity Test Planning and Preparation Phase since there are more Participants involved and since these high-level decisions are especially critical to the overall Capacity Test effort.

- Capacity Testing Execution Phase.  The Test Administrator and Test Generator are responsible for this step.  See Section 9.3 for more detail.

- Capacity Testing Report Phase.  The Test Administrator/Manager and the Test Generator are responsible for this step.  See Section 10.1 for more detail.

## Capacity Test Planning  and Preparation Phase

### Capacity Test Planning and Preparation Entrance Criteria

Capacity Testing entrance criteria are the same as the entrance criteria for the Functionality Test Planning and Preparation Phase described in Section 7.2, with the addition of:

- A valid test plan

- A “live” (i.e., production) test environment

- A scheduled date for the tests.

### Capacity Test Planning and Preparation Phase Activities

The Test Administrator/Manager is responsible for planning the capacity test based on the requirements in Section 6.  The first deliverable is a detailed plan for the pre-order and ordering testing, which will be provided to the Test Generator.  Both Test Generator and Test Administrator will collaborate on the finalization of this plan.  At a minimum, the test plans and test cases will address:

- The complete test environment including Verigate, DataGate, LEX and EDI.

- Entrance criteria for each phase

- Exit criteria for each phase

- The Capacity Testing fits within the overall schedule

- The test execution schedule and how it integrates into the overall timeline

- The Performance Measures that are applicable to the Capacity Testing.  See Table 6-4.

- The mechanism for generating the LSRs, which will simulate the arrival of live transactions

- The method for storing and displaying measurements and outcomes

- Determine the number of runs (of 8400) that would make up a statistically valid test (e.g. a baseline), for both ordering and pre-ordering capacity tests.

The pre-ordering and ordering Capacity Tests can be run independent of each other.  They involve separate processing (i.e., the systems used for each are distinct).  The additional tracking and management complications of this approach need to be addressed in the Test Plans.

### Capacity Testing Planning and Preparation Activities by Role and Responsibility

Capacity Testing participants have these responsibilities:

- The Test Administrator/Manager will prepare a test script outlining the input and the definition of expected observations for the pre-ordering Capacity Testing

- The Test Administrator/Manager will prepare a test case outlining the input and the definition of expected observations for the ordering Capacity Testing

- The Test Generator will debug the test scripts until they run as designed (including mechanized errors/rejects)

- The Test Administrator/Manager will have the option to complete and verify a hands-on trial of selected test cases in the test script.

- The Test Administrator/Manager will determine the number of runs required for a statistically valid capacity test.

### Capacity Testing Planning and Preparation phase Exit Criteria

The exit criteria for the Capacity Testing Planning and Preparation phase are the same as the Functionality Test Planning and Preparation phase.  This phase requires a test script validated by the Test Administrator/Manager.  A review session is required to complete this phase.  This phase requires a complete set of verified test scripts for the pre-order and test cases for the ordering tests.

## Capacity Test Execution Phase

During the execution phase, the pre-ordering and the ordering Capacity Tests are executed.  It is not anticipated that these tests be run at the same time.

### Capacity Testing Execution Entrance Criteria

The testing requires:

Output for Planning/Preparation Phase

### Capacity Testing Execution Activities

#### Test Generator

The Test Generator will:

- Conduct the pre-order Capacity Testing

- Conduct the ordering Capacity Testing

- Record all relevant data.

#### Test Administrator/Manager

The Test Administrator/Manager will:

- Observe /monitor the testing.  If the Test Administrator/Manager determines that the test does not meet expected results, it will be repeated and the reasons will be noted.

- Validate that the test scripts are completed in the prescribed manner

- Analyze scalability documentation

- Validate performance measurement calculations.

### Capacity Testing Execution Exit Criteria

A review session is required to complete this phase.  The Execution Phase is complete when the Test Administrator/Manager concurs that the following conditions are met:

- All test specifications are executed 100% and classified as completed according to their plan.  The testing against all appropriate performance measurements including associated benchmarks by total LSR and by interface, will be pass/fail as indicated in Section 6.5.2.3.1.

- All major system outputs (i.e. output files, user interfaces) have been produced and validated.

- All severity 1 and 2 modification requests have been closed or cancelled.

MR Severity Guidelines to be assigned by Test Administrator/Manager:

| Severity | # Definition |
| --- | --- |
| Severity Level 1 | Problem detected has halted testing progress; a fix required immediately for testing to continue. No acceptable workaround is available. The problem detected can prevent a major testing objective from being met in the current phase. Examples: abend, general protection fault, dialogue error “Critical path – requires immediate attention and action” |
| Severity Level 2 | Problem has been detected in a specific area of the system, however an acceptable workaround exists. Preferably, the problem should be fixed before using a workaround or fixed in the next run. Examples: data problem, technical environment problem, incorrect system file “Critical path – requires attention” |
| Severity Level 3 | Problem has been detected: however, progress can continue as planned. Problem investigation and resolution can be pursued the following business day. The problem should be fixed prior to the next scheduled run or test phase. It is transparent to the customer, but not the user. Examples: Validation discrepancies (base/test), dialogue branching incorrect “Non-critical path – should be fixed” |
| Severity Level 4 | Problem has been detected, however, progress can continue as planned. A determination must be made as to whether a fix will be required or deferred. Examples: Dialogue messages inconsistent, font is incorrect (screen or bill). “Non-critical path – fix may not be necessary – possibly deferred” |
| Severity Level 5 | An enhancement has been requested, however, it is not needed immediately. The enhancement may or may not be within the scope of this release. Examples: Future user requirement, change size of a window. “Non-critical path – enhancement may be deferred to a future release” |

- Test  Administrator/Manager determines that no retesting is required.

## Capacity Test Report  Phase

In this phase, the analysis of the tests are  compiled and reported.

### Capacity Testing  Report Entrance Criteria

This phase requires the outcomes recorded in the test  cases (i.e., a successful test execution).

### Capacity Testing  Report Activities

The Test Generator will produce Test Generator Test Results including at least:

- Test results, using criteria for success as described in the Test Plan

- Documentation of test inputs and outputs

- Documentation of the test environment.

Pacific will produce documentation for the test environment, the applicable Performance Measures, environmental issues, outstanding issues, and problem resolutions.

The Test Administrator/Manager’s Evaluation Report will convey findings based on:

- Monitoring the phases of the Capacity Test

- Validating the Capacity Test data and results

- Evaluating the Capacity Testing Test Generator’s Results.

### Capacity Testing Report Exit Criteria

These Results will be combined into a single report document and presented to the Commission.

The Test Administrator/Manager will be responsible of ensuring all documentation is complete.

# Conclusion and Summary

This Master Test Plan defines the testing environment, approach and strategy to implement functionality and capacity testing of Pacific’s OSS environment.  It includes entrance and exit criteria for each phase, identifies roles and responsibilities for each participant, and identifies processes to be followed so that the work can be scheduled and progress is adequately tracked.

It identifies success criteria and a final report that will be produced after analysis is complete.  The final report will include any non-compliance identified, as well as statistical evaluation of the data.  In addition it will assess Pacific’s documentation and training, as well as the scalability of the architecture and operations to accommodate future market growth.  This report will be used by the Commission, and as appropriate, the FCC to determine whether Pacific OSSs provide to the CLEC’s access that is at parity with Pacific’s retail access, and a meaningful opportunity for CLEC’s to compete.

# TERMINOLOGY AND GLOSSARY

This attachment lists the terminology and acronyms used in this document.

| Acronym | Term | Definition |
| --- | --- | --- |
| AC | Alternate Current |  |
| xDSL | Asymmetric Digital Subscriber Line | A general name for an evolving high speed transmission technology which uses existing copper wire from the telephone company central office to the subscriber’s premise and has electronic equipment at the central office and at the subscriber’s premises, and transmits and receives high speed digital signals |
| ALF | Access to LFACS Information |  |
| AOG eligible | Automatic Order Generator eligible | LSRs that are identified by LASR as having the potential for mechanized service order generation |
|  | Arrival Rate | Incoming number of transactions over a defined time period (typically an hour) |
| ASBS | Ancillary Services Billing System |  |
| ASG | Access Service Group |  |
| AWT | Average Work Time |  |
| BAN | Billing Account Number |  |
|  | Baseline | To identify a “base” from which subsequent work can proceed. Approved by the Commission |
|  | Basic Loop | A transmission path that connects an end-user’s premises to a Pacific Central Office |
| CABS | Carrier Access Billing System | Pacific system that provides for CLEC billing |
| CAFD | Comptroller AMA Format Description |  |
| CBC | Cannot Be Called |  |
| CCO | Cannot Call Out |  |
|  | Change Control | Process that provides an organized and formal method for managing change requests to baselined items. |
| CIC | Carrier Identification Code |  |
| CLEC | Competitive Local Exchange Carrier | A communications company which sells/re-sells communications services in direct competition with the Incumbent Local Exchange Carrier (ILEC) |
| CLLI | Common Language Location Identifier | An 11 digit alphanumeric code used as a method of identifying physical locations and equipment i.e., central offices relay racks etc. |
| CO | Central Office |  |
| CPE | Customer Premise Equipment | Customer-owned equipment |
| CPUC | California Public Utilities Commission |  |
| CSR | Customer Service Record | A record of customer specific information such as name, address, telephone number, telecommunication services subscribed to and certain other data relating to the services provided. |
| Capacity Testing | Capacity Test | Test ability of new mechanized systems to support expected 2Q2000 workloads. (). A pre-ordering and ordering test will be performed for purposes of this test. |
| DC | Direct Current |  |
| DOJ | Department of Justice |  |
| DSLAM | Digital Subscriber Line Access Multiplexer | Network Multiplexing equipment needed to support xDSL testing. |
| ECCKT | Exchange Carrier Circuit ID |  |
| EDI | Electronic Data Interchange | Interface protocol that provides for mechanized order processing. Both the CLECs and Pacific will have systems (EDI Interface) to support the EDI functionality |
|  | End-to-End Testing | For the purposes of this testing end-to-end is defined as testing to demonstrate the flow-through capability of providing local service requests to the CLECs in parity to existing retail. |
|  | Fatal Errors | Errors that have been returned to LEX or EDI from Pacific's OSSs. They can either be corrected (fatal) with a supplemental request or with a new request (super fatal). |
| FCC | Federal Communications Commission |  |
| FDD | Flexible Due Date |  |
| FOC | Firm Order Confirmation | Response from the service order processor that acknowledges successful receipt of a CLEC order (i.e., provides notification SORD edits have passed). |
| Functional Testing | Functionality Test | A documented set of instructions designed to test and/or validate specific functions of a process or system. |
| Functional testing | Federal Telecommunications Act | Referring to the Telecommunications Act of 1996 |
| GUI | Graphical User Interface | A simplified method of accessing programs within a computer by using a mouse to point to icons, which in turn cause the programs to perform a specific function. |
| ILEC | Incumbent Local Exchange Carrier |  |
| ISDN | Integrated Services Digital Network | Digital services designed for use with desktop applications, telephone switches, computer telephony and voice processing systems |
| IXC | Inter-exchange Carrier | Long-haul, long distance interLATA carriers for voice, video and data traffic. |
|  | Jeopardy (relative to Master Test Plan process) | A notice that is issued whenever a key project milestone and/or commitment is at risk according to the Master Test Plan. |
| JPSA | Joint Partial Settlement Agreement | Agreement on Performance Measures standards between Pacific and CLECs. Filed in R.97-10-16/I.97-10-017. |
| LASR | Local Access Service Request | Pacific data system which receives Local Service Requests |
| LATA | Local Access and Transport Area | As defined in 47 U.S.C. Section 3 (25) |
| LD | Long Distance | Long distance call services between LATAs, currently provided by non-Pacific company |
| LEX | Local Service Request Exchange | Ordering interface |
| LIDB | Line Information Data Base | Database used primarily for residential customers. |
| LNP | Local Number Portability |  |
| LOC | Local Operations Center | Local Operations Center that provides for provisioning and maintenance needs |
| LPIC | Local Primary Interexchange Carrier | Local primary interexchange carrier selected by end-user. |
|  | Loop | A transmission path that connects an end-user’s premises to a Pacific Central Office |
| LSC | Local Service Center |  |
| LSOR | Local Service Ordering Requirements | Document that defines the service order detailed requirements that aid the CLEC in requesting Resale and UNE services from Pacific. This document is based on the OBF Local Service Ordering Guidelines and Pacific usage definitions and rules of application. |
| LSR | Local Service Request | A form prepared by the CLEC to request Pacific to provide the services as specified in the specific tariffs/contracts agreements. Information required for administration, billing and contact details is provided for in the various fields within the LSR. |
| M&P | Methods and Procedures | Current methods and procedures (e.g., tasks) defined to support operations required. These tasks are thoroughly planned out, explained and typically are outlined in detailed steps. |
| M&R | Maintenance and Repair | Ability to provide for requests, status and resolution of potential troubles |
|  | Mechanized orders | LSRs that can flow-through Pacific’s electronic ordering system without manual intervention |
|  | Migration | Refers to “conversion as is” or “conversion as specified.” |
| MLT | Mechanized Loop Test | A mechanized test used to determine loop situations |
| MTP | Master Test Plan |  |
| MTU | Maintenance Test Unit |  |
| NDT | No Dial Tone |  |
|  | Non Fatal Errors | Errors that LASR sends to AOG error report in Folders for LSC review and processing. |
| NP | Number Portability |  |
| OBF/TCIF | Ordering and Billing Forum/ Telecommunications Interface Forum | Industry Standards Organizations dedicated to resolving critical issues such as billing format issues between competing local exchange carriers, etc. |
| OC&C | Other Charges & Credits | Other Charges and Credits Bill Section |
| OCN | Operating Company Number | A four-digit number assigned to uniquely identify CLECs. |
| OSMOP | Operator Services Marketing Order Process | Provides LIDB access. |
| OSS | Operations Support Systems | For purposes of this test OSS refers to systems that provide for the mechanized flow-through processing |
| PBSM | Pacific Bell Service Manager | A Pacific developed character based stand-alone system that provides access to Pacific’s maintenance and repair functionality. |
| PBX | Private Branch Exchange |  |
| PFA | Products and Feature Availability |  |
|  | Phase | A period within the life cycle of the project where all activities have a common goal and includes many related activities. Occurs over a specified time frame (start and end date). Examples: Planning, Preparation and Execution. The phases may overlap each other in order to streamline the process as much as possible. |
| PIC | Primary Inter-exchange Carrier | Primary interexchange carrier selected by end-user. |
| PM | Performance Measures | As defined in JPSA. |
| PMO | Present Method of Operation | Current methods and procedures used, which are typically manual and mechanized operations currently deployed and implemented that take into account present processes and functions. |
| PON | Purchase Order Number |  |
|  | Port | Unbundled switching Option A only. |
| POTS | Plain Old Telephone Service |  |
| RFP | Request For Proposal |  |
|  | Resale | Service that allows a CLEC to purchase Pacific retail services in order to resell these services to their own end-user. |
|  | Risk Management | Balancing costs of risk avoidance and the consequences of the risk |
| SME | Subject Matter Expert | Expert in defined area |
| SNI | Standard Network Interface |  |
| SOC | Service Order Completion | Response from the service order processor that acknowledges the provisioning systems provided a successful completion of the request (LSR) (i.e., provides notification the service has been provisioned). |
| SORD | Service Order Retrieval and Distribution | Pacific system used to create, store and distribute service orders to various work groups to establish service. |
|  | Test Case | Test Cases are comprised of Test Scenarios duplicated with different Test End-Users to make up the required number of test cases as they relate to UNE 3rd Party Testing (i.e., 600 Test Cases for Functionality Testing and 8,400 for Capacity Testing). |
|  | Test Scenario | A specifically defined request and activity as it relates to UNE 3rd Party Testing. These Test Scenarios total 256 for Functionality Testing and 184 for Capacity Testing. |
|  | Test Specification | Document defining test case scenarios, purpose, method, expected results required for various test phases |
| TN | Telephone Number | A number associated with a telephone service, typically 7 digits in length; the first 3 digits are associated with the prefix and the last 4 with a specific range |
| UNE | Unbundled Network Elements | As defined in FTA. |
|  | UNE Loop | A transmission path that connects an end-user’s premises to a Pacific Central Office |
| USOC | Universal Service Order Codes |  |
| USOP | Universal Service Order Practice |  |

# APPENDIX A:  ATTACHMENTS

## Attachment 1 – Test Scenario Coverage Matrix

### Attachment 1A - Functionality Test

As Attached

### Attachment 1B - Capacity Test

As Attached

## Attachment 2 – Test Case Specification Template and Example

Test Specification Template

The Test Specification Template below identifies the key components and guidelines for developing and documenting the Test Specification.  The test scenario to be validated is specified and test cases and tests to support this validation are detailed.

Table A-2: Test Specification Template

| Test Specification Template |  |  |  |  |
| --- | --- | --- | --- | --- |
| <Test Id>, <Author> (maps to the high level Test Scenarios) Test identifier is to be a unique identifier usually consisting of the requirement identifier and an agreed up suffix/prefix along with identifier of major process tested (e.g., Retail to UNE Loop with Port Reconfiguration, etc.) Introduction – Provide definition of the high level test scenario |  |  |  |  |
| 1a. Test Case #1 – Pre-ordering (requirements tested) |  |  |  |  |
| Purpose - details what the test case is trying to prove. Dependencies: - Environment needs (e.g., generic overview of process consisting of front-end systems (e.g., LEX, EDI Interface) and associated releases involved for functionality tests) - Setup activities (e.g., how handle Test End-Users) Entrance Criteria - Method - Detail the actual steps to be taken to implement the purpose statement. Include: |  |  |  |  |
| - For example, create a table to help track steps, expected results, etc. |  |  |  |  |
| Step | Expected Results | Actual Results | Pass/Fail Criteria | Comments |
| Step | Expected Results | Actual Results | Pass/Fail Criteria | Comments |
| 1b. Test Case #2 – Ordering (requirements tested) |  |  |  |  |
| Repeat steps 1 through 5 of test Case #1 |  |  |  |  |
| 1c. Test Case #3 – Billing (requirements tested) |  |  |  |  |
| Repeat steps 1 through 5 of test Case #1 |  |  |  |  |
| 1d. Test Case #4 – Maintenance (Requirements tested) |  |  |  |  |
| Repeat steps 1 through 5 of Test Case #1 |  |  |  |  |

Test Specification Example

Test specification example: Retail to UNE Loop with Port Reconfiguration (Residence and Business):

Introduction

The purpose of testing scenarios in this category is to test the ability to convert a Pacific Retail Account to a CLEC UNE Loop with Port Account.  Scenarios in this category will include Residential single and multi-lines, Business single and multi-lines, Hunting, accounts without features, accounts with single features, accounts with multiple features, and the different types of Directory Listings.

Pre-Ordering

Purpose – The purpose of Pre-Order activity is CSR, Address Verification/Dispatch, Request for TN, Service Availability, Service Appointment Scheduling - Due Date, Facility Availability, PIC/LPIC, and Number of Rejects/Failed Inquiries.

Dependencies – The only system required to do the Pre-Order activity is DataGate.   DataGate is a system used to confirm information on an LSR before submittal.  Access to DataGate is real-time.

Entrance Criteria – The entrance criteria for pre-ordering is access to DataGate.  Pacific can provide access to DataGate and assign needed ID’s. Pacific retail line(s) with associated features and directory listing information will be installed before the conversion can take place.

Table A-3: Pre-Ordering Method

| Step | Expected Results | Actual Results | Pass/Fail Criteria | Comments |
| --- | --- | --- | --- | --- |
| Pull CSR | Obtain CSR |  | Obtain CSR |  |
| Check Service Availability | Obtain Service Availability List |  | Obtain Service Availability List |  |
| Check Due Date | Obtain Due Date |  | Obtain Due Date |  |
| Pull CLLI code | Obtain CLLI Code |  | Obtain CLLI Code |  |

Ordering

Purpose – The purpose of the ordering function is to actually write the LSR to convert a customer from a Pacific retail account to a CLEC UNE Loop with Port account.

Dependencies – In order to process an order, the LSR must be generated and processed through the Test Generator EDI Interface.  Once an order has been sent from a Test Generator EDI Interface, it will be received into the Pacific EDI Interface.   The order will then process through LASR for certain edits, then process through AOG to enter SORD and Pacific backend systems for processing.  If an order is not capable of passing through AOG, it will fall out to the Pacific LSC for manual processing into SORD.  In order to set up the ordering process, connectivity must be provided to the Pacific EDI Interface.

Entrance Criteria – Test Generator EDI Interface is available in order to process orders to Pacific.

Table A-4: EDI Ordering Method

| Step | Expected Results | Actual Results | Pass/Fail Criteria | Comments |
| --- | --- | --- | --- | --- |
| Generate LSR from CSR pulled in Pre-Order | Send 850 to Pacific |  |  |  |
| Send clean 850 through the EDI Interface | Receive 997 Confirmation and 855 notifying CLEC of clean order |  | Receive 997 Confirmation and 855 notifying CLEC of clean order |  |
| Send 850 with non-fatal errors through the EDI Interface | Receive 997 Confirmation and 855 notifying CLEC that 850 had non-fatal errors |  | Receive 997 and 855 | CLEC will now be required to send an 860 to correct non-fatal errors |
| Send 860 to correct non-fatal errors | Receive 997 and 865 notifying CLEC of clean order |  | Receive 997 and 865 |  |
| Send 850 with fatal errors through the EDI Interface | Receive 997 and 855 notifying CLEC of fatal errors |  | Receive 997 and 855 | CLEC will now be required to send a new 850 to correct the fatal errors |
| Send clean 850 to correct previous 850 with fatal errors | Receive 997 and 855 notifying CLEC of clean order |  | Receive 997 and 855 |  |

Billing

Purpose – To test the ability of Pacific to render a complete and accurate wholesale bill for orders converting a Pacific retail account to a CLEC UNE Loop with Port account.

Dependencies – Copies of Wholesale invoice, Customer Service Records, service orders, usage feeds and Pacific post billing ad-hoc reports and Pacific post billing systems.

Entrance Criteria – Access to Pacific backend billing systems and Pacific OSSs.

Table A-5: Billing Usage Method

| Step | Expected Results | Actual Results | Pass/Fail Criteria | Comments |
| --- | --- | --- | --- | --- |
| Dial from Unbundled to Pacific | AMA Call Code 002, MBI01 Local intraswitch (Detail) |  | Local intraswitch (Detail) |  |
| Unbundled to Directory Assistance (DA) | AMA Call Code 009, 194 End Office DA |  | End Office DA |  |

Maintenance

Purpose – The purpose of testing maintenance is to test the ability of Pacific to respond and reconcile maintenance issues and verify MLT functionality for UNE Loop with Port.

Dependencies – Access to Pacific Bell Service Manager.  Also, escalation for maintenance issues is handled through Pacific’s Local Operating Center.  Need to ensure PBSM access and ID’s for Trouble Administration.  Ensure the service orders are posted to completion in the CABS billing systems prior to execution, since only posted service ordered are downloaded to the back office OSSs.

Entrance Criteria – Access to PBSM.

Table A-6: Maintenance Method

| Step | Expected Results | Actual Results | Pass/Fail Criteria | Comments |
| --- | --- | --- | --- | --- |
| Administer MLT Test | Obtain MLT Test |  | Obtain MLT Test |  |
| Submit Trouble Report | Receive Trouble Ticket Number & expected time for repair |  | Trouble is resolved |  |

An Order Test Scenario Example (Validation Perspective)

A high level perspective of the testing functionality consists of:

Figure A-1: Example POTS Ordering Test Flow/Environment

From a high level perspective the following shows a typical scenario to be used in the ordering portion of the validation testing.  Within each scenario a variety of data will be used to exercise various situations that can occur.  Scenario testing focuses on the flow-through processing which represents typical common processing.  It does not intend to validate each and every feature and all the combinations of features since lower levels of testing provide for these types of tests.  It would be cost-prohibitive and uncommon to test all features and combinations of features for the various services in a flow-though manner.  Rather, the Test  Administrator has determined the scope of each of the various types of tests to be executed.

Example of basic scenario execution activities may consist of:

Test Generator requests to bring existing Pacific retail service over to a CLEC as “conversion as specified” to UNE Loop with Port:

- Execute Process for Data Gathering - use DataGate for pre-ordering process

- Execute Process for Placing Order

- Execute Process for Status, Order Completion and follow-up

- Execute Process for Billing Request

- Provide Bill Verification.

- Test End-User reports no dial tone:

- Execute creation of Trouble Ticket

- Access status of Trouble Ticket

- Access Trouble Ticket completion

- An example of scenario testing validation activities is:

- Pre-ordering

- Test Generator can verify TN

- Test Generator can verify customer account information.

- Ordering

- LSR reflects template

- Output reflects order content

- Billing Order reflects Order.

- Maintenance

- Test Generator can refer as appropriate

- Test Generator can identify features subscribed to by customer.

- Billing

- Test Generator can create various adjustments (credits, etc.)

- Test Generator can identify features subscribed to by customer

- Bill reflects Sales Request.

## Attachment 3 - Proposed Daily Report - Test Status and Assessment Form

Daily Report- Proposed Test Status and Assessment Form

| Test Status and Assessment Form |  |
| --- | --- |
| Product: | Date: |
| Assessment (green, yellow, or red): |  |

|  | Milestone | Initial Plan | Current Plan |
| --- | --- | --- | --- |

Problems

| Severity | Open (ui) | Closed | Total |
| --- | --- | --- | --- |
| Critical (1) |  |  |  |
| Serious (2) |  |  |  |
| Minor (3) |  |  |  |
| Total |  |  |  |

Test Cases and Other Test Parameters

| Planned | Executed | Passed | Failed | Time in Testing | Time Remaining |
| --- | --- | --- | --- | --- | --- |

Issues

General Notes

Purpose:

Instructions for Completing

The Test Status and Assessment template provides an arena for documenting the status of the tests as they move through flow-through testing.

To easily document the outcome, simply use this worksheet as a guide for each scenario.  The spaces provided will make it easy to identify what is being tested, as well as when it is being tested, and the assessments of the designated milestones.  These assessments will be assigned a color of green, yellow, or red based on the overall status of being on schedule relative to completing final validation and functionality.

For each milestone in the template, enter the dates and commentary as they apply to the initial plan and the current plan.

The next aspect to this template is a designated section labeled “Problems”.  The chart addresses the severity of the problems, if any.  The severity is separated into three distinctions: Critical, which is identified by (1), Serious, which is identified by a (2), and Moderate, which is identified by a (3).  Each of these severities will be applied to the following categories in regard to the scenario, Open (UI) and Closed.  There is also a Total column as well as a Total row to tally up the different severalties as they occur.

The final aspect to this template is a designated section labeled “Test Cases and Other Test Parameters”.  This chart consists of five columns: planned, executed, passing, failing and time in testing.  These should be filled out on the product being tested, as the information becomes available.

# Appendix B:  Special Change Management Process

##### Purpose

Expedited Interface Change Management Process for Third Party OSS Testing:  Pacific Bell and Competitive Local Exchange Carrier (CLEC)

This documents the process by which Pacific Bell (PACIFIC) will notify CLECs and OSS Testing Third Parties of changes to the OSS interfaces during the execution phase of Third Party OSS Testing, tentatively scheduled to begin in August, 1999 and to end in October, 1999.  The parties intend for this expedited process to be used only for changes to interfaces included in the OSS Test that directly impact the ability to proceed with Third Party Testing.  This Expedited Change Management Process for changes not related to testing (e.g. would not apply to changes to interfaces not included in the Test, to the introduction of new interfaces or to the retirement of interfaces).

##### Scope

This process pertains to all ordering, pre-ordering, provisioning and maintenance electronic interfaces included in the Third Party OSS Test as determined by the Commission and reflected in the final Master Test Plan.

This document applies to PACIFIC, Third Party OSS Test participants, and all CLECs operating in California.

##### Types of Changes

This Expedited Change Management Process manages the same types of changes as the standard Change Management Process, but is focused on those software changes needed in the production environment in order to proceed with OSS Testing.

##### Change Categories

Unlike the standard Change Management Process, changes for GUI and Gateway interfaces will be handled using the same process, as described below.

##### Steps in the Expedited Process:

- During the planning phase of the OSS Test and to facilitate communications regarding the Expedited Change Management Process during the OSS Test, the Test Administrator will be provided with a list of all CLECs that are on the standard Change Management Process distribution list (“CMP CLECs”).

- The Test Administrator and/or CPUC Staff will notify all CLECs of this process.  The Test Administrator will chair the Technical Advisory Board (TAB) and will advise CMP CLECs to elect three to five representatives to the TAB.

- CLEC representatives on the TAB will meet with any interested CMP CLECs to develop and document and expedited CLEC communication process (e.g. contact lists, mode of distributing information, etc.) prior to the start of the execution phase of the OSS Test.

- Prior to making any changes subject to this Expedited Change Management Process, PACIFIC will issue written Change Notices to the entire TAB detailing any proposed changes as well as the proposed implementation dates for the changes.  Proposed implementation dates will be selected so as to balance the needs of the OSS Test against the potential disruption of services to CLECs in production. The Chair will convene the TAB within one (1) business day to discuss the proposed changes.

- CLEC representatives on the TAB will have two (2) business days after the meeting to poll CLECs and either confirm the lack of objections or raise questions and issues via a written response to the Chair and Pacific Bell.

- PACIFIC may proceed to implement the change on the proposed implementation date if there are no outstanding issues.  However, if outstanding issues exist, the Chair will convene a special session of the TAB within one (1) business day of the written response in Step 5.  During that session, TAB members will work in good faith to discuss and reach consensus on a resolution those issues.  If the chair is unable to resolve the dispute, it will take the issue to the Commission staff.  If no agreement can be reached during that meeting, Pacific will proceed to implement the noticed changes only with the approval of the commission.

##### Emergency Situations

Emergency releases or emergency implementation date changes required during the course of the OSS Test will be handled as with existing emergency processes.

Emergency releases are releases that address major software problems, production system failure or an interface failure.  These also include releases that address significant production problems and the failure of scheduled release enhancements.

The notification process interval will be handled on a case by case basis and will depend on the type and extent of the emergency.  Notification to the TAB will be sent as soon as reasonably practicable after the emergency is recognized.  The emergency notification need not be in the form of a written Change Notice, and may be sent via other expedited means (e.g., broadcast fax).

##### Managing the Process and Environment

A standing agenda item at the weekly TAB meeting will provide an opportunity for TAB members to assess the effectiveness of this Expedited Change Management Process and the need for any revisions.  The TAB will consider any proposed changes to the execution.

TAB representatives will use this opportunity to identify issues and concerns and commit to taking the appropriate action(s).

Parties are free to pursue available legal remedies as referenced in the standard Change Management Process.

# Appendix C:  Military-style Testing

The MTP is a diagnostic evaluation of OSS readiness.  In a Military Style test philosophy, a mindset of “test until you pass” is generally adopted.  The test process works as follows:

- An interface, system, or process tested by the Test Generator/Test Administrator does not meet objective criteria, standards or expectations.

- The Test Generator/Test Administrator would create a written Exception Report describing the issue(s) raised.

- The Exception Report would be delivered to the Test Administrator, as required.

- If Exception Report affects business rules or interface, it will be brought to the TAB.

- Pacific Bell would prepare a written response to the exception describing any intended fix (es).

- Pacific advises the Test Administrator that the fix is complete.  The Test Administrator gives to the Test Generator.

- If the results meet the criteria, standards, or expectations, then the process is considered complete.

- If the results affect business rules or interface, the Test Administrator will inform the TAB.

- If the applicable criteria have not been met, then repeat the process until the criteria is met.

# Appendix D: Pacific Flow-through Plan

As Attached

AOG eligible refers to those LSRs that do not require manual intervention.

Up to and including the service order distribution process (FOC) (i.e., for purposes of this test plan all steps following are considered provisioning).

Limited number of Performance Measures as defined in Section 6.4.

These Pacific systems include DataGate, EDI Interface, LASR, AOG,Folders, WSM, LEX, Verigate, EBI, MS Gateway.

The vast majority of the  proposed volume is AOG eligible. Moreover, to the extent the Capacity Test takes place during regular business hours, Pacific’s current staff will be handling their regular load.