## Current
Pending CPCN Applications
Utility | Project Description | Application Number | Type | CEQA Contract and Status | CEQA PM / Legal | Assigned Comm'r | ALJ | Projected Cost | Projected Capacity | Application Deemed Complete | PHC | Scoping Memo | Draft EIR | Final EIR | Draft Decision | Final Decision | Construction Start | On Line | Notes
Pacific Corp | Yreka-Weed 115 kV Line | A.05-12-011 | PTC | 05PS5544 / Active / ESA | Rosauer / Reiger | Peevey | Thomas | $5.3M | _____ MW | 2006-04-25 | 2006-06-20 | 2006-07-12 | Draft MND - 9/1/06 / Draft EIR - (5/29/07) | Final MND - 10/17/06 / EIR - (7/30/07) | Northern Portion (NP) - 10/2/06; Southern Portion (SP) - (8/07) | NP - 10/19/06; SP - 3/15/07 CPUC votes to do EIR on SP - Final Dec. on SF - (9/07) | NP 10/07 / SP _______. | NP 6/07; SP _____. | Project divided into Northern and Southern portions to allow Northern Portion to proceed and address protests to Southern portion separately; CPUC voted 3/15/07 to do EIR on Southern Portion - D.07-03-043.
Sierra Pacific | Hirschdale 60 kV Transmission Line | A.06-04-017 | PTC | 05PS5564 / Active / ESA | Rosauer / Boccio / Reiger & Stoddard | Grueneich | Koss | $200K | _____ MW | 2006-11-09 | TBD | N/A | Draft MND - 2/16/07 | (Final MND - 4/20/07) | (5/07) | (6/07) | Jul / Aug 2007 | Fall 2007 | PTC application deficient until 11/9/06; utility delayed in correcting deficiencies.
SCE | Riverway 66/12kV Substation | A.06-06-004 | PTC | 06PS55611 / Active / Aspen | Merlino / Reiger & Stoddard | Grueneich | Kolakowski | $11.1M | N/A | 2006-07-13 | 2006-09-18 | TBD | (Draft MND - 5/25/07) | (Final MND - 8/5/07) | (8/07) | (9/07) | (9/07) | (6/08) | 6 month delay in contract approval.
SDG&E | Sunrise 500 kV Transmission Line | A. 06-08-010 | CPCN | 05PS5558 / Active /Aspen | Blanchard / Sher | Grueneich | Weissman | $1.265B | 1000 MW | 2006-09-09 | 1/31/06 and 9/13/06 | 2006-11-01 | (8/3/07) | (11/20/07) | (12/07) | (1/08) | ASAP after CPCN det'n | June '10 | Initial application filed 12/05 was incomplete - no PEA; SDG&E supplemented application 8/2006.
SCE | Kimball 66/12 kV substation in Chino | A.06-12-032 | PTC | 06PS5652 / Active / HDR | Rosauer / Stoddard | Grueneich | Smith | $13M | N/A | (6/21/07) | TBD | TBD | (Draft MND - 12/07) | (Final MND - 3/08) | (4/08) | (5/08) | July '08 | July '09 | Construct a new substation and upgrade 8 miles of existing 66 kV line. Application filed with CPUC 12/29/06. Significant deficiencies in application are creating delays in CEQA process.
SCE | Valley - Ivy Glen 115 kV subtransmission line in southwestern Riverside County | A. 07-01-031 | PTC | 06PS5653 / Pending / Consultant selected | Uchida / Vlahos | Grueneich | Yacknin | $23M | ____ MW | 2007-02-16 | TBD | TBD | TBD | TBD | TBD | TBD | Early '08 | June '09 | New ROW needed by the LEAPs project (Lake Elsinore). SCE filed application 1/16/06.
SCE | El Casco System Project - 220/115/12 kV substation and reconductoring and replacing approx. 15 miles of a 115 kV line near Calimesa in Riverside County | A. 07-02-022 | PTC | 06PS5650 / Active / Aspen | Mosley / Reiger | Grueneich | Kolakowski | $92M (2006) | Varies - see notes | 2007-03-14 | TBD | TBD | TBD | TBD | TBD | TBD | Phase I - June '08; Phase II - June '10 | Phase I - June '09; Phase II - June '10 | Will create the El Casco System to relieve Vista and Devers Systems in northern Riverside County. Formerly named "Oak Valley". Sun Lakes community is protesting this project.
Key: (date) = projected dates; N/A = not applicable; MND = mitigated negative declaration; MW = projected carrying capacity of line; Projected Cost = Utility estimate of construction cost.

## Future
Anticipated CPCN/PTC Filings
Utility | Project | Application Type | Projected Filing Date | CEQA Contract and Status | CEQA PM / Legal | Projected Cost | Projected Capacity | Construction Start | On Line | Notes
SCE | San Joaquin Cross Valley Loop - 20 mile 220 kV line which loops into SCE's existing Big Creek No. 3-Springville 220 kV line into Rector substation in northern Tulare county | CPCN | Mid '07 | 06PS5657 / Drafting RFQ | Uchida / Reiger & Stoddard | $32M |  | Summer '08 | 4/09 | Contract Request form is signed. Waiting for project description from SCE.
Pacfic Corp | Morrison Creek Substation 69kV | PTC | Mid '07 | 06PS5021 / Active / ESA | Merlino / Rieger & Stoddard | $2M |  |  | TBD | PacifiCorp plans to file 1st quarter 2007.
SCE | Fogarty 66/12 kV substation in southwestern Riverside County in city of Lake Elsinore | PTC | April/May '07 | 06PS5653 / Pending/ Consultant selected | Uchida / Sher | $21M |  | Fall '08 | 6/09 | Project consists of the following: construct a new 115/12/kV substation in the city of Lake Elsinore; construct 6 new 12 kV underground distribution lines; loop 1 existing 115 kV subtransmission line into the proposed substation; construct 2 4.8 MVAR capacitor banks. RFQ is combined with Valley-Ivyglen.
SCE | Ritter Ranch 66/12 kV substation in City of Palmdale | PTC | Mid '07 | 06PS5673 / SOQs due March 29, 2007 / Interviews April 16 -20 | Rosauer / Chaset | $17M |  | 11/08 | 6/09 | New 66/12 kV substation in Palmdale; construct 4 new 12kV underground distribution lines; loop 2 existing 66 kV subtransmission lines into proposed substation.
SCE | Devers-Mirage 115 kV system split subtransmission line in cities of Palm Springs and Thousand Palms | CPCN | May 2007 | 06PS5651/ Pending / Consultant selected | Merlino / Reiger | $18.5 M | Not applicable | Fall '08 | 6/09 | Split the existing Devers-Mirage 115 kV system into 2 separate systems.
SCE | Tehachapi Renewable Transmission Project (TRTP) | CPCN | On or before 6/29/07 | 06PS5663 / Pending / Consultant selected | Boccio and Rahman / | $1800M | 4500 MW |  | 2011 - 2015 | Previously known as Tehachapi Phases 2, 3 and 4; SCE has begun environmental work and should begin pre-filing CEQA review in April 2007.
SCE | Stirling Solar Dish 220 kV line connecting two substations | CPCN | Late '07 |  |  |  | 500 to 850 MW
SCE | Vulcan-Green Borders 220 KV line |  | Late 2007 | [5 empty] | 2012 | New 220 kV transmission line and associated modifications to access geothermal energy.
SCE | Riverside Public Utility (RPU) 220 kV interconnection substation and 220 kV line near city of Riverside | CPCN | Mid-Late 2007 |  |  | $38M |  |  | 2008
PG&E | Chico - 115kV line - 30 miles | CPCN | TBD |  |  | TBD |  |  | TBD
PG&E | Vaca Dixon-Fulton 115 kV Connection-50 miles | PTC | TBD |  |  | <$50M |  |  | 6/2015
SCE | Heritage 66/12 kV Substation | PTC | 1st Qtr 2008 |  |  | $12M |  |  | 6/2010
SCE | Tenaja 115/12 kV Substation | PTC | 1st Qtr 2008 |  |  | $15M |  |  | 6/2010
SCE | New Porterville 66/12 kV Substation | PTC | 2nd Qtr 2008 |  |  | $12M |  |  | 6/2010
PG&E | Midway to near Gregg 500 kV line | CPCN | Spring 2008 | [5 empty] | 2012 | Upgrade to Path 15 to facilitate delivery of Tehachapi wind resources to PG&E service territory
SCE | Triton 66/12 kV Substation | PTC | 3rd Qtr 2008 |  |  | $12M |  |  | 6/2010
SCE | Pacificenter 66/12 kV Substation | PTC | 4th Qtr 2008 |  |  | $12M |  |  | 6/2011
SCE | New Hanford Substation | PTC | 2008
PG&E | Starwood/Midway intertie | PTC | 2007 |  |  | TBD |  |  | 2009

## Completed
Completed CPCN Applications
Utility | Project Description | Application Number | Type | CEQA Contract and Status | CEQA PM / Legal | Assigned Comm'r | ALJ | Projected Cost | Projected Capacity | Application Deemed Complete | PHC | Scoping Memo | Draft EIR | Final EIR | Draft Decision | Final Decision | Construction Start | On Line | Notes
SDG&E | Silvergate Substation | A.05-03-024 | PTC | Dudek / Active | Uchida / Sher | Grueneich | Allen |  |  | 10/24/05 | 4/20/06 | 7/28/06 | 10/28/05 | 5/12/06 |  | 9/7/06 - D.06-09-022
SCE | Inland Empire Valley Energy Center (IEEC) 500 kV Gen-Tie | A.06-03-028 | CPCN | N/A - see notes | N/A | Grueneich | Koss | $11M | 800+ MW | N/A | N/A | N/A | N/A | N/A | 2006-10-06 | 10/19/06 - D.06-10-048 | 1/07 | 10/07 | CEC CEQA lead for gen ties; generator to pay costs of gen tie.
SCE | Devers-Palo Verde 500 kV Transmission Line | A.05-04-015 | CPCN | 04PS5459 / Active / Aspen | Blanchard / Sher | Grueneich | TerKeurst | Cost cap $545.285M (2005 $) - see note | 1200 MW | 2005-09-30 | 2005-07-20 | 2005-08-26 | 2006-05-04 | 2006-10-23 | 2006-12-22 | 1/25/2007 - D.07-01-040 | 2007 | 12/09 | Release of final EIR delayed by Kofa Wildlife Refuge failure to provide timely comments on administrative draft. Decision adopts cost cap of $545,285,000 in 2005 dollars, which is decreased by $24,080,000 if the Devers-Harquahala line is terminated at Harquahala Junction. The maximum authorized cost is increased by $8,282,000 if the Alligator Rock—North of Desert Center route segment is used.
PG&E | Delta Distribution Planning Area | A.05-08-022 | PTC | 05PS5523 / Active / Aspen | Rahman / Reiger | Peevey | Allen | $22.4M | 450 MW | 2006-02-03 | 2006-06-14 | N/A | MND - 9/22/06 | Final MND - 12/4/06 | 2007-02-14 | 3/1/07 - D. 07-03-009 | (2nd Quarter 2007) | Summer 2007
SCE | Segment 1 - Tehachapi Renewable Transmission Plan (TRTP) 500 kV | A.04-12-007 | CPCN | 04PS5478 / Active / Aspen | Boccio / Chaset | Grueneich | ALJ Division | $80.3M | 750 MW total for Segments 1, 2, & 3 | 2005-04-06 | 2005-05-25 | 2005-06-07 | Published: 8/06 Closed review period: 9/18/06 | 2006-12-27 | 2007-01-30 | 3/1/07 - D. 07-03-012 | 2007 | Early '09 | Extensive delays caused by USFS resistence to proposed route through Angeles. EPA and the public requested a extension for the review of the draft EIR/EIS. The EIR/EIS review period was extended 15 days. City of Santa Clarita proposed an alternative route in comments on DEIR which delayed release of FEIR by 5 weeks.
SCE | Segments 2 & 3 - Tehachapi Renewable Transmission Plan (TRTP) 500 kV | A.04-12-008 | CPCN | 06PS5562 / Active / Aspen | Rahman / Chaset | Grueneich | ALJ Division | $165M | 750 MW total for Segments 1, 2, & 3 | 2005-11-20 | 2005-05-25 | 2005-06-15 | Draft EIR: 8/06 Comments Due: 10/9/06 PPH: 10/11-12/06 | 2007-01-05 | 2007-02-13 | 3/15/07 - D. 07-03-045 | 2007 | Early '10 | Initial Application filed 12/04 deemed incomplete. SCE resubmitted 9/30/2005.