September 22, 1998

TO:	Rule 22 Members

FROM:	Mark Schindel (Southern California Edison)

SUBJECT:	Preliminary Schedule Estimates for New EDI Formats

As requested at the last Rule 22 meeting on 9/1/98, the following is the response by Southern California Edison on a preliminary schedule estimate for being ready to support new EDI Formats for Billing data in ESP Consolidated option (810) and DASR/Account Maintenance (814).  The following chart provides our estimates for these EDI formats, based on our perspective of where we currently stand on these data exchanges and the work remaining.  Also, since SCE is using a quarterly release schedule for its major software implementations, we have identified the tentative release for each of these EDI formats.  If you have any questions or need further information, please contact Mark Schindel (schindme@sce.com).

Explanation of Information in the Chart:

1.	Work Effort Steps  -  are divided into Four Sections (Requirements Definition, System Specifications, System Programming & Testing, and Implementation & External Testing).  Each of these Sections is subdivided into Major Tasks and Key Deliverables.  Also, under each sections, I have indicated who is performing these tasks (i.e., joint UDC & ESP efforts or separate UDC & ESP efforts).

2.	SCE 1999 Target Release  -  identifies the timeframe (in Quarters), when SCE estimates the work of the first three Sections will be completed, so that ESPs can start their testing with us.  The designation of Quarters corresponds with SCE’s plans for 1999 to Implement major software changes in Quarterly Releases.  (NOTE: Section IV represents the work and timeframe beyond this Release, in order to get all Market Participants converted over to the New EDI formats.)

3.	EDI Formats  -  are the two formats that the Rule 22 group requested estimates from the UDCs.  These two formats currently have EDI Mapping Guides developed by their respective DA subteams.  The 810 represents the EDI Format for Billing Data exchanged in the ESP Consolidated Billing option.  The 814 represents the EDI Format for DASR and Account Maintenance exchanged in Connect, Status Notification, Disconnect, and Update.

4.	Time Estimates  -  are given for work efforts in each Section and for each Format.  These estimates represent overall elapsed time (in months) to complete the tasks within that Section.  Although both EDI Formats appear to converge at the 3rd Quarter of 1999, the time estimates for each format are separate and distinct.  For Section I, these estimates recognize that work is already in progress, and therefore represent only the estimated remaining time to complete.  Also, because there are still a number of business and policy issues that need resolving in order to complete the work in Requirements Definition (Section I), the estimates for the Systems work (Sections II, III, and IV) are still only preliminary.

| WORK EFFORT STEPS | EDI FORMATS |  |
| --- | --- | --- |
|  | 810 | 814 |
| I. Requirements Definition (work done by ESP-UDC EDI subteam) | (TIME 2 - 3 mos | ESTIMATES) 2 - 4 mos |
| A. Define Business Requirements B. Identify Data Elements C. Develop EDI Mapping Guidelines D. Document Business Case scenarios by means of EDI Tutorial documentation (to be used later as Acceptance Test Cases) Key Deliverables: Business Process Flows; Data Dictionary; EDI Mapping Guide; Business Case Scenarios EDI Tutorial documents |  |  |
| II. System Specifications (work done by each individual UDC & ESP) | 3 - 4 mos | 3 - 4 mos |
| A. Analyze Systems impacts based on Business Requirements B. Develop System design & specifications to handle requirements C. Develop Project Plan with necessary tasks, schedule, and milestones D. Develop Test Scripts to be used in Internal testing Key Deliverables: Detail System Design & Specifications; Detail Project Plan; Detail Test Scripts |  |  |
| III. System Programming & Testing (work done by each individual UDC & ESP) | 3 - 4 mos | 4 - 5 mos |
| A. Program necessary System changes based on specifications B. Prepare necessary Internal testing environment C. Execute Internal Testing of System changes with Quality Assurance against specifications & requirements Key Deliverables: Coded Programs; Test Plan; Verified Test Results |  |  |
| SCE's 1999 TARGET RELEASE: (For Completion of Work through Section III) | 3rd Qtr | 3rd Qtr |
| IV. Implementation & External Testing (coordinated work by paired UDC & ESP) | 4 - 5 mos | 5 - 6 mos |
| A. Coordinate External Testing with EDI Trading Partners B. Implement System changes in support of new EDI Format and Business Processes Key Deliverables: External Test Plan; Verified Test Results; Coordinated Implementation Plans |  |  |